## Slide 1: Chapter 2: Project Management

## Slide 2: Learning Objectives
Link information systems to business needs
Learn how to create a system request
Understand system feasibility
Learn how to perform a feasibility analysis
Understand how to select a project
Become familiar with work breakdown structure, Gantt charts & network diagrams
Become familiar with use-case driven effort estimation
Learn how to create an interactive project workplan
Learn how to manage the scope, refine estimates and manage the risk of a project
Become familiar with how to staff a project
Learn how the environment and infrastructure workflows interact with the project management workflow

## Slide 3: Introduction
Project Management is the process of planning and controlling system development within a specified time at a minimum cost with the right functionality
A project is a set of activities with a specified beginning and end point meant to create a system that brings value to the business
Project Managers monitor and control all tasks and roles that need to be coordinated
Inception phase: generate a system request based on a business need or opportunity
Perform a feasibility analysis; revise the system request
Approve or decline the project

## Slide 4: Project Identification
Projects are driven by business needs
  Identified by business people
  Identified by IT people
  (better yet) identified jointly by business and IT
The project sponsor believes in the system and wants to see it succeed
  Normally this is a business person
  Should have the authority to move it forward

## Slide 5: Business Value
Tangible Value
  Can be quantified and measured directly
  Example: 2 percent reduction in operating costs
Intangible Value
  We know it will add value & save time, but we may not be able to quantify or measure its benefits
  Example: improved customer service

## Slide 6: The System Request
A document that describes the reasons for and the value added from building a new system
Contains 5 elements:
  Project sponsor: the primary point of contact for the project
  Business need: the reason prompting the project
  Business requirements: what the system will do
  Business value: how will the organization benefit from the project
  Special issues: Anything else that should be considered

## Slide 7: Feasibility Analysis
Is this project feasible?
  What are the risks?
  Can these risks be overcome?
Major components:
  Technical feasibility (Can we build it?)
  Economic feasibility (Should we build it?)
  Organizational feasibility (Will they use it?)

## Slide 8: Technical Feasibility
Identify risks in the following areas:
  The functional area: Are analysts familiar with this portion of the business?
  The technology: Less familiarity generates more risk
  Project size: Large projects have more risk
  Compatibility: Difficult integration increases the risk

## Slide 9: Economic Feasibility (Cost-Benefit Analysis)
Identify the costs and the benefits
Assign values to the costs and benefits
Determine the cash flow
Determine the value using one or more methods:
  Net present value (NPV)
  Return on investment (ROI)
  Break-even point

## Slide 10: Formulas for Determining Value

## Slide 11: Example Cost-Benefit Analysis

## Slide 12: Example Break-Even Point

## Slide 13: Organizational Feasibility
Will the users accept the system?
Is the project strategically aligned with the business?
Conduct a stakeholder analysis
  Project champion(s)
  Organizational management
  System users
  Others

## Slide 14: Project Selection
Projects are approved, declined or delayed based on value added vs. risks
Project portfolio management
  Goals:
    Maximize cost/benefit ratio
    Maintain an optimal mix of projects based on:
      Risk
      Size, cost & length of time to complete
      Purpose, scope & business value
  Limited resources require trade-offs
Selected projects enter the project management process

## Slide 15: Project Management Tools
Aids in creating workplans
Identify all tasks, their sequence and estimate the time to complete each one
Work breakdown structures (WBS): a hierarchy of tasks to identify:
  Duration of each task
  Current status of each task
  Task dependencies (shows which tasks must be completed before others can begin)
Gantt charts: horizontal bar chart that shows the WBS graphically
Network diagrams: PERT and CPM

## Slide 16: Project Effort Estimation
Estimation involves trade-offs between functionality, time and cost
It is the process of assigning projected values for time and effort
Most accurate estimates come from experience
Use-case point method; based on:
  Technical complexity factors (13)
  Environmental factors (8)

## Slide 17: Use-case Estimation Example
Actors & Use-cases:

## Slide 18: Use-case Estimation Example
Technical complexity factors:

## Slide 19: Use-case Estimation Example
Environmental factors & final estimate:

## Slide 20: Creating & Managing the Workplan
Workplan: a dynamic and sequential list of all tasks needed to complete a project
Approaches:
  Modify existing or completed projects
  Derive the tasks from the methodology being used
Unified Process:
  Iterative & incremental
  Workplan is also iterative & incremental
    Tasks and time intervals follow the phases
    Different tasks executed for each workflow

## Slide 21: Evolutionary Work Breakdown Structures
Organized in a standard manner across all projects
Created in an incremental & iterative manner
Generality supports learning from past mistakes and successes
Unified Process:
  Workflows are the major divisions
  Workflows are decomposed along the phases
  Phases are decomposed along the required tasks
  Tasks are added as each iteration is completed

## Slide 22: Scope Management
Scope “creep”
  Occurs after the project is underway
  Results from adding new requirements to the project
  Can have a deleterious effect on the schedule
Techniques to manage the project scope:
  Identify all requirements at the outset
  Allow only those changes deemed absolutely necessary
  Carefully examine the impact of suggested changes
  Delay some changes for “future enhancements”
  Time boxing

## Slide 23: Staffing the Project
Goals:
  Determine how many people are required
  Match skill sets to required activities
  Motivate the team to meet the objectives
  Minimize conflicts
Deliverable—The staffing plan, which includes:
  Number & kind of people assigned
  Overall reporting structure
  The project charter (describes the project’s objectives and rules)

## Slide 24: Creating a “Jelled” Team
A team of people so strongly knit that the whole is greater than the sum of its parts
Characteristics of a jelled team:
  Very low turnover rate
  Strong sense of identity
  A feeling of eliteness
  Team vs. individual ownership of the project
  Team members enjoy their work

## Slide 25: The Staffing Plan
Calculate the number of people needed:
Lines of communication increase exponentially as people are added to a project
Create a reporting structure for projects with large numbers of people assigned
Form sub-teams as necessary
Assign the Project Manager, Functional lead & Technical lead
Pay attention to technical and interpersonal skills

## Slide 26: Motivating People
Motivation is the greatest influence on performance
Monetary rewards usually do not motivate
Suggested motivating techniques:
  20% time rule
  Peer-to-peer recognition awards
  Team ownership (refer to the team as “we”)
  Allow members to focus on what interests them
  Utilize equitable compensation
  Encourage group ownership
  Provide for autonomy, but trust the team to deliver

## Slide 27: Handling Conflict
Preventing or mitigating conflict:
  Cohesiveness has the greatest effect
  Clearly defining roles and holding team members accountable
  Establish work & communications rules in the project charter
Additional techniques:
  Clearly define plans for the project
  Make sure the team understands the importance of the project
  Develop detailed operating procedures
  Develop a project charter
  Develop a schedule of commitments in advance
  Forecast other priorities and their impact on the project

## Slide 28: Environment & Infrastructure Management
Environment—Choose the right set of tools
  Use appropriate CASE tools to:
    Increase productivity and centralize information (repository)
    Utilize diagrams—more easily understood
  Establish standards to reduce complexity
Infrastructure—Document the project appropriately
  Store deliverables & communications in a project binder
  Use Unified Process standard documents
  Don’t put off documentation to the last minute

## Slide 29: Summary
Project Initiation
Feasibility Analysis
Project Selection
Traditional Project Management Tools
Estimating Project Effort
Create and manage the workplan
Staff the project
Manage the environment and infrastructure work flows of the project