COSMOS Documentation Series

COSMOS
User's Guide

#### Version 4.1

The Software Cost Modeling System
By ETSU Design Studio Groups at

Oak Ridge

This manual was produced using HelpBreeze®, by Solutionsoft.

Solutionsoft

370 Altair Way, Suite 200

Synnyvale, CA 94086

www.solutionsoft.com

 1996, 1998 East Tennessee State University - Department of Computer and Information Sciences.  All rights reserved.

Printed in the United States of America

Arial and Times New Roman fonts.  Copyright  1991 Monotype Corporation PLC.  All rights reserved.

Companies, names, and data used in examples herein are fictitious unless otherwise noted.

MS-DOS is a registered trademark of Microsoft Corporation.

Windows and Windows NT are trademarks of Microsoft Corporation

IBM and OS/2 are registered trademarks of International Business Machines, Inc.

Arial and Times New Roman are registered trademarks of The Monotype Corporation PLC.

The "Black Hole" image was obtained from NASA Archives.

Contents

Revisions	i

Revision 1.1  10/11/1995	i

Revision 1.2  11/1/1995	i

Revision 1.3  1/14/1996	ii

Revision 1.4  3/8/1996	ii

Revision 2.1  4/1/1996	ii

Revision 2.2  4/18/1996	ii

Revision 3.1 11/15/1997	ii

Revision 3.2 12/07/1997	iii

Revision 3.3 03/01/1998	iii

Revision 4.1 04/05/1998	iii

Getting Started	1

Using This Guide	1

COSMOS Conventions	1

Document Conventions	1

Keyboard Conventions	2

Hardware Requirements	2

Software Requirements	2

Product Information	2

Starting COSMOS	3

Chapter 1  Introducing COSMOS	4

The COSMOS Planning Tool	4

Function Point Analysis	4

User Identifiable Function Types	5

Processing Complexity Traits	6

Effort Estimation via COCOMO	7

Product Attributes	8

Hardware Attributes	8

Personnel Attributes	8

Project Attributes	8

Effort Estimation via Rayleigh	10

Projects	10

Systems	11

Chapter 2  Understanding COSMOS Basics	13

Menu Bar	13

Tool Bar	14

File Menu	16

New Dialog Box	17

Open Dialog Box	17

Save As Dialog Box	18

Print Dialog Box	18

Print Preview Window	19

Print Setup Dialog Box	20

View Menu	20

Project Menu	21

Import FP Model	22

Import COCOMO Model	22

Import Rayleigh Model	22

Export FP Model	22

Export COCOMO Model	22

Export Rayleigh Model	22

Description Dialog Box	22

Use FP Sensitivity Analysis Data	23

Use COCOMO Sensitivity Analysis Data	23

Use Rayleigh Sensitivity Analysis Data	23

Project Summary Information Window	24

System Menu	25

System Summary Information Window	26

System Level Estimation Projects Dialog Box	27

System Level Estimation Attributes Dialog Box	27

Missing Project File Dialog Box	28

Function Point Menu	29

Function Point Summary Information Window	29

Function Point Count Dialog Box	30

Value Adjustment Factor Dialog Box	31

Function Point Sensitivity Adjustments Dialog Box	32

Function Point Reverse Engineering Dialog Box	33

COCOMO Menu	34

COCOMO Summary Information Window	35

Attributes Dialog Box	36

Cost Drivers Dialog Box	37

COCOMO Sensitivity Adjustments Dialog Box	37

COCOMO Reverse Engineering Dialog Box	38

Rayleigh Menu	39

Rayleigh Summary Information Window	39

Rayleigh Attributes Dialog Box	40

Rayleigh Sensitivity Adjustments Dialog Box	41

Rayleigh Reverse Engineering Dialog Box	42

Options Menu	43

Display Options Dialog Box	44

Language Customization Dialog Box	44

Window Menu	45

Help Menu	46

Chapter 3  Managing Stand-Alone Models	47

Creating a New Model	47

Updating an Existing Model	47

Entering Model Data	47

Function Point Models	48

Entering Function Point Model Description	48

Entering Unadjusted Function Point Counts	48

Entering Value Adjustment Factors	48

Initializing Your Function Point Model	48

COCOMO Models	49

Entering COCOMO Model Description	49

Entering Attributes	49

Entering Cost Driver Ratings	49

Initializing Your COCOMO Model	49

Rayleigh Models	50

Entering Rayleigh Model Description	50

Entering Rayleigh Attributes	50

Initializing Your Rayleigh Model	50

Saving a Model	51

Closing a Model	51

Exiting COSMOS	51

Chapter 4  Managing Projects	52

Creating a New Project	52

Updating an Existing Project	52

Entering Project Data	52

Entering Project Description	52

Modifying Model Data	53

Importing A Model Into Your Project	53

Exporting A Model From Your Project	53

Initializing Your Project	53

Saving a Project	53

Closing a Project	54

Exiting COSMOS	54

Chapter 5  Managing Systems	55

Creating a New System	55

Updating an Existing System	55

Entering System Data	55

Entering System Description	55

Adding Projects to the System	56

Setting Attributes to the System	56

Initializing Your System	56

Saving a System	56

Closing a System	56

Exiting COSMOS	57

Chapter 6  Using Advanced COSMOS Features	58

Sensitivity Analysis	58

Entering Function Point Sensitivity Adjustments	58

Entering COCOMO Sensitivity Adjustments	59

Entering Rayleigh Sensitivity Adjustments	59

Using Sensitivity Analysis in Projects	60

Viewing Sensitivity Analysis Results	60

Saving, Importing, and Exporting Sensitivity Analysis Adjustments	60

Reverse Engineering	60

Using Function Point Reverse Engineering	61

Using COCOMO Reverse Engineering	61

Using Rayleigh Reverse Engineering	61

Chapter 7  Printing	63

Printing Models/Projects	63

Previewing	63

Setting Up Your Printer	63

Appendix A  COSMOS System Messages	65

Message Boxes	65

About Message Box	65

Bad File Type Message Box	65

Close Message Box	65

COCOMO Initialization Message Box	65

Function Point Initialization Message Box	65

Rayleigh Initialization Message Box	65

Integer Message Box	66

Load Languages for Customization Message Box	66

Project Initialization Message Box	66

Save As Message Box	66

COSMOS.INI File Not Found Message Box	66

Appendix B  Troubleshooting	67

Correcting System Errors	67

Appendix C  References	68

List of References	68

Glossary of Terms	69

Analyst	69

COCOMO	69

COCOMO Model	69

COCOMO Model Type	69

COCOMO Phase Distribution	69

Component	69

Constructive Cost Model	69

Cost Driver	69

EAF	70

Effort Adjustment Factor	70

Embedded Mode	70

External Input	70

External Inquiry	70

External Interface File	70

External Output	70

Function Point Model	70

Function Points	70

Internal Logical File	71

Main Build Phase	71

Model	71

Organic Mode	71

Person Month	71

Project	71

Rayleigh Model	71

Reverse Engineering	71

Semi-detached Mode	72

Sensitivity Analysis	72

SLOC	72

Software Engineer	72

Software Reliability	72

Source Lines of Code	72

System	72

TDEV	72

Turnaround Time	72

Virtual Machine	72

Index	74

# Revisions

COSMOS was produced over the course of two years as a laboratory project by career software development professionals who are graduate students in East Tennessee State University’s Software Engineering program.

## Revision 1.1  10/11/1995

This is the original version of the document.

| Added: | Getting Started |
| --- | --- |
|  | Chapter 1, Introducing Cosmos |
|  | Chapter 3, Understanding COSMOS Basics |
|  | Chapter 4, Managing Stand-Alone Models |
|  | Chapter 5, Managing Projects |
|  | Appendix A, COSMOS System Messages |
|  | Appendix D, Formulae |
|  | Appendix I, References |
|  | Glossary of Terms |
|  | Index |

## Revision 1.2  11/1/1995

| Modified: | Made corrections to improve spelling, grammar, consistency, and clarity throughout |
| --- | --- |
|  | Changed font of body text to Times New Roman |
|  | Picture on cover |
|  | Moved References to Appendix I |
|  | Changed explanation of startup conditions from displaying another dialog box after the Description Dialog Box to displaying the Summary Information Screen |
|  | Changed to clear description on initialization |
|  | Changed page size from 7 x 9 to 8.5 x 11 |
|  | Made changes to improve flow of help |
| Added: | Page references |
|  | Save/Open/Close functions in Chapters 3 - 5 |
|  | Appendix C, INI File Entries |
|  | COCOMO sections in Chapters 3 and 4 |
|  | Appendix F, Complexity Assignment Guidance |

## Revision 1.3  1/14/1996

| Modified: | Made corrections to improve spelling, grammar, consistency, and clarity throughout |
| --- | --- |
|  | Removed New Window |
|  | Updated COSMOS.INI file in Appendix C, INI File Entries |
|  | Removed Edit Menu |
|  | Updated screen shots |
|  | Chapter 2, Tutorial moved to a separate document |
|  | Manual renamed to COSMOS User's Guide |
| Added: | Import/Export FP/COCOMO Models in Project |
|  | Display Options Dialog Box |
|  | Product Information Section |

## Revision 1.4  3/8/1996

| Modified: | Corrections made to improve spelling, grammar, consistency, and clarity throughout |
| --- | --- |
|  | Menu Bar callouts added |
|  | Screen shots updated to include context sensitive help |
| Added: | Print, Print Preview, and Print Setup options |
|  | Printing Chapter |

## Revision 2.1  4/1/1996

| Modified: | Screen shots updated to reflect new version |
| --- | --- |
|  | COSMOS.INI section updated |
| Added: | Sensitivity Analysis |
|  | Using Advanced COSMOS Features Chapter |
|  | Appendix B, Troubleshooting |

## Revision 2.2  4/18/1996

| Modified: | Screen shots updated to reflect new version |
| --- | --- |
|  | COSMOS.INI section updated |
| Added: | Reverse Engineering |
|  | Saving, Importing, and Exporting Sensitivity Analysis section |

## Revision 3.1 11/15/1997

| Modified: | Hardware and software documentation requirements to reflect conversion to a 32 bit system for COSMOS version 3.1 |
| --- | --- |
| Added: | Screen shots to reflect Windows 95 standards |

## Revision 3.2 12/07/1997

| Modified: | Documentation to reflect IFPUG 4.0 terminology for COSMOS version 3.1 COSMOS.INI file to reflect the Rayleigh Model for COSMOS version 3.2 COSMOS.INI file to reflect the COCOMO Phase Distribution for COSMOS version 3.2 |
| --- | --- |
| Added: | Screen shots to reflect IFPUG 4.0 terminology Rayleigh Menu Importing and Exporting Rayleigh Models Rayleigh Attributes Rayleigh Reverse Engineering Rayleigh Sensitivity Analysis Note: The topics above have been defined in the documentation. No link connections where made to the Rayleigh Sensitivity Analysis and Reverse Engineering documentation since the functionality has not been incorporated into the COSMOS application. Screen shots to reflect COCOMO Phase Distribution Appendix G COCOMO Phase Distribution Appendix H The Rayleigh Model (provides a description of the Rayleigh model and its output - the MBI) |

## Revision 3.3 03/01/1998

| Modified: | Documentation to reflect the Rayleigh Sensitivity Analysis and Rayleigh Reverse Engineering Documentation to reflect the Intermediate COCOMO Model: Product Level Estimates |
| --- | --- |
| Added: | Screen shots to reflect Rayleigh Sensitivity Analysis and Reverse Engineering Rayleigh Sensitivity Analysis Rayleigh Reverse Engineering References made to the Intermediate COCOMO Model: Product Level Estimates Version Stamp - Check if projects and models match the COSMOS application version release. Version Stamp - Check if COSMOS.INI file match the COSMOS application version release. |

## Revision 4.1 04/05/1998

| Modified: | Removed Appendices C through H. These appendices were added to the COSMOS Technical Reference. Deleted hotspots to topics contained in Appendices C through H. Referenced COSMOS Technical Reference. Rename Appendix C to be References. New screen snapshots captured because of changes to the toolbar when adding System menus. |
| --- | --- |
| Added: | Chapter 5 Managing Systems was added. |
| Deleted: | Version Stamp - Check if projects and models match the COSMOS application version release. |

# Getting Started

## Using This Guide

This user's guide applies standardized methods for explaining windows and user input to help you take full advantage of COSMOS.

### COSMOS Conventions

COSMOS is a Microsoft Windows  application and follows the Windows conventions with regard to menu bars, menus, toolbars, window managers, and mouse and keyboard techniques.  For more information see your User's Guide for the Microsoft Windows Operating System.

Icons for frequently used functions appear on the Toolbar, which is located just below the Menu Bar.  You may enable/disable display of the Toolbar from the View Menu.

Located at the bottom of the COSMOS main window is the Status Bar which describes the currently selected menu item.  Other status information such as "Printing..." and "Ready" is also displayed here.  Again, you may enable/disable display of the Status Bar from the View Menu.

Two types of shortcut keys are provided by COSMOS.  The first type is indicated by an underlined letter on a Menu Bar or Menu item. Pressing that key is an alternate way of choosing that selection when the Menu Bar is selected or the Menu is open. See Menu Bar for more information and a diagram of the Menu Bar, showing the underlined shortcut key name.

Shortcut keys of the second type are listed to the right of menu item names.  These key combinations may be used to select the function without opening the menu.  See File Menu for a diagram of the File Menu, showing the shortcut keys for this menu.

### Document Conventions

The formatting conventions used in this guide are as follows:

| Font type | Description |
| --- | --- |
| bold | All push buttons, dialog boxes, menus, and menu items are typed in a bold font for easy identification. |
| italic | Input items are represented in italic font. For example, if the guide states that a file name is to be entered, you would type in the name of your file and not the words, "file name." |
| CAPITALS | The names of keyboard keys are represented in all uppercase |

When running COSMOS, it is possible to have multiple Models and/or Projects open at the same time, but only one of these may be active at any time.  The term "current Model" or "current Project" is used to denote the Model or Project which is currently active.

### Keyboard Conventions

Keyboard input is represented in this guide as follows:

| Notation | Description |
| --- | --- |
| KEY1+KEY2 | A plus sign (+) between two or more key names means that you need to press the keys simultaneously. For example, "Press ALT+F" means that you would press the Alt key and keep it held down while you pressed the F key. |
| KEY1,KEY2 | A comma (,) between two or more key names means that you press the keys in sequence. For example, "Press F7,4" means that you would press the F7 key then release it, and then press the 4 key. |

## Hardware Requirements

	An 80486-based computer or higher

	A mouse

	At least 8 megabytes (MB) of RAM

	A minimum of  5 MB of hard disk space

	3.5" inch disk drive, if installing COSMOS from diskette

## Software Requirements

	Microsoft Windows 95 or Windows NT version 4.0

## Product Information

This product is provided as "freeware."  Any use or sale for profit is strictly prohibited.

DISCLAIMER OF WARRANTY

This software and its manuals are being provided "as is" without warranties as to performance.  This program is being provided without any express or implied warranties whatsoever.  Because of the diversity of conditions and hardware under which this program may be used, no warranty of fitness for a particular purpose is offered.  The user must assume the entire risk of using the program.  Any liability of the provider is limited exclusively to product replacement.

This document contains material which has been extracted from the IFPUG Counting Practices Manual.  It is reproduced in this document with permission of IFPUG.

## Starting COSMOS

| COSMOS Icon | Once you have run the setup program and your installation of COSMOS is successful, you are ready to start using COSMOS. Within the Windows environment, double-click the left mouse button on the COSMOS icon or highlight the COSMOS icon and press ENTER. You may also start COSMOS by running the cosmos.exe executable file from the Windows Explorer or the Run option under the Start menu. You will then see the COSMOS Screen and Menu Bar which look like: |
| --- | --- |
|  | From here, you will have a variety of choices from which to select. Under the File Menu, you can create a new Project, Function Point Model, COCOMO Model, Rayleigh Model, or System or you can open an existing Project, Model, or System. |

# Chapter 1  Introducing COSMOS

## The COSMOS Planning Tool

COSMOS, Software Cost Modeling System, helps you to create software project plans and estimate project schedules and staffing.  It also helps to create System development estimation. It is a tool designed for predicting the size of a software system and the amount of effort required to develop it. You will find that the flexibility and control offered by COSMOS facilitates "what-if" analysis. COSMOS is based on two classic models, Function Point Analysis (FPA) and the Constructive Cost Model (COCOMO) and an alternative model, the Rayleigh Model.

COSMOS offers the Project feature because FPA results may be used as input for COCOMO analysis.  Also, COCOMO results may be used as input for Rayleigh analysis.  This feature offers you an easy way to associate function point data with your COCOMO analysis and COCOMO analysis with Rayleigh analysis.  COSMOS also offers the System feature that uses the projects' estimates to provide you with a system estimate.

If you are familiar with Microsoft Windows  applications, you will find that COSMOS follows many of the Windows conventions.  The menu bars, toolbars, dialog boxes, and pushbuttons all work in the accustomed manner to make learning COSMOS easy.

A brief introduction to FPA, COCOMO, Rayleigh, and System follows.  If you are interested in more details or formulae used for calculations see the COSMOS Technical Reference (Function Point Formulae, COCOMO formulae, Rayleigh Formulae, and System Development Estimation).

## Function Point Analysis

Function Point Analysis was developed by Allen Albrecht.  It is a methodology used to estimate the amount of "functionality" software performs in terms of data input, generated output, and file maintenance and utilization (Albrecht 83).  Function points are derived from a measurement of the software's information domain and its processing complexity.  The information domain is classified into five user identifiable function types, each of which has three levels of complexity.  The five types and their associated complexity levels are described in the following sections.  More detailed information about the User Function Types is included in the COSMOS Technical Reference (see Function Point Complexity Assignments).  COSMOS follows the counting practices as documented in the International Function Point User's Group (IFPUG) Counting Practices Manual, Version 4.0 for New Development Projects.

### User Identifiable Function Types

1. Number of External Inputs

External input  (EI) is a transactional function that processes data or control information from outside the boundary of the application under consideration.  An external input adds, modifies, or deletes information from internal logical files (described below).  The external input is unique if either the input format or the processing logic is unique.

| Complexity | Description |
| --- | --- |
| Low | Few data elements included in the external input type and a limited number of internal logical file types referenced by the external input type |
| Average | The external input type not conclusively low or high |
| High | Many data elements included in the external input type and a significant number of internal logical file types referenced by the external input type |

2. Number of External Outputs

External output (EO) is a transactional function that generates data or control information to be sent outside the boundary of the application under consideration.  The external output is unique if either the output format or the processing logic is unique.  Output can be files, reports, or messages sent to users or to other applications.

| Complexity | Description |
| --- | --- |
| Low | A single column or two columns with no subtotals |
| Average | Multiple columns with subtotals |
| High | Multiple file references and complicated data transformations |

3. Number of Internal Logical Files

A set of logically related data maintained inside the application.

| Complexity | Description |
| --- | --- |
| Low | Few record types |
| Average | The internal logical file type not conclusively low or high |
| High | Many record types |

4. Number of External Interface Files

A set of logically related data used inside the application, but maintained external to the application.

| Complexity | Description |
| --- | --- |
| Low | Few record types |
| Average | The external file type not conclusively low or high |
| High | Many record types |

5. Number of External Inquiries

External inquiry (EQ) is a transactional function that accepts data from outside the boundary of the application under consideration and uses it to retrieve (but not derive or calculate) data to be sent outside the boundary of the application.  The external inquiry is unique if the input/output combination is unique or the processing logic is unique. Input typically takes the form of identifiers or key values and output is generally data listings or reports (without calculated data).  The inquiry does not modify data.

| Complexity | Description |
| --- | --- |
| Low | A combination of low external input type and low external output type |
| Average | The external inquiry type not conclusively low or high |
| High | A combination of high external input type or high external output type |

### Processing Complexity Traits

Once the user identifiable function types are weighted and counted, the unadjusted function point counts can be computed.  General complexity levels are considered for 14 traits to adjust the standard processing measure for complexity.  Each of the 14 traits is ranked for degree of influence on a scale ranging from 0 (not present or no influence) to 5 (strong influence throughout). The traits are described as follows:

| Trait | Description |
| --- | --- |
| Data Communications | The degree to which communication facilities are required for the application |
| Distributed Functions | The existence of distributed functions in the application |
| Performance | The degree to which performance is a critical issue |
| Heavily Used Configuration | The installation of the application on current equipment that is heavily used |
| Transaction Rate | The measurement of the transaction rate |
| On-line Data Entry | The complexity of on-line data transactions with consideration to the number of screens and functions |
| End User Efficiency | The degree to which on-line functions promote end user efficiency |
| On-line Update | The use of on-line updates to master files |
| Complex Processing | The amount of complex processing. Complex processing may have many control interactions and decision points, a significant number of logical and mathematical equations, or extensive exception processing |
| Reusability | The evaluation of code in terms of reusability |
| Installation Ease | The degree to which the application is easily installed |
| Operational Ease | The proficiency of the application's general operations such as startup, backup, recovery, and shutdown |
| Multiple Sites | The number of installations of the application across diverse organizations or sites |
| Facilitate Change | The appraisal of the application in terms of how easily it accommodates user modifications such as providing a flexible query facility or functions for setting and maintaining user-defined parameters |

The adjusted function point count for the system is a product of the unadjusted function point count and the value adjustment factor.

The measurement of functionality can be used to generate an estimated source lines of code  (SLOC). Based on an estimate of the average number of lines required to build one function, an approximate SLOC can be obtained by multiplying the number of function points by the functionality estimate for a selected programming language such as C, C++, COBOL, etc.

## Effort Estimation via COCOMO

COCOMO is an effort estimation tool introduced by Barry Boehm (Boehm 84).  Boehm defined a hierarchy of models: basic, intermediate, and advanced. The basic COCOMO Model is a static single-valued model that calculates development effort and cost as a function of the estimated SLOC.  The intermediate COCOMO Model calculates development effort and cost as a function of program size in terms of estimated SLOC and a subjective assessment of several system attributes. The advanced COCOMO Model includes all intermediate features plus an assessment of cost driver's impact on each phase of the system life cycle. COSMOS is based on the intermediate COCOMO Model.

COCOMO delineates software projects into three modes: organic, semi-detached, and embedded. Organic mode is used to describe small, simple projects where the requirements do not require strict adherence.  Semi-detached mode describes intermediate size projects with requirements that identify some rigid constraints.  Embedded mode describes a software project with requirements containing very strict hardware, software, and operational constraints.

The COCOMO Model calculates person months and project duration using estimated SLOC and the effort adjustment factor (EAF) derived from 15 cost driver attributes.  The cost drivers are grouped into four major categories: product, hardware, personnel, and project attributes.  Each of the attributes is rated on influence on project complexity using a 6-point basis that ranges from very low to extra high (not all ratings are allowed for all attributes).  Based on the rating, the corresponding effort multiplier of each cost driver is used to compute the EAF.  More information about the cost driver attributes is located in the COSMOS Technical Reference (see COCOMO Complexity Influence Assignments).

### Product Attributes

These are attributes of the software product you are to develop.

| Attribute | Description |
| --- | --- |
| Required Software Reliability | The degree to which software errors can be tolerated. The range for poor reliability can be from a slight inconvenience to risk to human life |
| Size of Application Database | The ratio of the data storage to the program size |
| Complexity of Product | The degree of complexity in the application's functions; Simple functions have simple expressions in the computational operations, very little nesting in the control operations, and the data management operations consist of simple arrays in main memory; Complex functions have highly nested control operations, difficult mathematical computations, dynamic data relationships in the data storage, and micro-coding for device-dependent operations |

### Hardware Attributes

These are attributes of the hardware platform you are working with.

| Attribute | Description |
| --- | --- |
| Time | The measurement of time required for user feedback |
| Run-Time Performance Constraints | The measurement of use of available execution time |
| Memory Constraints | The measurement of use of available storage space |
| Virtual Machine Volatility | The amount of change to the application's environment such as the operating system and hardware upgrades |
| Required Turnaround Time | The measurement of time required for user feedback |

### Personnel Attributes

These are attributes of your project team members.

| Attribute | Description |
| --- | --- |
| Analyst Capability | The percentile ranking of the analyst's aptitude |
| Software Engineer Capability | The percentile ranking of the programmer's aptitude |
| Application Experience | The number of years the staff has gained background knowledge regarding the application |
| Programming Language Experience | The number of years of experience the staff has worked with the language |
| Virtual Machine Experience | The number of years of experience the staff has worked with the operating system and hardware |

### Project Attributes

These are attributes of your software development process for this project.

| Attribute | Description |
| --- | --- |
| Use of Software Tools | The richness in features of the tools being used for development; tools can be very basic and require additional manual involvement or the tools can be quite comprehensive with automated design, documentation, and coding components |
| Application of SE Methods | The degree of commitment of the staff to using software engineering methods |
| Required Development Schedule | The significance of the project delivery date; A high rating means that early delivery is very desirable or needed |

## Effort Estimation via Rayleigh

Rayleigh is an effort estimation tool introduced by Lawrence H. Putnam.  The Rayleigh approach separates projects into three separate phases: Feasibility Studies, Functional Design and Main Build.  The Feasibility Studies phase outlines project specifications and plans; the Functional Design phase records functional design specifications, test plans, and management plants; the Main Build phase begins at the start of detail logic design and ends when the system is fully operational.

Putnam offers two equations for estimating software development effort and analyzing the effects of compressing or expanding the schedule.  The software equation computes the development effort required and therefore the cost.  The inputs to this equation are source lines of code  (SLOC), time for development in years, special skills factor (B) and productivity measure (PM).  The skills factor values and the productivity measure values are obtained from Tables 1 through 4 of the Putnam article, "Rayleigh Model," pp. 995-996.  The Manpower Buildup Index Equation computes the manpower buildup index parameter which can be expressed in 6 different levels.  The inputs for this equation are the effort computed from the software equation, size in SLOC, and the special skill factor.  More information about the Manpower Buildup Index is located in the COSMOS Technical Reference (see the Rayleigh Model).

## Projects

The Project feature of COSMOS allows you to combine the Function Point (FP), the COCOMO, and the Rayleigh analysis of a project into one grouping.  Projects allow you to mix and match different scenarios for your project.  Using Projects, you can save project combinations for future reference.

## Systems

The System feature of COSMOS allows you to combine projects.  Systems enable you to mix and match different project scenarios.  The metrics computed by the System are total adjusted function points, total source lines of code, total adjusted effort, cumulative time to develop, total time to develop, and system manpower buildup.

# Chapter 2  Understanding COSMOS Basics

## Menu Bar

The Menu Bar contains selections for the major COSMOS functions: File, View, Project, Function Point, COCOMO, Rayleigh, Options, Window, and Help.  The selections available to the user vary, depending on what you are doing in COSMOS.  For example, when you elect to work on a Function Point Model, the Project, COCOMO, and Rayleigh menu items will not be available.  When working on a COCOMO Model, the Project, Function Point, and Rayleigh menu items will not be available.  Similarly, the Project, Function Point, and COCOMO menu items will not be available when you work on a Rayleigh model.  Only when you have elected to work on a Project will all menu choices be available.

The following figure shows the Menu Bar when the Project and all Models are available:

A summary of the COSMOS Menu Bar functions is given below, including function names, shortcut keys, and brief function descriptions:

| Menu Selection | Shortcut Keys | Description |
| --- | --- | --- |
| File | ALT, F | Standard open, close, save, print, and exit functions |
| View | ALT, V | Enable/disable Toolbar and Status Bar display |
| Project | ALT, P | Initialization and data entry for Projects |
| Function Point | ALT, U | Initialization and data entry for Function Point Models |
| COCOMO | ALT, C | Initialization and data entry for COCOMO Models |
| Rayleigh | ALT, R | Initialization and data entry for Rayleigh Models |
| Options | ALT, O | COSMOS customization options |
| Window | ALT, W | Standard window controls |
| Help | ALT, H | COSMOS help information |

The following figure shows the Menu Bar when the System is available:

A summary of the COSMOS Menu Bar functions is given below, including function names, shortcut keys, and brief function descriptions:

| Menu Selection | Shortcut Keys | Description |
| --- | --- | --- |
| File | ALT, F | Standard open, close, save, print, and exit functions |
| View | ALT, V | Enable/disable Toolbar and Status Bar display |
| System | ALT, S | Initialization and data entry for Systems |
| Options | ALT, O | COSMOS customization options |
| Window | ALT, W | Standard window controls |
| Help | ALT, H | COSMOS help information |

## Tool Bar

You can use the COSMOS dockable Toolbars as a shortcut for frequently accessed Menu Bar(s) commands.  Most of the commands found on the Menu Bar(s) are also available from the Toolbars.  By selecting the appropriate button, you can open, enter details, adjust, or print your models, projects, and systems.  You can rearrange the Toolbars to make the access the COSMOS' functions easy.  The Toolbars will maintain the setup locations between invocations of COSMOS.  Selecting the View Menu and checking the Toolbar option can access Toolbar Configurations.

The following figure shows the COSMOS Toolbar when all functions are available:

## File Menu

The File Menu is displayed when File is chosen from the Menu Bar.  The selections displayed on this menu vary depending on whether a Model or Project is currently open.  The following figure shows the File Menu when all selections are available:

| Note: This menu provides two types of shortcut keys. Use “Ctrl+N”, “Ctrl+O”, “Ctrl+S” or “Ctrl+P” when the File Menu is not open. The underlined shortcut keys (“N”, “O”, “C”, “S”, “A”, “P”, “v”, “r”, “1”, “2”, “3”, “4”, “x”) may only be used when this menu is open. |  |
| --- | --- |

The functions available on the File Menu are:

| Menu Selection | Shortcut Keys | Description |
| --- | --- | --- |
| New | Ctrl+N or N | Opens a new Model or Project; A dialog box is displayed to allow you to choose the type of component to open |
| Open | Ctrl+O or O | Opens an existing Model or Project; A dialog box is displayed to allow you to select the Model or Project to be opened |
| Close | C | Closes the currently opened Model or Project; COSMOS continues to run |
| Save | Ctrl+S or S | Saves the currently opened Model or Project to disk; If this Model has been saved before, it is saved under the same disk, directory and file name, otherwise the selection is treated as a Save As |
| Save As | A | Saves the currently opened Model or Project to disk; A dialog box is displayed to allow you to enter the disk, directory and file name under which the component should be stored |
| Print | Ctrl+P or P | Prints the currently opened Model or Project; A dialog box is displayed to allow you to specify how it should be printed |
| Print Preview | V | Displays the current Model or Project information on the screen, just as it would appear if printed |
| Print Setup | R | Allows you to specify print options via a dialog box |
| Previous Model/Project | 1 or 2 or 3 or 4 | Allows you to open a recently opened Model or Project by choosing its name from a list |
| Exit | X | Exits COSMOS |

### New Dialog Box

The New Dialog Box is displayed when you select New from the File Menu to allow you to choose the type of component to be created.

From the displayed list you may pick the type of new component to create a Project, a Function Point Model, a COCOMO Model, a Rayleigh Model, or a System.

Exiting this dialog box via OK creates a new component of the selected type, while Cancel causes no new component to be created.  When a new component is created, a Description Dialog Box is displayed.  When Cancel is chosen, the New Dialog Box will disappear.

### Open Dialog Box

To open an existing Model, Project, or System, select Open from the File Menu.  The Open Dialog Box will be displayed.

This dialog box provides several pull-down and scrolling lists, as well as a text box for data entry.   You may either type in the specification of the file to open or pick from the lists as follows:

| File Name text box | You may type in the complete file specification for the Model, Project, or System to open in this box. If you omit the extension, the default extension from the List File as Type list will be used. |
| --- | --- |
| File Name list | Alternatively you may select a file name from this list. This file will be located in the drive/directory designated in the Directories list |
| Directories/Drives list | You may select a directory for the file to open from this list. The directories will be from the drive designated at the top of the list. You may select a drive from this list. |
| Files of Type list | You may select the type of file to be opened from this list to set up the default extension. This determines which type of file will be displayed in the File Name list. |

Exit this dialog box by selecting Open to execute the open or Cancel to abort the operation.

### Save As Dialog Box

When you select Save As from the File Menu or when you select Save and the current Model, Project, or System has not been saved before, the Save As Dialog Box is displayed.

This dialog box also provides several pull-down and scrolling lists, as well as a text box for data entry.   You may either type in the file specification or pick from the lists as follows:

| File Name text box | You may type in the complete file specification for the saved Model, Project, or System in this box. If you omit an extension, the default extension from the Save File as Type list will be used. |
| --- | --- |
| File Name list | Alternatively you may select a file name from this list. This file will be located in drive/directory designated in the Directories list. |
| Directories/Drives list | You may select a directory or a drive for the saved file from this list. The directories will be from the drive designated at the top of the list. |
| Save as Type list | You may select the type of file to be saved from this list to set up the default extension. This also determines which type of file will be displayed in the File Name list. |

Exit this dialog box by selecting Save to execute the save or Cancel to abort the operation.

### Print Dialog Box

When you select Print from the File Menu, the Print Dialog Box is displayed.

This dialog box allows you to specify how or what portion of your report will be printed.

You may specify the following options:

| Printer | Select the printer name and specify the printer properties Check the Print to File box to send output to a file Properties: Specify the resolution and formatting for your report. The higher the Print Quality, the greater the clarity of the output. Selecting a lower Print Quality may allow your model, project, or system to print faster. |
| --- | --- |
| Print Range | Select either: All (print the entire report) Pages (print the report for the specified page range) Selection is not allowed |
| Copies | Specify the number of copies to be printed Collate Copies (Selection is not allowed) |

Select OK to send your report to the printer or select Cancel to terminate the print request.  By selecting Setup, the Print Setup Dialog Box will be displayed to allow you to change printers or print settings.

### Print Preview Window

The Print Preview Window is displayed when you select Print Preview from the File Menu.  This window allows you to see how your report will be printed before it is sent to the printer.

The following buttons are available at the top of the Print Preview Window:

| Print | Displays the Print Dialog Box to allow you to send your report to the printer |
| --- | --- |
| Next Page | View the next page of the report |
| Prev Page | View the previous page of the report |
| One Page/Two Page | Toggle between viewing one or two pages of the report at a time |
| Zoom In | Magnify an area of the report to see greater detail |
| Zoom Out | Return to a full page view of the report |
| Close | Exit Print Preview and return to the model, project, or system |

### Print Setup Dialog Box

When you select Print Setup from the File Menu or Setup from the Print Dialog Box, the Print Setup Dialog Box is displayed.

This dialog box allows you to change printers or to specify your print settings.  Select Properties to change the characteristics of your printer.  Select OK to save your changes or select Cancel to disregard the changes.

## View Menu

The View Menu, which is displayed when you select View from the Menu Bar, allows you to customize your display.

The functions available from the View Menu are:

| Menu Selection | Shortcut Keys | Description |
| --- | --- | --- |
| Toolbar | T | When this item is checked, the COSMOS Toolbar Configuration Dialog Box is displayed. You can check or uncheck the Toolbar you wish to display at the top of the screen, just below the Menu Bar. Select this item to turn the Toolbar on or off. |
| Status Bar | S | When this item is checked, the COSMOS Status Bar is displayed at the bottom of the screen. Select this item to turn the Status Bar on or off. |

## Project Menu

The Project Menu, which is displayed when you select Project from the Menu Bar, allows you to prepare size and time estimates for projects.

The functions available from the Project Menu are:

| Menu Selection | Shortcut Keys | Description |
| --- | --- | --- |
| Import FP Model | F | Retrieves a stand-alone Function Point Model into the current Project |
| Import COCOMO Model | C | Retrieves a stand-alone COCOMO Model into the current Project |
| Import Rayleigh Model | R | Retrieves a stand-alone Rayleigh Model into the current Project |
| Export FP Model | P | Saves a stand-alone copy of the Function Point Model of the current Project |
| Export COCOMO Model | O | Saves a stand-alone copy of the COCOMO Model of the current Project |
| Export Rayleigh Model | A | Saves a stand-alone copy of the Rayleigh Model of the current Project |
| Description | D | Displays the Description Dialog Box to allow you to enter or modify the Project description information |
| Use FP Sensitivity Analysis Data | U | Use the Function Point sensitivity adjustments in the Project's Sensitivity Analysis |
| Use COCOMO Sensitivity Analysis Data | S | Use the COCOMO sensitivity adjustments in the Project's Sensitivity Analysis |
| Use Rayleigh Sensitivity Analysis Data | E | Use the Rayleigh sensitivity adjustments in the Project's Sensitivity Analysis |
| Initialize | I | Resets all Project values, including descriptions to default values |

### Import FP Model

You may import an existing Function Point Model into a Project by selecting Import FP Model from the Project Menu.  The Import FP Model is displayed to allow you to select the Function Point Model you wish to import.  The source lines of code from the selected Function Point Model will be used as input to the Project's COCOMO Model.

### Import COCOMO Model

You may import an existing COCOMO Model into a Project by selecting Import COCOMO Model from the Project Menu.  The Import COCOMO Model is displayed to allow you to select the COCOMO Model you wish to import.  The COCOMO Model will be recalculated based on the source lines of code from the Project's Function Point Model.

### Import Rayleigh Model

You may import an existing Rayleigh Model into a Project by selecting Import Rayleigh Model from the Project Menu.  The Open Dialog Box is displayed to allow you to select the Rayleigh Model you wish to import.  The Rayleigh Model will be recalculated based on the source lines of code from the Project's Function Point Model.

### Export FP Model

You may save a Project's Function Point Model as a stand-alone Function Point Model by selecting Export FP Model from the Project Menu.  The Export FP Model is displayed to allow you to specify a file name for your exported Function Point Model.

### Export COCOMO Model

You may save a Project's COCOMO Model as a stand-alone COCOMO Model by selecting Export COCOMO Model from the Project Menu.  The Export COCOMO Model is displayed to allow you to specify a file name for your exported COCOMO Model.

### Export Rayleigh Model

Your may save a Project's Rayleigh Model as a stand-alone Rayleigh Model by selecting Export Rayleigh Model from the Project Menu.  The Export Rayleigh Model is displayed to allow you to specify a file name for your exported Rayleigh Model.

### Description Dialog Box

The Description Dialog Box is displayed immediately after you select the type of new component you wish to create.  It is also displayed when you select Description from the Project, Function Point, COCOMO, Rayleigh, or System Menu.

| Tip: You can use the Enter key to enter a carriage return in the Description text |  |
| --- | --- |

You may view the current Model or Project description and enter new or revised information in the fields of the dialog box.  The information you may enter includes:

| Title | The name of the project being modeled |
| --- | --- |
| Prepared By | Your name |
| Description | Any descriptive text you wish to enter (this field scrolls to permit entry of a description with a maximum of 500 characters) |

If you exit this box by selecting the Cancel button, the dialog box will be removed, returning you to the Summary Information Window and any changes made to the description information will be disregarded.   If you select the OK button, any changes made in the Description Dialog Box are saved and you will be returned to the Summary Information Window.

### Use FP Sensitivity Analysis Data

You may check the Use FP Sensitivity Analysis Data option to have your project use the Function Point Sensitivity Adjustments as the parameters for your sensitivity calculations.  Projects may use either Function Point, COCOMO, or Rayleigh Sensitivity Adjustments, but only one at a time.

### Use COCOMO Sensitivity Analysis Data

You may check the Use COCOMO Sensitivity Analysis Data option to have your project use the COCOMO Sensitivity Adjustments as the parameters for your sensitivity calculations.  Projects may use either Function Point, COCOMO or Rayleigh Adjustments, but only one at a time.

### Use Rayleigh Sensitivity Analysis Data

You may check the Use Rayleigh Sensitivity Analysis Data option to have your project use the Rayleigh Sensitivity Adjustments as the parameters for your sensitivity calculations.  Projects may use either Function Point, COCOMO, or Rayleigh Adjustments, but only one at a time.

### Project Summary Information Window

The Project Summary Information Window is displayed after opening a new or existing Project.  For new Projects, this window is displayed after exiting the Description Dialog Box.  For existing Projects, this window is displayed upon opening the Project.

| Note: You cannot modify data directly in this window. Use the selections available on the Function Point Menu, COCOMO Menu and Rayleigh Menu to make adjustments to your project. Since the data on this window may be too big to fit on your screen, scroll bars are provided to allow your to view the entire window |  |
| --- | --- |

The first three fields of this window contain description information which has been previously entered by the user.  The remainder of the window contains the most recent Function Point, COCOMO, and Rayleigh descriptions and results.  These results are computed from data entered by the user or from default values if data has not yet been entered.

The information displayed in the Project Summary Information Window for a Project may be customized based on your preferences.  See Display Options Dialog Box for information on how to set your display preferences.  The following shows the Project Summary Information Window with the Function Point, COCOMO, and Rayleigh Descriptions enabled.

| With the Function Point, COCOMO, and Rayleigh descriptions and intermediate totals disabled, you will be able to see all of the Project Summary Information Window at one time |  |
| --- | --- |

## System Menu

The System Menu, which is displayed when you select System from the Menu Bar, allows you to prepare size and time estimates for systems.

The functions available from the System Menu are:

| Menu Selection | Shortcut Keys | Description |
| --- | --- | --- |
| Attributes | A | Gives the time to develop and effort in person months for the System. |
| Projects | P | Use this to add projects into the System |
| Description | D | Displays the Description Dialog Box to allow you to enter or modify the System description information |
| Initialize | I | Resets all System values, including descriptions to default values |

You may view the current System description and enter new or revised information in the fields of the dialog box.  The information you may enter includes:

### System Summary Information Window

The System Summary Information Window is displayed after opening a new or existing System.  For new Systems, this window is displayed after exiting the Description Dialog Box.  For existing Systems, this window is displayed upon opening the System.

| Note: You cannot modify data directly in this window. Use the selections available on the System Menu to make adjustments to your system. Since the data on this window may be too big to fit on your screen, scroll bars are provided to allow your to view the entire window |  |
| --- | --- |

The first three fields of this window contain description information which has been previously entered by the user.  The remainder of the window contains the most recent system and project summary results.  These results are computed from data entered by the user or from default values if data has not yet been entered.

The information displayed in the System Summary Information Window for a System may be customized based on your preferences.  See Display Options Dialog Box for information on how to set your display preferences.  The following shows the System Summary Information Window with the System Level Estimation Information description enabled.  The information in this window includes:

| Name | The name of the project being modeled |
| --- | --- |
| Prepared By | Your name |
| Description | A description of the project (this field scrolls to permit display of long descriptions) |
| Total Adj. Function Points | The total number of adjusted function points obtained from the summation of all the projects' adjusted function points |
| Total Source Lines of Code | The total number of source lines of code obtained from the summation of all the projects' source lines of code |
| Total Adj. Effort | The total number of adjusted effort obtained from the summation of all the projects' adjusted effort |
| Product Design | Cumulative time to develop in the product design phase |
| Project Number | Project Number as stored in the System |
| Programming | Cumulative time to develop in the programming phase |
| Integration & Test | Cumulative time to develop in the integration and test phase |
| Final Test & Eval. | Cumulative time to develop in the final test and evaluation phase |
| Total Time to Develop | Total time to develop the system in calendar months |
| System Manpower Buildup Index (MBI) Level | System MBI level number |
| Project Summary Information | Each project's adjusted function points, source lines of code, programming effort, integration and test effort, programming TDEV, integration and test TDEV, and MBI level. |

### System Level Estimation Projects Dialog Box

The System Level Estimation Projects Dialog Box is displayed after you select the Projects option from the System Menu.

The Start Time Adjustment in months can be entered via this dialog box.

Select the Add button to add projects to the System or select the Delete button to delete projects from the System.  Selecting either OK or Cancel removes this dialog box.  Select OK to save your changes or select Cancel to disregard your changes.

### System Level Estimation Attributes Dialog Box

The System Level Estimation Attributes Dialog Box is displayed after choosing the Attributes selection from the System Menu.

| Note: The selection of "Project Derived" will return the computed TDEV and Effort values. If the selection is "User Specified", the user must enter the values for the TDEV and Effort. |  |
| --- | --- |

Preliminary information needed for System adjusted effort analysis is entered here. The information which may be entered here is as follows:

| Time to Develop (TDEV) | Enter a decimal value representing your estimated development schedule in months. |
| --- | --- |
| Effort | Enter a decimal value representing your estimated development effort in person months. |

Select OK to save your changes or select Cancel to disregard your changes.

### Missing Project File Dialog Box

The Missing Project File Dialog Box is displayed when trying to open a System that cannot find one or more of the projects it uses to compute system level estimation.

You may choose the Browse option to find the missing project(s) or choose the OK or Cancel options to recalculate the system level estimation and continue.

## Function Point Menu

The Function Point Menu is displayed when the Function Point option is selected from the Menu Bar.  Items on this menu allow you to alter the Function Point input data and to view the results.

The selections available on this menu are:

| Menu Selection | Shortcut Keys | Description |
| --- | --- | --- |
| Function Point Count | F | Displays the Function Point Count Dialog Box to allow you to enter or modify unadjusted function point counts and to select a programming language |
| Value Adjustment Factor | V | Displays the Value Adjustment Factor Dialog Box to allow you to rate various project factors with regard to their influence on project complexity |
| Description | D | Displays the Description Dialog Box to allow you to enter or modify the Model description information |
| Sensitivity Analysis | S | Displays the Function Point Sensitivity Adjustment Dialog Box to allow you to enter the parameters for sensitivity calculations |
| Reverse Engineering | R | Displays the Function Point Reverse Engineering Dialog Box to allow you to perform "what if" analysis on your Model. |
| Initialize | I | Resets the description, the unadjusted function point counts, the value adjustment factors, and the programming language to default values |

### Function Point Summary Information Window

The Function Point Summary Information Window is displayed after opening a new or existing Function Point Model.  For new Models, this window is displayed after exiting the Description Dialog Box.  For existing Models, this window is displayed upon opening the Model.

| Note: The estimated source lines of code for software written in the selected language to implement these function points is shown in parentheses next to the language. You cannot modify data directly in this window. Use the selections available on the Function Point Menu to make adjustments to your model. |  |
| --- | --- |

The first three fields of this window contain description information which has been previously entered by the user.  The rest of the window contains the most recent function point results, computed from data entered by the user or from default values if data has not yet been entered.  The information in this window includes:

| Name | The name of the project being modeled |
| --- | --- |
| Prepared By | Your name |
| Description | A description of the project (this field scrolls to permit display of long descriptions) |
| Function Point Count | The number of unadjusted function points, computed from the user function type numbers |
| Value Adjustment Factor | An adjustment factor computed from the weighted application characteristics |
| Function Points | The adjusted function point count computed from the function point count and the value adjustment factor |
| Language | The programming language you selected for computing Source Lines of Code |
| Source Lines of Code | The estimated number of lines of code for this project, if implemented in the language shown |

### Function Point Count Dialog Box

The Function Point Count Dialog Box is displayed after you select the Function Point Count option from the Function Point Menu.

| Note: The default values for the language multipliers are defined in Appendix C, INI File Entries. |  |
| --- | --- |
| Note: You may only enter integer values | The following information may be entered via this dialog box: |

| External Input | The number of low, average, and high external inputs |
| --- | --- |
| External Output | The number of low, average, and high external outputs |
| Internal Logical File | The number of low, average, and high internal logical files |
| External Interface File | The number of low, average, and high external interface files |
| External Inquiry | The number of low, average, and high external inquiries |
| Language | The language to be used for this project. Make a selection from the pull-down list |

The totals for each row and the grand total are updated as you enter the function point count numbers.

Selecting either OK or Cancel removes this dialog box.  Select OK to save your changes or select Cancel to disregard your changes.

### Value Adjustment Factor Dialog Box

To display the Value Adjustment Factor Dialog Box, choose the Value Adjustment Factor selection from the Function Point Menu.

| Note: The default value for each adjustment is None. You may only select one value for each adjustment |  |
| --- | --- |

Choose the amount of influence which each of the listed factors has on the complexity of your project by selecting the appropriate option button.

As with the Function Point Count Dialog Box, select OK to save your changes or select Cancel to disregard the changes.

### Function Point Sensitivity Adjustments Dialog Box

The Function Point Sensitivity Adjustments Dialog Box is displayed after you select the Sensitivity Analysis option from the Function Point Menu.

This dialog box allows you to specify the parameters that are used for your Function Point Sensitivity Analysis calculations.  Select one of the following radio buttons to choose the level for entering Sensitivity Analysis adjustments to your Function Point Model:

| Details | Apply adjustments to the individual function point counts |
| --- | --- |
| Intermediate Totals | Apply adjustments to the total for each category of function point counts |
| Unadjusted FPs | Apply adjustments to the Unadjusted Function Points |
| Adjusted FPs | Apply adjustments to the Adjusted Function Points |

After you have chosen the adjustment level, you may enter the adjustment percentages for the Sensitivity Analysis calculations.  You will be allowed to only enter percentages that correspond to the currently chosen adjustment level.  You may change the adjustment level at any time by selecting the radio button for the desired level.  The adjustment percentages for a level are saved when a new level in selected.

For more information on using Sensitivity Analysis for your model, see Sensitivity Analysis in Chapter 6, Using Advanced COSMOS Features.

### Function Point Reverse Engineering Dialog Box

The Function Point Reverse Engineering Dialog Box is displayed when you select the Reverse Engineering option from the Function Point Menu.

This dialog box allows you to perform "what-if" analysis on your Function Point Model.  When the dialog box is first displayed, all three columns are populated with the calculation totals from your Function Point Model.  Select the radio button beside the model input you wish to change.  Enter the new value and select Calculate to see how the model is adjusted based on this value as its starting point.  The results of the calculation are displayed in the Output column.  The Original column displays the actual values contained in your Model.  All Source Lines of Code calculations are based on the language selected for the model in Function Point Count Dialog Box.

Selecting Reset will return the Input values to the Original values from your Model.

Select Close to exit the dialog box and return to the Summary Information Window.   Reverse Engineering adjustments are not applied to your model.

For more information on using Reverse Engineering for your model, see Reverse Engineering in Chapter 6, Using Advanced COSMOS Features.

## COCOMO Menu

The COCOMO Menu is displayed when you select the COCOMO option from the Menu Bar.  Items on this menu allow you to alter COCOMO input data and to view the results.

The selections available on this menu are:

| Menu Selection | Shortcut Keys | Description |
| --- | --- | --- |
| Attributes | A | Displays the Attributes Dialog Box to allow you to enter or modify the development model, the development mode, and the source lines of code |
| Cost Drivers | C | Displays the Cost Drivers Dialog Box to allow you to specify the effect of product, hardware, personnel, and project factors on project effort and schedule |
| Description | D | Displays the Description Dialog Box to allow you to enter or modify the Model Description information |
| Sensitivity Analysis | S | Displays the COCOMO Sensitivity Adjustment Dialog Box to allow you to enter the parameters for sensitivity calculations |
| Reverse Engineering | R | Displays the COCOMO Reverse Engineering Dialog Box to allow you to perform "what if" analysis on your Model. |
| Initialize | I | Resets the description, the development mode and model, the source lines of code, and the cost drivers to default values after requesting a confirmation |

### COCOMO Summary Information Window

The COCOMO Summary Information Window is displayed after opening a new or existing COCOMO Model.  For new Models, this window is displayed after you exit the Description Dialog Box.  For existing Models, this window contains any description information you have previously entered and is displayed when you open the Model.

| Note: You cannot modify data directly in this window. Use the selections available on COCOMO Menu to make adjustment to your model |  |
| --- | --- |

The first three fields of this window contain COCOMO Model description information which has been previously entered by the user.  For new Models these fields are blank. The rest of the fields contain the most recent COCOMO results, computed from data entered by the user or from default values if data has not been entered.  The information in this window includes:

| Name | The name of the project being modeled |
| --- | --- |
| Prepared By | Your name |
| Description | A description of your project (this field scrolls to permit display of long descriptions) |
| Source Lines of Code | The estimated lines of code (excluding comment lines) contained in the delivered software product |
| Nominal Person Months | The number of person-months it will take to complete this project, computed from the source lines of code, and project mode (organic, semi-detached, or embedded) |
| Adjusted Person Months | The number of person-months it will take to complete this project, adjusted by the project cost driver ratings |
| Time To Develop | The calendar time it will take to develop this project (in months) |
| Phase Distribution | Provides information for the three phases: Product Design, Programming, Integration, and Test. The Phase Distribution option is defaulted to OFF in the Display Options Dialog Box. |

### Attributes Dialog Box

The Attributes Dialog Box is displayed after choosing the Attributes selection from the COCOMO Menu.

| Note: The Basic and Advanced models are not implemented in this version of COSMOS and are shown in gray. Selection of these models is not permitted |  |
| --- | --- |

Preliminary information needed for COCOMO effort analysis is entered here.  Select the COCOMO mode and enter the source lines of code estimated for your project.  The Intermediate COCOMO Model type is the only COCOMO Model used by COSMOS.  The Intermediate model allows you to customize your estimate to reflect your environment through the use of cost driver adjustments.  The information which may be entered here is:

| Mode | Select one of: Organic (project is from a familiar, stable, and fairly unrestrained environment) Semidetached (project is not Organic or Embedded) Embedded (project environment is unfamiliar, tightly constrained, and unforgiving) |
| --- | --- |
| Model | Select one of: Basic (whole project estimate with no cost driver adjustment applied) Intermediate (whole project estimate with cost driver adjustment) Advanced (project estimate by phases) Only the Intermediate selection is available at this time. |
| Source Lines of Code | In the case of a Project, the Lines of Code will be filled in with the Source Lines of Code computed in the Function Point Model of this Project. If you are entering or modifying a stand-alone COCOMO Model then you will enter the estimated lines of code for the project being modeled. |

Select OK to save your changes or select Cancel to disregard your changes.

### Cost Drivers Dialog Box

The Cost Drivers Dialog Box is displayed when you select Cost Drivers from the COCOMO Menu.

| Note: You may only enter one value for each attribute. |  |
| --- | --- |

From this window you will rate attributes of your product, your hardware environment, your project team personnel and your project on a scale of Very Low to Extra High (note that all ratings are not available for all attributes as specified by the COCOMO Model).  You may display all attributes in the Attributes scrolling list or you may select a specific type of attribute by choosing one of the buttons at the top of this dialog box.  The current effort rating for each displayed attribute is listed in front of the attribute.  You may change the rating of any attribute by selecting that attribute and then choosing a new effort rating from the effort buttons.

Select OK to save any changes made or Cancel to disregard those changes.

### COCOMO Sensitivity Adjustments Dialog Box

The COCOMO Sensitivity Adjustments Dialog Box is displayed after you select the Sensitivity Analysis option for the COCOMO Menu.

This dialog box allows you to specify the parameters that are used for your COCOMO Sensitivity Analysis calculations. Select one of the following radio buttons to choose the level for entering Sensitivity Analysis adjustments to your COCOMO Model:

| SLOC | Apply adjustments to the number of source lines of code |
| --- | --- |
| Nom. Person Mon. | Apply adjustments to the nominal person months |
| Adj. Person Mon. | Apply adjustments to the adjusted person months |

After you have chosen the adjustment level, you may enter the adjustment percentage for the Sensitivity Analysis calculations.  You will be allowed to only enter a percentage for the currently chosen adjustment level.  You may change the adjustment level at any time by selecting the radio button for the desired level.  The adjustment percentage for a level is saved when a new level in selected.

For more information on using Sensitivity Analysis for your model, see Sensitivity Analysis in Chapter 6, Using Advanced COSMOS Features.

### COCOMO Reverse Engineering Dialog Box

The COCOMO Reverse Engineering Dialog Box is displayed when you select Reverse Engineering from the COCOMO Menu.

This dialog box allows you to perform "what-if" analysis on your COCOMO Model.  When the dialog box is first displayed, all three columns are populated with the calculation totals from your COCOMO Model.  Select the radio button beside the model input you wish to change.  Enter the new value and select Calculate to see how the model is adjusted based on this value as its starting point.  The results of the calculation are displayed in the Output column.  The Original column displays the actual values contained in your Model.

Selecting Reset will return the Input values to the Original values from your Model.

Select Close to exit the dialog box and return to the Summary Information Window.   Reverse Engineering adjustments are not applied to your model.

For more information on using Reverse Engineering for your model, see Reverse Engineering in Chapter 6, Using Advanced COSMOS Features.

## Rayleigh Menu

The Rayleigh Menu is displayed when you select the Rayleigh option from the Menu Bar.  Items on this menu allow you to alter Rayleigh input data and to view the results.

The selections available on this menu are:

| Menu Selection | Shortcut Keys | Description |
| --- | --- | --- |
| Attributes | A | Displays the Attributes Dialog Box to allow you to enter or modify the application type, schedule, and the source lines of code |
| Description | D | Displays the Description Dialog Box to allow you to enter or modify the Model Description information |
| Sensitivity Analysis | S | Displays the Rayleigh Sensitivity Adjustment Dialog Box to allow you to enter the parameters for sensitivity calculations |
| Reverse Engineering | R | Displays the Rayleigh Reverse Engineering Dialog Box to allow you to perform "what if" analysis on your Model |
| Initialize | I | Resets the application type, schedule, and the source lines of code |

### Rayleigh Summary Information Window

The Rayleigh Summary Information Window is displayed after opening a new or existing Rayleigh Model.  For new Models, this window is displayed after you exit the Description Dialog Box.  For existing Models, this window contains any description information you have previously entered and is displayed when you open the Model.

| Note: You cannot modify data directly in this window. Use the selections available on Rayleigh Menu to make adjustment to your model. |  |
| --- | --- |

The first three fields of this window contain Rayleigh Model description information which has been previously entered by the user.  For new Models these fields are blank. The rest of the fields contain the most recent Rayleigh results, computed from data entered by the user or from default values if data has not been entered.  The information in this window includes:

| Name | The name of the project being modeled |
| --- | --- |
| Prepared By | Your name |
| Description | A description of your project (this field scrolls to permit display of long descriptions) |
| Source Lines of Code | The estimated lines of code (excluding comment lines) contained in the delivered software product |
| Time To Develop (TDEV) | The calendar time it will take to develop this project (in months) |
| Main Build Phase Time | Constitutes effort, peak staffing, size of the system, and errors. Representing only the given percent of the total Time To Develop spent in the Main Build Phase |
| Application Type | The type of application being developed |
| Manpower Buildup Index (MBI) Level | Integer value representing the effect of time compression, also referred to as the manpower accelerator |

### Rayleigh Attributes Dialog Box

The Attributes Dialog Box is displayed after choosing the Attributes selection from the Rayleigh Menu

| Note: The selection of an Application Type that is not the "User Specified System" will return the PI and PM values corresponding to the Application Type. If the selection is "User Specified System" for the Application Type, the user must enter the values for the PI and PM. |  |
| --- | --- |

Preliminary information needed for Rayleigh effort analysis is entered here.  Select the Rayleigh application type.  If the application type selected is user specified system then enter the productivity index or productivity measure.  Enter the main build phase percentage.   If Rayleigh is developed as a stand-alone model, enter the development schedule (months) and the source lines of code.  The information which may be entered here is:

| Application Type | Select any of the application types listed. If application type selected is user specified system, enter a productivity index or a productivity measure |
| --- | --- |
| Time to Develop (Months) | Enter a decimal value representing your estimated development schedule in months |
| Main Build Phase Percentage | Enter an integer value represented your estimated percent of development |
| Source Lines of Code | In the case of a Project, the Lines of Code will be filled in with the Source Lines of Code computed in the Function Point Model of this Project. If you are entering or modifying a stand-alone Rayleigh Model then you will enter the estimated lines of code for the project being modeled. |

Select OK to save your changes or select Cancel to disregard your changes.

### Rayleigh Sensitivity Adjustments Dialog Box

The Rayleigh Sensitivity Adjustments Dialog Box is displayed after you select the Sensitivity Analysis option for the Rayleigh Menu.

This dialog box allows you to specify the parameters that are used for your Rayleigh Sensitivity Analysis calculations.  Select one of the following radio buttons to choose the level for entering Sensitivity Analysis adjustments to your Rayleigh Model:

| SLOC | Apply adjustments to the number of source lines of code |
| --- | --- |
| TDEV | Apply adjustments to the time to develop (schedule) |
| PM | Apply adjustments to the productivity measure |
| PI | Apply adjustments to the productivity index |

After you have chosen the adjustment level, you may enter the adjustment percentage for the Sensitivity Analysis calculations.  You will be allowed to only enter a percentage for the currently chosen adjustment level.  You may change the adjustment level at any time by selecting the radio button for the desired level.  The adjustment percentage for a level is saved when a new level in selected.

For more information on using Sensitivity Analysis for your model, see Sensitivity Analysis in Chapter 6, Using Advanced COSMOS Features.

### Rayleigh Reverse Engineering Dialog Box

The Rayleigh Reverse Engineering Dialog Box is displayed when you select Reverse Engineering from the Rayleigh Menu.

This dialog box allows you to perform "what-if" analysis on your Rayleigh Model.  When the dialog box is first displayed, all three columns are populated with the calculation totals from your Rayleigh Model.  Select the radio button beside the model input you wish to change.  Enter the new value and select Calculate to see how the model is adjusted based on this value as its starting point.  The results of the calculation are displayed in the Output column.  The Original column displays the actual values contained in your Model.

Selecting Reset will return the Input values to the Original values from your Model.

Select Close to exit the dialog box and return to the Summary Information Window.   Reverse Engineering adjustments are not applied to your model.

For more information on using Reverse Engineering for your model, see Reverse Engineering in Chapter 6, Using Advanced COSMOS Features.

## Options Menu

When you select the Options option from the Menu Bar, this menu is displayed:

The functions available on the Options Menu are:

| Menu Selection | Shortcut Keys | Description |
| --- | --- | --- |
| Display | D | Displays the Display Options Dialog Box to allow you to set your preferences for what information is shown in the Project, Function Point, COCOMO, Rayleigh, and System Summary Information Windows. |
| Languages | L | Displays the Language Customization Dialog Box to allow you to add new languages or modify the SLOC for existing languages. |

### Display Options Dialog Box

The Display Options Dialog Box is displayed when you select Display from the Options Menu.

| Note: The FP, COCOMO, and Rayleigh Descriptions option applies to Projects. This option will not be available for Function Point, COCOMO, Rayleigh Models, and System. The COCOMO Phase distribution option applies to COCOMO models and Projects only. The Sensitivity Analysis applies to the Function Point, COCOMO, Rayleigh Models only. |  |
| --- | --- |
| Hint: Disabling the FP, COCOMO, and Rayleigh Descriptions for a project may allow you to see complete project results at one time | For this dialog box you will define how information is displayed in the Function Point, COCOMO, Rayleigh, and Project Summary Information Windows. The description, Function Point, COCOMO, and Rayleigh descriptions (for projects only), COCOMO phase distribution (for COCOMO models and projects only), intermediate totals, totals, and sensitivity analysis results will be displayed for your model or project if the box next to it is marked. Unmark the item if you do not want to see it. The display options will be saved with your model or project. The display options apply to the active model or project only. The default display options for new models and projects can be changed by modifying the COSMOS.INI file. The COSMOS Technical Reference, Appendix A: INI File Entries contains detailed information on modifying the COSMOS.INI file. |

| Description | Show description for the current project or model |
| --- | --- |
| FP, COCOMO, and Rayleigh Descriptions | Show additional descriptions for the COCOMO and Function Point Model for the current project. This option is only available for projects. |
| COCOMO Phase Distribution | Shows distribution of effort and schedule for the Organic, Semidetached, and Embedded modes |
| Intermediate Totals | Show the intermediate totals used in the calculation for your project or model |
| Totals | Show the result of the final calculation for your project or model |
| Sensitivity Analysis | Show the results from using Sensitivity Analysis for your project or model |

### Language Customization Dialog Box

The Language Customization Dialog Box is displayed when you select Languages from the Options Menu.

This dialog box allows you to modify the languages and multipliers used by COSMOS.

If a Function Point Model or a Project is the active window, the Language Customization Dialog Box is preceded by a message asking if you wish to load the COSMOS default languages or load the languages saved with your model or project.  Select Yes to load the languages saved with your model or project.  Select No to load the COSMOS default languages.  For more information concerning this message box, see Load Languages for Customization Message Box in Appendix A, COSMOS System Messages.

To modify the multiplier for an existing language, select the desired language from the language list.  You may also select a language by typing its name in the language field.  As you type, the languages that most closely match the text you type are displayed.  When you select the language, its current multiplier value is displayed.  Enter the new multiplier and select Modify to update the list.

To add a new language, enter its name in the language field and then enter its SLOC per function point in the multiplier field.  Select Modify to update the list.

To delete a language from the list, select the desired language and then select Delete.

Select Use Defaults to refresh the language list with the languages and multipliers contained in the COSMOS.INI file.  See the COSMOS Technical Reference, Appendix A: INI File Entries for more information about default settings for COSMOS.

Your changes are not applied until you exit this dialog box.  Mark Set Defaults to have the default COSMOS languages list updated.  Mark Set Current Model to have the languages list in your current model updated.   Select OK to exit the dialog box and apply your changes.  Select Cancel to exit and disregard your changes.

## Window Menu

The Window Menu is displayed when you select Window from the Menu Bar.

The possible selections on this menu are:

| Menu Selection | Shortcut Keys | Description |
| --- | --- | --- |
| Cascade | C | Arranges all currently opened windows in a stack |
| Tile | T | Arranges all currently opened windows so all are visible |
| Arrange Icons | A | Distributes icons evenly within the selected window group |
| Select a Window | 1 or 2 or 3 ... | Allows you to select a window to display and make active from the currently opened windows |

## Help Menu

The Help Menu is displayed when you select Help from the Menu Bar.

| To see COSMOS help information for a specific dialog box, select the Help button on the dialog box |  |
| --- | --- |

The functions available from the Help Menu are:

| Menu Selection | Shortcut Keys | Description |
| --- | --- | --- |
| Contents | F1 or C | Displays the table of contents for the COSMOS help information. From here you can obtain help on various COSMOS topics |
| Tutorial | T | Displays the tutorial. From here you can follow an example showing the steps in creating a COSMOS project. |
| How to Use Help | H | Displays the standard Microsoft Windows  help guidance |
| About COSMOS | A | Displays the About Message Box which provides information about the COSMOS product |

# Chapter 3  Managing Stand-Alone Models

## Creating a New Model

A stand-alone Model is one which is not included in a Project.  Chapter 4, Managing Projects, contains more information on projects.  When you work with a stand-alone Model, you are working with either a Function Point Model, a COCOMO Model or a Rayleigh Model.

When you create a new Model, you enter various types of information about the Model.  COSMOS stores this information for you and calculates results.  This section describes how you may create a brand-new Function Point, COCOMO, or Rayleigh Model:

- Select File from the Menu Bar and select New from the File Menu.  The New Dialog Box will be displayed.

- Select the type of component you wish to use, either Function Point, COCOMO, or Rayleigh. The Description Dialog Box will now be displayed.

- Enter descriptive information about the software project you are modeling here and then select OK.  The Summary Information Window for Function Point, COCOMO, or Rayleigh will be displayed.

## Updating an Existing Model

| Tip: Function Point Models are stored with the “.fpm” extension by default, while the default of the COCOMO Model extension is “.ccm”, and the Rayleigh Model extension is “.rlm”. | After you create a Model, you may save the Model's information to disk as described in Saving a Model. You may view or modify the Model at a later time. You may change or review a saved Function Point, COCOMO Model, or Rayleigh Model as follows: - Select Open from the File Menu. You will see a dialog box from which you may select a saved Model or Project. - Select the Model you wish to update and the Summary Information Window for Function Point, COCOMO, or Rayleigh will be displayed. |
| --- | --- |

## Entering Model Data

A new Model is created with default entries for all data values, except for the descriptive information, which is left blank.  This means that when entering new data, you are never actually starting from scratch, but instead you are always modifying data which is already there.  After you have opened a new or existing Model you may change the data by following the steps listed in this section.

## Function Point Models

Three different types of data may be entered for Function Point Models: descriptive information, unadjusted functions count values and value adjustment factors.  In addition, a Function Point Model may be initialized to default values.

### Entering Function Point Model Description

As described in Creating a New Model you may enter descriptive information at the time you create your Model.  You may also modify this information at any time the Function Point Summary Information Window is displayed by following these steps:

- Select Function Point from the Menu Bar.  The Function Point Menu will be displayed.

- Select Description. The Description Dialog Box will now be displayed.

- Enter descriptive information about the software project you are modeling here and then select OK.  The Function Point Summary Information Window will be displayed with the updated description.

### Entering Unadjusted Function Point Counts

You may enter the unadjusted function point counts for your project and select your programming language as follows:

- Select Function Point from the Menu Bar. The Function Point Menu will be displayed.

- Select Function Point Count.  The Function Point Count Dialog Box will be displayed.

- Enter the function counts. Note that default value of zero appears initially for all categories if you are entering new Model data.

- Select a programming language from the Language Combo Box.

- When you have finished, select OK.  The Function Point Summary Information Window will be displayed with the updated information.

### Entering Value Adjustment Factors

In a similar manner you may enter processing complexity adjustments:

- Select Function Point from the Menu Bar. The Function Point Menu will be displayed.

- Select Value Adjustment Factor.  The Value Adjustment Factor Dialog Box will be displayed.

- Enter the adjustments by selecting the appropriate buttons.

- When you have finished, select OK.  The Function Point Summary Information Window will be displayed with the updated information.

### Initializing Your Function Point Model

| Note: If you initialize the Model, any data previously entered will be overwritten | You may initialize your Function Point Model to default values by following these steps: - Select Function Point from the Menu Bar. The Function Point Menu will be displayed. - Select Initialize. The Function Point Initialization Message Box will be displayed. - Confirm the operation by selecting Yes. The Function Point Summary Information Window will be displayed with the default information. |
| --- | --- |

## COCOMO Models

Entering COCOMO data is very similar to entering Function Point data.   Again you may enter three types of information: descriptive information, attributes, and cost driver ratings.  COCOMO data may also be initialized to default values.

### Entering COCOMO Model Description

As described in Creating a New Model you may enter descriptive information at the time you create your Model.  You may also modify this information at any time the COCOMO Summary Information Window is displayed by following these steps:

- Select COCOMO from the Menu Bar.  The COCOMO Menu will be displayed.

- Select Description. The Description Dialog Box will now be displayed.

- Enter descriptive information about the software project you are modeling here and then select OK.  The COCOMO Summary Information Window will be displayed with the updated description.

### Entering Attributes

You may enter the development mode and model for your project as follows:

	Select COCOMO from the Menu Bar.  The COCOMO Menu will be displayed.

	Select Attributes.  The Attributes Dialog Box will be displayed.

	Enter the mode and development model.  Note that default selections appear initially.

	When you have finished, select OK.  The COCOMO Summary Information Window will be displayed with the updated information.

### Entering Cost Driver Ratings

In a similar manner you may enter cost driver ratings:

- Select COCOMO from the Menu Bar.  The COCOMO Menu will be displayed.

- Select Cost Drivers.  The Cost Drivers Dialog Box will be displayed.

- Enter the cost driver ratings by selecting the appropriate buttons.

- When you have finished, select OK.  The COCOMO Summary Information Window will be displayed with the updated information.

### Initializing Your COCOMO Model

| Note: If you initialize the Model, any data previously entered will be overwritten | You may initialize your COCOMO Model to default values by following these steps:  Select COCOMO from the Menu Bar. The COCOMO Menu will be displayed.  Select Initialize. The COCOMO Initialization Message Box will be displayed.  Confirm the operation by selecting Yes. The COCOMO Summary Information Window will be displayed with the default information. |
| --- | --- |

## Rayleigh Models

Entering Rayleigh data is very similar to entering Function Point data or COCOMO data.   Again you may enter two types of information: descriptive information and attributes.  Rayleigh data may also be initialized to default values.

### Entering Rayleigh Model Description

As described in Creating a New Model you may enter descriptive information at the time you create your Model.  You may also modify this information at any time the Rayleigh Summary Information Window is displayed by following these steps:

	Select Rayleigh from the Menu Bar.  The Rayleigh Menu will be displayed.

	Select Description. The Description Dialog Box will now be displayed.

	Enter descriptive information about the software project you are modeling here and then select OK.  The Rayleigh Summary Information Window will be displayed with the updated description.

### Entering Rayleigh Attributes

You may enter the productivity, schedule, and project size information for your project as follows:

	Select Rayleigh from the Menu Bar.  The Rayleigh Menu will be displayed.

	Select Attributes.  The Attributes Dialog Box will be displayed.

	Enter the application type to select the productivity values (if application type selected is "user specified system", select and enter the productivity index (PI) or the productivity measure (PM)).  Also enter the time to develop (TDEV), the Main Build Phase percent of TDEV, and estimated source lines of code (SLOC).  Note that default selections appear initially.

	When you have finished, select OK.  The Rayleigh Summary Information Window will be displayed with the updated information.

### Initializing Your Rayleigh Model

| Note: If you initialize the Model, any data previously entered will be overwritten | You may initialize your Rayleigh Model to default values by following these steps:  Select Rayleigh from the Menu Bar. The Rayleigh Menu will be displayed.  Select Initialize. The Rayleigh Initialization Message Box will be displayed.  Confirm the operation by selecting Yes. The Rayleigh Summary Information Window will be displayed with the default information. |
| --- | --- |

## Saving a Model

When you open a Model, COSMOS copies that Model from the disk for display on your screen.  Changes you make to the Model are stored temporarily in your computer's memory.  To keep the changes permanently you must save the Model on a disk.

To save the current Model for the first time or to save the Model under a different directory, disk and/or file name, follow these instructions:

	From the File Menu, select Save As.  The Save As Dialog Box will be displayed.  If you are saving the Model for the first time selecting Save will work the same way.

	To save the Model to the current drive and in the current directory, type a file name and optional extension for the Model in the File Name box.

	To save the Model to a different drive and/or directory, select the drive and/or directory or type the complete location, file name, and optional extension in the File Name text box.

	Select the Save button.

To save a Model using its current name, disk, and directory:

	From the File Menu, select Save.

## Closing a Model

If you have completed work on the current Model you may close the Model and optionally save all changes you have made to the Model as follows:

	From the File Menu select Close.

	If you have made changes to the Model since it was last saved the Close Message Box will be displayed.  Select Yes to close the Model and save all changes or select No to close the Model without your latest changes.  If you have never saved this Model before, the save will be treated as a Save As.  You may also select Cancel to abort the close operation.

## Exiting COSMOS

You may end your COSMOS session as follows:

	From the File Menu select Exit.

	If you have made changes to any open Model since it was last saved the Close Message Box will be displayed.  Select Yes to close the Model(s), save all changes, and exit or select No to close the Model(s), and exit without saving your latest changes.  If you have open Models which have never been saved before, the save of these Models will be treated as a Save As.  You may also select Cancel to abort the exit operation.

# Chapter 4  Managing Projects

## Creating a New Project

| Tip: If you have several projects with similar characteristics, create stand-alone Function Point, COCOMO, and Rayleigh Models which you may import into various Projects and then modify to fit the project being estimated. | As discussed in Chapter 1, Introducing COSMOS, you may combine a Function Point Model, a COCOMO Model, and a Rayleigh Model to form a Project. This will allow you to compute the lines of code using the Function Point Model and to apply this to the COCOMO or Rayleigh Model automatically. When a Project is created, it contains one Function Point Model, one COCOMO Model, and one Rayleigh Model, each of which is initialized to default values. To create a new Project: - Select File from the Menu Bar, then select New from the File Menu. The New Dialog Box will be displayed. - Select Project from this Dialog Box. The Description Dialog Box will now be displayed. - Enter descriptive information about the software project you are modeling here and then select OK. The Project Summary Information Window will be displayed with the descriptive information you just entered in the upper part of the window. The remainder of the window will show Function Point, COCOMO, and Rayleigh descriptions (which are blank) and results (the results are computed from defaults). You may change any of the three descriptions (Project, Function Point, COCOMO, or Rayleigh) from the corresponding Description Dialog Box at any time. |
| --- | --- |

## Updating an Existing Project

| Tip: Projects are stored with the “.prj” extension by default | After entering a new Project, you may wish to make some changes to the data. This is done as follows:  Select Open from the File Menu. You will see a dialog box from which you may select a saved Model or Project.  Select the Project you wish to update and the Project Summary Information Window for that Project will be displayed. |
| --- | --- |

## Entering Project Data

Once a new or existing project is opened, you may enter new data or change existing data. You may import existing Models into your project or you may export a Model created within your project.  When you create a new Project, just as when creating stand-alone Models, the new Project is created with default entries for all data values, except for the descriptive information.  After you have opened a new or existing Project you may change the data by following the steps listed in this section.

### Entering Project Description

You may modify the Project's description by following these instructions:

	Select Project from the Menu Bar, then select Description.  The Description Dialog Box will be displayed.

	Change the description information as you desire, then select OK.  The Project Summary Information Window is displayed with the updated description.

### Modifying Model Data

You may modify data in your Project's Models as follows:

	Select either Function Point, COCOMO, or Rayleigh from the Menu Bar.

	Now follow the instructions listed in Entering Model Data to enter or change the information for your project.   Note that when you exit from any data entry dialog box, the Project Summary Information Window will be displayed, rather than the Function Point, COCOMO, or Rayleigh Summary Information Window.

### Importing A Model Into Your Project

| Note: The Model which was previously in your Project will be replaced by the imported Model. The previous Model data is lost. | You may import a stand-alone Model by following these instructions:  Select Project from the Menu Bar and select either Import FP Model, Import COCOMO Model, or Import Rayleigh Model.  You will now see the Open Dialog Box. This dialog box contains a scrolling list of the Models available for import. Select the desired Model from the list and then select OK. You will be returned to the Project Summary Information Window. The results will be updated to reflect the newly imported Model. |
| --- | --- |

### Exporting A Model From Your Project

| FP Models are saved with a “.fpm” suffix. COCOMO Models are saved with a “.ccm” suffix. Rayleigh Models are saved with a “.rlm” suffix. | You may export a copy of either the Function Point, the COCOMO Model, or the Rayleigh Model into a stand-alone Model, which is then available for importing into other projects, or for stand-alone analysis. The Model in your project is unchanged. To do this: - From the Project Menu, select Export FP Model, Export COCOMO Model or Export Rayleigh Model. The Save As Dialog Box will be displayed. - Type the file name you wish to give the exported Model into the dialog box which will be displayed, then select OK. The Project Summary Information Window will be displayed. |
| --- | --- |

### Initializing Your Project

| Note: This will replace any data previously entered for all Models with default values | You may initialize both Models in your project at the same time as follows:  Select Project from the Menu Bar, then select Initialize.  The Function Point Model, the COCOMO Model, and the Rayleigh Model for this project will be initialized to default values after you confirm the operation via the Project Initialization Message Box. |
| --- | --- |

## Saving a Project

Like Models, Projects are also kept in your computer's memory while you are working with them and need to be saved to disk if you want to view or modify the information later.

To save the current Project for the first time or to save the Project under a different directory, disk and/or file name, follow these instructions:

	From the File Menu, select Save As. The Save As Dialog Box will be displayed.  If you are saving for the first time, you may select Save instead.

	To save the Project to the current drive and in the current directory, type a file name and optionally an extension for the Project in the File Name text box.

	To save the Project to a different drive and/or directory, select the drive and/or directory or type the complete location, file name, and optional extension in the File Name text box.

	Select the Save button.

To save a Project using its current name, disk, and directory:

	From the File Menu, select Save.

## Closing a Project

If you have completed work on the current Project you may close the Project and optionally save all changes you have made to the Project as follows:

	From the File Menu select Close.

	If you have made changes to the Project since it was last saved, the Close Message Box will be displayed.  Select Yes to close the Project and save all changes or select No to close the Project without your latest changes.  If you have never saved this Project before, the save will be treated as a Save As.  You may also select Cancel to abort the close operation.

## Exiting COSMOS

You may end your COSMOS session as follows:

	From the File Menu select Exit.

	If you have made changes to any open Project since it was last saved the Close Message Box will be displayed.  Select Yes to close the Project(s), save all changes, and exit or select No to close the Project(s) and exit without saving your latest changes.  If you have open Projects which have never been saved before, the save of these Projects will be treated as a Save As.  You may also select Cancel to abort the exit operation.

# Chapter 5  Managing Systems

## Creating a New System

|  | As discussed in Chapter 1, Introducing COSMOS, you may combine various projects to form a System. This will allow you to compute the total adjusted function points, total source line of code, total adjusted effort, cumulative time to develop, total time to develop, and system manpower buildup. To create a new System: - Select File from the Menu Bar, then select New from the File Menu. The New Dialog Box will be displayed. - Select System from this Dialog Box. The Description Dialog Box will now be displayed. - Enter descriptive information about the system you are modeling here and then select OK. The System Summary Information Window will be displayed with the descriptive information you just entered in the upper part of the window. The remainder of the window will show System Level Estimation Information and Project Summary Information results (the results are computed from defaults). |
| --- | --- |

## Updating an Existing System

| Tip: Systems are stored with the “.sle” extension by default | After entering a new System, you may wish to make some changes to the data. This is done as follows:  Select Open from the File Menu. You will see a dialog box from which you may select a saved System.  Select the System you wish to update and the System Summary Information Window for that System will be displayed. |
| --- | --- |

## Entering System Data

Once a new or existing system is opened, you may enter new data or change existing data. You may add existing Projects into your system.  When you create a new System, the new System is created with no projects loaded and default values for attribute data.  After you have opened a new or existing System you may change the data by following the steps listed in this section.

### Entering System Description

You may modify the System's description by following these instructions:

	Select System from the Menu Bar then select Description.  The Description Dialog Box will be displayed.

	Change the description information as you desire, then select OK.  The System Summary Information Window is displayed with the updated description.

### Adding Projects to the System

You may add projects to the system as follows:

- Select System from the Menu Bar then select Projects.  The System Level Estimation Projects Dialog Box will be displayed.

- Select the Add button to add projects to the System or the Delete button to delete projects from the System.

If you select the OK button, any changes made in the System Level Estimation Projects Dialog Box will be saved.  If you exit this box by selecting the Cancel button, changes will be disregarded.

### Setting Attributes to the System

You may set the attributes to the system as follows:

- Select System from the Menu Bar then select Attributes.  The System Level Estimation Attributes Dialog Box will be displayed

- Set the TDEV and Effort attributes.

If you select the OK button, any changes made in the System Level Estimation Attributes Dialog Box will be saved.  If you exit this box by selecting the Cancel button, changes will be disregarded.

### Initializing Your System

|  | You may initialize your System as follows:  Select System from the Menu Bar, then select Initialize. |
| --- | --- |

## Saving a System

Systems are kept in your computer's memory while you are working with them and need to be saved to disk if you want to view or modify the information later.

To save the current System for the first time or to save the System under a different directory, disk and/or file name, follow these instructions:

	From the File Menu, select Save As. The Save As Dialog Box will be displayed.  If you are saving for the first time, you may select Save instead.

	To save the System to the current drive and in the current directory, type a file name and optionally an extension for the System in the File Name text box.

	To save the System to a different drive and/or directory, select the drive and/or directory or type the complete location, file name, and optional extension in the File Name text box.

	Select the Save button.

To save a System using its current name, disk, and directory:

	From the File Menu, select Save.

## Closing a System

If you have completed work on the current System you may close the System and optionally save all changes you have made to the System as follows:

	From the File Menu select Close.

	If you have made changes to the System since it was last saved, the Close Message Box will be displayed.  Select Yes to close the System and save all changes or select No to close the System without your latest changes.  If you have never saved this System before, the save will be treated as a Save As.  You may also select Cancel to abort the close operation.

## Exiting COSMOS

You may end your COSMOS session as follows:

	From the File Menu select Exit.

	If you have made changes to any open System since it was last saved the Close Message Box will be displayed.  Select Yes to close the System(s), save all changes, and exit or select No to close the System(s) and exit without saving your latest changes.  If you have open Systems which have never been saved before, the save of these Systems will be treated as a Save As.  You may also select Cancel to abort the exit operation.

# Chapter 6  Using Advanced COSMOS Features

## Sensitivity Analysis

|  | Sensitivity Analysis allows you to adjust your model to allow for uncertainties in your model inputs (for example, function point counts or source lines of code). You may enter a percentage to indicate the level of uncertainty that you have for a model input. This adjustment percentage is then used by COSMOS to calculate a range when producing the results for your project or model. |
| --- | --- |
| To view Sensitivity Analysis results, Display Sensitivity Analysis must be marked on the Display Options Dialog Box. | The following shows the results from a COCOMO Model that has a 5% Sensitivity Adjustment applied to the estimated source lines of code: |

In this example, the 10,000 SLOC is converted into a sensitivity range of 9500 - 10,500 SLOC.  The model is then calculated based on both the estimated SLOC and the sensitivity range.  The results for the Sensitivity Analysis are displayed to the right of the results for the estimate.  This example shows that it should take between 37.3 and 41.8 Nominal and Adjusted Person Months and between 8.9 and 9.2 calendar months to develop 10,000 SLOC based on an uncertainty of 5% in your SLOC estimate.

### Entering Function Point Sensitivity Adjustments

COSMOS allows you to enter sensitivity adjustments for your Function Point Model at four different levels.  You may enter a single adjustment for the Unadjusted or Adjusted Function Points, a different adjustment for each category of function point counts, or an individual adjustment for each of fifteen function point counts.

You may enter Function Point sensitivity adjustments by following these steps:

	Select the Summary Information Window for your Function Point Model or Project to make it the active window.

	Select Function Point from the Menu Bar.   The Function Point Menu will be displayed.

	Select Sensitivity Analysis.  The Function Point Sensitivity Adjustment Dialog Box will now be displayed.

	Select the radio button for Details, Intermediate Totals, Unadjusted FPs, or Adjusted FPs to choose the level to apply the sensitivity adjustments to your model.

	You are now allowed to enter the adjustment percentages in the adjustment fields for the chosen level.  The adjustment fields available are based on the adjustment level chosen.

	After entering your adjustment percentages, select OK to keep your adjustments and return to your model's Summary Information Window.  You may also select Cancel if you wish to return to your model without keeping your changes.

### Entering COCOMO Sensitivity Adjustments

There are three different levels available for entering COCOMO Sensitivity Adjustments.  You may enter a single adjustment for the Source Lines of Code, Nominal Person Months, or Adjusted Person Months.

You may enter COCOMO sensitivity adjustments by following these steps:

	Select the Summary Information Window for your COCOMO Model or Project to make it the active window.

	Select COCOMO from the Menu Bar.   The COCOMO Menu will be displayed.

	Select Sensitivity Analysis.  The COCOMO Sensitivity Adjustment Dialog Box will now be displayed.

	Select the radio button for SLOC, Nom. Person Mon., or Adj. Person Mon. to choose the level to apply the sensitivity adjustments to your model.

	You are now allowed to enter the adjustment percentage in the adjustment field for the chosen level.  The adjustment field available will change based on the adjustment level chosen.

	After entering your adjustment percentages, select OK to keep your adjustments and return to your model's Summary Information Window.  You may also select Cancel if you wish to return to your model without keeping your changes.

### Entering Rayleigh Sensitivity Adjustments

There are five different levels available for entering Rayleigh Sensitivity Adjustments.  You may enter a single adjustment for the Source Lines of Code, Schedule, Productivity Measure, Productivity Index, or Schedule (Main Build Phase).

You may enter Rayleigh sensitivity adjustments by following these steps:

	Select the Summary Information Window for your Rayleigh Model or Project to make it the active window.

	Select Rayleigh from the Menu Bar.   The Rayleigh Menu will be displayed.

	Select Sensitivity Analysis.  The Rayleigh Sensitivity Adjustment Dialog Box will now be displayed.

	Select the radio button for SLOC, Schedule, PM, or PI to choose the level to apply the sensitivity adjustments to your model.

	You are now allowed to enter the adjustment in the adjustment field for the chosen level.  The adjustment field available will change based on the adjustment level chosen.

	After entering your adjustment, select OK to keep your adjustments and return to your model's Summary Information Window.  You may also select Cancel if you wish to return to your model without keeping your changes.

### Using Sensitivity Analysis in Projects

Projects can use Function Point, COCOMO, or Rayleigh sensitivity adjustments, but only one of them may be selected.   You may change which model adjustments are used by following these steps:

	Select Project from the Menu Bar.  The Project Menu will be displayed.

	Select either Use Function Point Sensitivity Analysis Data to use your Function Point Adjustments, or select Use COCOMO Sensitivity Analysis Data to use your COCOMO Sensitivity Adjustments, or select Use Rayleigh Sensitivity Analysis Data to use your Rayleigh Sensitivity Adjustments.  A check mark will be displayed to the left of the model that is currently selected.

You may use either the Function Point Sensitivity Adjustment Dialog Box, the COCOMO Sensitivity Adjustment Dialog Box, or the Rayleigh Sensitivity Adjustment Dialog Box to enter sensitivity adjustments for a project.  You can only enter the sensitivity adjustments for the model that is selected on the Project Menu.

### Viewing Sensitivity Analysis Results

The results for Sensitivity Analysis are displayed in the Summary Information Window for your project or model.  Sensitivity Analysis must be marked in the Display Options Dialog Box for the results to be displayed.  Sensitivity Analysis results are displayed in parentheses to the right of the original result.

### Saving, Importing, and Exporting Sensitivity Analysis Adjustments

Your Sensitivity Analysis Adjustments are automatically saved with your model or project.  When a Function Point, COCOMO, or Rayleigh Model is imported into a Project, its Sensitivity Analysis Adjustments are imported with it.  Similarly, when a model is exported from a Project, the Sensitivity Analysis Adjustments are exported with it.  However, when a COCOMO or Rayleigh Model is exported from a Project that is using Function Point Sensitivity, the exported SLOC Adjustment Percentage will be calculated to reflect the sensitivity range of the Function Point Model.

## Reverse Engineering

You can use COSMOS Reverse Engineering to do "what-if" analysis on your model.  Starting with the results from your Function Point, COCOMO, or Rayleigh Model, Reverse Engineering allows you to view the impact of scheduling or other constraints on your model.  For example, you can modify the COCOMO Time to Develop (TDEV) to determine the Source Lines of Code that can be developed in this time period.

To provide greater accuracy in Reverse Engineering calculations, the input fields allow a precision of seven digits to the right of the decimal.  The initial inputs are the values calculated by COSMOS for your model before they were rounded for the Summary Information Window.  You are not required to enter your inputs to this degree of precision.

Reverse Engineering only allows you to try different parameters on your model.  No model adjustments entered in Reverse Engineering will be saved in your actual model.  Use the Function Point, COCOMO or Rayleigh Menus to make permanent changes for your model or project.

### Using Function Point Reverse Engineering

You may perform "what-if" analysis on a Function Point Model by following these steps:

	Select the Summary Information Window for your model or project to make it the active window.

	Select Function Point from the Menu Bar.  The Function Point Menu will be displayed.

	Select Reverse Engineering.  The Function Point Reverse Engineering Dialog Box will now be displayed with the results from your Function Point Model.

	Select the radio button next to the model parameter you wish to change.

	You are now allowed to enter a new value for the selected model parameter.

	Select Calculate to update the window based on your adjustment.  COSMOS will apply your adjustment both forward and backward through the Function Point Model.  The results are displayed in the Output column.  The initial model values are still displayed in the Original column.

	You may now enter another model adjustment to the same field, select another field to be adjusted, or select Reset to refresh your inputs with the original Function Point values from your model.

	When you have completed your "what-if" analysis, select Close to return to your model or project.

### Using COCOMO Reverse Engineering

You may perform "what-if" analysis on a COCOMO Model by following these steps:

	Select the Summary Information Window for your model or project to make it the active window.

	Select COCOMO from the Menu Bar.  The COCOMO Menu will be displayed.

	Select Reverse Engineering.  The COCOMO Reverse Engineering Dialog Box will now be displayed with the results from your COCOMO Model.

	Select the radio button next to the model parameter you wish to change.

	You are now allowed to enter a new value for the selected model parameter.

	Select Calculate to update the window based on your adjustment.  COSMOS will apply your adjustment both forward and backward through the COCOMO Model.  The results are displayed in the Output column.  The initial model values are still displayed in the Original column.

	You may now enter another model adjustment to the same field, select another field to be adjusted, or select Reset to refresh your inputs with the original COCOMO values from your Model.

	When you have completed your "what-if" analysis, select Close to return to your model or project.

### Using Rayleigh Reverse Engineering

You may perform "what-if" analysis on a Rayleigh Model by following these steps:

	Select the Summary Information Window for your model or project to make it the active window.

	Select Rayleigh from the Menu Bar.  The Rayleigh Menu will be displayed.

	Select Reverse Engineering.  The Rayleigh Reverse Engineering Dialog Box will now be displayed with the results from your Rayleigh Model.

	Select the radio button next to the model parameter you wish to change.

	You are now allowed to enter a new value for the selected model parameter.

	Select Calculate to update the window based on your adjustment.  COSMOS will apply your adjustment both forward and backward through the Rayleigh Model.  The results are displayed in the Output column.  The initial model values are still displayed in the Original column.

	You may now enter another model adjustment to the same field, select another field to be adjusted, or select Reset to refresh your inputs with the original Rayleigh values from your Model.

	When you have completed your "what-if" analysis, select Close to return to your model or project.

# Chapter 7  Printing

## Printing Models/Projects

COSMOS allows you to print a report of your model or project.  The report contains the same information that is displayed on the Project or Model Summary Information Window.  The display options used to control the information shown on the Summary Information Window also controls what information is printed on the report.  See Display Options Dialog Box  for more information on how to set your display preferences.

To print a report for your project or model, follow these steps:

	If the model or project that you want to print is not open, select Open from the File Menu and then select the file for your model or project.

	Select the Summary Information Window for your model or project to make it the active window.

	Select File from the Menu Bar.  The File Menu will be displayed.

	Select Print.  The Print Dialog Box will now be displayed.

	From the Print Dialog Box, enter details about how many copies of the report you want printed or specify a page range to print.

	If the information in the Print Dialog Box is correct, select Print to send your report to the printer.

## Previewing

You may preview the report of your model or project on the screen before sending it to the printer.  To do this:

	If the model or project that you want to preview is not open, select Open from the File Menu and then select the file for your model or project.

	Select the Summary Information Window for your model or project to make it the active window.

	Select File from the Menu Bar.  The File Menu will be displayed.

	Select Print Preview.  The report will now be displayed in the Print Preview Window.

	When you have finished previewing the report, you may select Print to display the Print Dialog Box or select Close to return to your model or project.

## Setting Up Your Printer

COSMOS allows you to change printers or to modify the settings for your current printer.   To do this:

	Select File from the Menu Bar.  The File Menu will be displayed.

	Select Print Setup.  The Print Setup Dialog will now be displayed.

	Select the printer you wish to use or modify the settings for your printer.

	Select OK to apply your changes or select Cancel to disregard the changes.

# Appendix A  COSMOS System Messages

## Message Boxes

All system messages produced by the COSMOS system are displayed in Message Boxes.  Many of these messages are provided by the Microsoft Foundation Classes, upon which COSMOS was built.  See the Microsoft Foundation Classes reference manuals for more information on these messages.

## About Message Box

This message box gives general information, including version and copyright date, about the COSMOS product.  It is displayed when the About selection is chosen from the Help Menu.

## Bad File Type Message Box

"This file is not recognized by COSMOS"

This informational message is displayed when you are performing a file operation, such as Open and the specified file type is one which COSMOS does not recognize.

## Close Message Box

"Save Changes to filename"

This confirmation message is displayed when you attempt to close a Model or Project without saving the latest changes to the current Model or Project or when you exit COSMOS without saving the latest changes to any opened Model or Project.   This message gives you a chance to save the current Model or Project, to continue without saving, or to abort the close or exit operation.

## COCOMO Initialization Message Box

"All existing data for the COCOMO model will be reset to their default values.  Continue?"

This warning message is displayed when you attempt to initialize the current COCOMO Model, to give you a chance to abort the initialization process.

## Function Point Initialization Message Box

"All existing data for the function point model will be reset to their default values.  Continue?"

This warning message is displayed when you attempt to initialize the current Function Point Model, to give you a chance to abort the initialization process.

## Rayleigh Initialization Message Box

"All existing data for the Rayleigh model will be reset to their default values.  Continue?"

This warning message is displayed when you attempt to initialize the current Rayleigh Model, to give you a chance to abort the initialization process.

## Integer Message Box

"Please enter an integer"

This error message is displayed any time you enter non-integer data into a text box when COSMOS is expecting integer data.  Select OK and correct the input.

## Load Languages for Customization Message Box

"Load languages from filename?  (Selecting 'NO' will load the COSMOS default languages.)"

This warning message is displayed when you have a Function Point Model or a Project as the active window and select Language Customization from the Options Menu.  The Languages Customization Dialog Box allows you to modify the languages and language multipliers used by COSMOS.  This message box allows you to choose whether to load the Languages Customization Dialog Box with the languages saved with your model or project or with the default languages list from the COSMOS.INI file.  Regardless or which option you choose, you will be able to save your modified languages list to your active model and/or to the COSMOS.INI file.

## Project Initialization Message Box

"All existing data for the project will be reset to their default values.  Continue?"

This warning message is displayed when you attempt to initialize the current Project, to give you a chance to abort the initialization process.

## Save As Message Box

"This file already exists.  Replace existing file?"

If you enter the file specification of an existing saved Model or Project during a Save As, this confirmation will be displayed, allowing you to continue or abort the save.

## COSMOS.INI File Not Found Message Box

If trying to run the COSMOS application without a COSMOS.INI file, this Not Found Message Box will be displayed.

# Appendix B  Troubleshooting

## Correcting System Errors

| Problem | Solution |
| --- | --- |
| Cost Driver Window will not open on a new model or project | Make sure the file COSMOS.INI exists in the same directory as COSMOS.EXE. If the COSMOS.INI file exists, replace it with an unmodified version from the COSMOS ZIP file. |
| Cost Driver Window will not open on an existing model or project | The Cost Drivers saved with the model or project have been corrupted or do not exist. Using a standard text editor, replace the Product_CDA_Group, Hardware_CDA_Group, Personnel_CDA_Group, and Project_CDA_Group in the model or project file with the corresponding section from the COSMOS.INI file. See the COSMOS Technical Reference, Appendix A: INI File Entries for more information. |
| No languages available in Function Point Count Dialog Box on a new model or project | Make sure the file COSMOS.INI exists in the same directory as COSMOS.EXE. If the COSMOS.INI file exists, replace it with an unmodified version from the COSMOS ZIP file. |
| No languages available in Function Point Count Dialog Box on an existing model or project | The Languages section saved with the model have been corrupted or do not exist. Using a standard text editor, replace the Languages section of the model or project file with the Languages section from the COSMOS.INI file. See the COSMOS Technical Reference, Appendix A: INI File Entries for more information. |
| Sensitivity Analysis results do not appear on the Project or Model Summary Information Window | Sensitivity Analysis must be marked in the Display Options Dialog Box for Sensitivity Analysis to be displayed. |

# Appendix C  References

## List of References

1.	Albrecht, Allan J. and John E. Gaffney, Jr., "Software Function, Source Lines of Code and Development Effort Prediction: A Software Science Validation," IEEE Transactions on Software Engineering, Volume SE-9, No. 6, November, 1983.

2.	Boehm, Barry W., "Software Engineering Economics,"  IEEE Transactions on Software Engineering, Volume SE-10, Number 1, January, 1984, pp. 4-21.

3.	Boehm, Barry W., Software Engineering Economics, 1981, Prentice-Hall, Inc.  A Simon & Schuster Company.  Upper Saddle River, New Jersey 07458, pp. 90.

4.	Boehm, Barry W., Software Engineering Economics, 1981, Prentice-Hall Inc. A Simon & Shuster Company.  Upper Saddle River, New Jersey 07458, pp. 114-163.

5.	International Function Point Users Group, "Function Point Counting Practices Manual" (Release 4.0), January 1994.

6.	Lawrence H. Putnam, "Rayleigh Model," Encyclopedia of Software Engineering,1994, pp. 192-1000.

7.	Microsoft Corporation, "User's Guide For The Microsoft Windows Operating System," 1990.

8.	Jones, Capers, "Backfiring: Converting Lines of Code to Function Points," Computer, November, 1995, pp. 87-88.

9.	Pressman, Roger, Software Engineering: A Practitioners Approach, 3rd edition, McGraw-Hill, New York, NY, 1992, pp. 48-61 and 84-95.

10.	Thayer, Richard H., Tutorial: Software Engineering Project Management, IEEE Computer Society Press, Los Alamitos, CA, 1988.

# Glossary of Terms

## Analyst

A person whose role is the investigation and determination of a user's needs. The findings of the analyst form the basis of the Software Requirements Specification (SRS) of an application.

## COCOMO

The Constructive Cost Model, published in 1981 by Dr. Barry Boehm, which defines a method of estimating required software project effort and schedule, given project lines of code.

## COCOMO Model

A saved collection of descriptive information, COCOMO attributes, COCOMO cost driver attribute ratings and the resulting effort and project time estimates.

## COCOMO Model Type

The type of COCOMO Model used.  Model types may be Basic, Intermediate, or Advanced.  Currently, COSMOS only uses the Intermediate COCOMO model type.

## COCOMO Phase Distribution

The Phase Distribution consists of three phases: Product Design Phase, Programming Phase, and Integration and Test Phase.

## Component

A Function Point Model, a COCOMO Model, Rayleigh Model, or a Project.

## Constructive Cost Model

See COCOMO Model.

## Cost Driver

A factor which may have a positive or negative impact on the effort required to complete a software development project.

## EAF

See Effort Adjustment Factor.

## Effort Adjustment Factor

The product of all COCOMO cost driver attribute effort multipliers, used to adjust the project person months in Intermediate and Advanced COCOMO.

## Embedded Mode

A classification in COCOMO used for ambitious projects from unfamiliar, unforgiving, and tightly constrained environments.

## External Input

A user data type or user control type that crosses the application boundary and adds, modifies, or deletes internal logical files. The input is unique if either the input format or the processing logic is unique. An external input can have a ranking of low, average or high.

## External Inquiry

Either (1) an input/output combination that crosses the application boundary and retrieves data or (2) control information for immediate response. The inquiry does not modify data. An external inquiry can have a ranking of low, average or high.

## External Interface File

A set of logically related data used outside the application. An external interface file can have a ranking of low, average or high.

## External Output

A user data type or user control type that leaves the application boundary. The output is unique if the input format or the processing logic is unique.  Output can be files, reports, or messages sent to users or to other applications. An external output can have a ranking of low, average or high.

## Function Point Model

A saved collection of descriptive information, input/output/file counts, value adjustment factors, and the resulting function point count and estimated source lines of code.

## Function Points

A measure of the amount of function a software system is to perform, developed by Allan J. Albrecht.  The number of function points a system has is a weighted sum of the number of inputs, outputs, files, and inquiries provided to or generated by the system.

## Internal Logical File

A set of logically related data used inside the application. An internal logical file can have a ranking of low, average or high.

## Main Build Phase

Main Build Phase is one of the three phases of the Rayleigh approach.  This phase begins at the start of the detail logic design and ends when the system is fully operational.  These phases lead to the calculation of the Manpower Buildup Index.

## Model

Either a Function Point Model, a COCOMO Model, or a Rayleigh Model.

## Organic Mode

A classification used in COCOMO to describe projects which come from stable, familiar, forgiving, and relatively unconstrained environments.

## Person Month

A unit of measurement for effort used in estimating schedules.  This is the amount of work a single person can do in one calendar month.

## Project

A combination of one Function Point Model, one COCOMO Model, and one Rayleigh Model plus descriptive information about the project.  The lines of code calculated in the Function Point Model serve as an input to the COCOMO Model and to the Rayleigh Model.

## Rayleigh Model

A saved collection of descriptive information, Rayleigh attributes, and the resulting manpower buildup estimate.

## Reverse Engineering

"What-if" analysis on a model to test the impact of scheduling or other constraints on the model.

## Semi-detached Mode

A classification used in COCOMO for intermediate-sized projects which have some rigid constraints.

## Sensitivity Analysis

Adjustment of a model or project to allow an estimated range to be produced based on uncertain model inputs.

## SLOC

See source lines of code.

## Software Engineer

A person educated, trained and/or experienced in the analysis, design, coding, testing, and documentation techniques of developing software applications.

## Software Reliability

The probability that a software will perform its functions without error.

## Source Lines of Code

The number of lines of code delivered for a project, excluding comment lines.

## System

A collection of one or more projects which implement an incrementally design and constructed software system.

## TDEV

Time of development in calendar months.

## Turnaround Time

The time between the submission of a request and the return of the results.

## Virtual Machine

A term used in the COCOMO Model in reference to the hardware and operating system environment of an application.

# Index

A

About Message Box 46, 65

Albrecht, Allen 68

analyst 8

Attributes Dialog Box 34, 36, 39, 49, 50

B

Boehm, Barry 7, 68

C

Close Message Box 51, 54, 57, 65

COCOMO 13, 22, 43, 47, 53, 60

COCOMO Complexity Influence Assignments 7

COCOMO formulae 4

COCOMO Initialization Message Box 49, 65

COCOMO Menu 13, 24, 34, 35, 36, 37, 38, 42, 43, 49, 59, 61

COCOMO Model 17, 35, 38, 39, 42, 43, 47, 49, 53, 59, 60

COCOMO Reverse Engineering Dialog Box 35, 38, 39, 61

COCOMO Sensitivity Adjustment Dialog Box 59, 60

COCOMO Sensitivity Adjustments Dialog Box 37

COCOMO Summary Information Window 35, 49

component 16

COSMOS.INI 67

cost driver 7, 34, 37, 41, 49, 67

Cost Drivers Dialog Box 34, 37, 41, 49

Creating a New Model 48

customizing ii, 43, 44, 45, 63, 66

D

Description Dialog Box i, 17, 21, 24, 25, 26, 29, 35, 39, 47, 48, 49, 50, 52, 53, 55

Display Options Dialog Box ii, 24, 26, 36, 43, 44, 58, 60, 63, 67

E

EAF 7

effort adjustment factor 7

Entering Model Data 53

Export COCOMO Model 21, 53

Export FP Model 21, 53

Export Rayleigh Model 53

external input 31

external inquiry 6, 31

external interface file 5, 31

external output 5, 31

F

File Menu 1, 16, 47, 51, 52, 54, 55, 56, 57, 63

File Menu 17, 18, 19, 20, 63

function count 6, 29, 33, 48, 58

Function Count Dialog Box 29, 32, 34, 67

Function Point 13, 22, 43, 47, 53, 60

Function Point Complexity Assignments 4

Function Point Formulae 4

Function Point Initialization Message Box 48, 65

Function Point Menu 24, 30, 31, 32, 33, 34, 48, 58, 61

Function Point Model 13, 17, 22, 29, 33, 34, 44, 47, 48, 53, 60, 61, 62, 66

Function Point Reverse Engineering Dialog Box 29, 33, 61

Function Point Sensitivity Adjustment Dialog Box 58, 60

Function Point Sensitivity Adjustments Dialog Box 32

Function Point Summary Information Window 48

H

Help Menu 46, 65

I

Import COCOMO Model 21, 53

Import FP Model 21, 53

Import Rayleigh Model 22, 53

INI File Entries 45, 67

L

language 7, 8, 29, 30, 34, 43, 44, 48, 66

Language Customization Dialog Box 44

Load Languages for Customization Message Box 45

logical internal file 31

M

Manpower Buildup Index 40, 71

Manpower Buildup Index Equation 10

Menu Bar ii, 1, 16, 20, 21, 25, 29, 34, 39, 43, 46, 47, 48, 49, 50, 52, 53, 55, 56, 58, 59, 60, 61, 62, 63

N

New Dialog Box 47, 52, 55

O

Open Dialog Box 53

Options Menu 43, 44, 45, 66

P

Phase Distribution 36, 69

preview ii, 16, 63

print ii, 16, 63, 64

Print Dialog Box 19, 20, 63

Print Preview Window 63

Print Setup Dialog 64

Print Setup Dialog Box 19

printer 19, 20, 63

processing complexity 31, 48

Processing Complexity Adjustment Dialog Box 31

programming language 7, 8, 29, 34, 43, 44, 48, 66

programming language 7, 8, 29, 30, 48

Project 13, 22, 43

Project Initialization Message Box 53, 66

Project Menu 22, 53, 60

Project Summary Information Window 24, 26, 52, 53, 55

R

Rayleigh 13, 22, 43, 47, 53, 60

Rayleigh Formulae 4

Rayleigh Initialization Message Box 50

Rayleigh Menu 24, 26, 40, 41, 42, 50, 59, 62

Rayleigh Model 44, 47, 52, 53, 60

Rayleigh Reverse Engineering Dialog Box 62

Rayleigh Sensitivity Adjustment Dialog Box 59, 60

Rayleigh Summary Information Window 50

S

Save As Dialog Box 51, 53, 54, 56

Save As Message Box 66

Saving a Model 47

Sensitivity Adjustments 21, 23, 32, 37, 58, 59, 60

Sensitivity Analysis ii, 21, 29, 35, 58, 59, 60, 67

shortcut keys 16

shortcut keys 34, 39, 43, 46

SLOC 7, 34, 35, 38, 39, 40, 42, 43, 45, 58, 59

software equation 10

source lines of code 7, 30, 42, 43, 45, 59

source lines of code 34, 35, 38, 39, 40, 42, 58, 59

stand-alone model 47, 53

Status Bar 13, 20

Summary Information Window 25, 44, 47

Summary Information Window 34, 35, 39, 43, 58, 59, 60, 61, 62, 63, 67

system ii, 4, 6, 7, 8, 10, 11, 19, 20, 26, 27, 40, 41, 50, 55, 56, 65, 71, 72, 73

System 1, iii, 1, 3, 4, 11, 13, 14, 17, 18, 25, 26, 27, 28, 41, 44, 45, 55, 56, 57, 65, 67, 68, 72

T

TDEV 60

The Function Point Count Dialog Box 48

Time to Develop 60

Toolbar 13, 20

turnaround time 8

V

Value Adjustment Factor Dialog Box 48

W

Window Menu 45