COSMOS Documentation Series

COSMOS
Technical Reference

#### Version 4.1

#### Revision E5

The Software Cost Modeling System
By the ETSU Design Studio Groups at Oak Ridge

 1998 East Tennessee State University - Department of Computer and Information Sciences.  All rights reserved.

Printed in the United States of America

Arial and Times New Roman fonts.  Copyright  1991 Monotype Corporation PLC.  All rights reserved.

Companies, names, and data used in examples herein are fictitious unless otherwise noted.

MS-DOS is a registered trademark of Microsoft Corporation.

Windows 95 and Windows NT are trademarks of Microsoft Corporation

IBM and OS/2 are registered trademarks of International Business Machines, Inc.

Arial and Times New Roman are registered trademarks of The Monotype Corporation PLC.

The "Black Hole" image was obtained from NASA Archives.

Contents

Preface	6

Revisions	6

Revision 4.1  5/1/1998	6

Notices	7

Disclaimers	7

DISCLAIMER OF WARRANTY	7

Acknowledgements	7

Chapter 1: Introduction 	8

Purpose of COSMOS	8

Brief COSMOS Product Description	8

COSMOS Capabilities and Theory of Operation	8

COSMOS Versions and Development History	11

COSMOS Personnel	11

Chapter 2: Function Point Model 	12

Introduction to Function Points	12

Function Point Analysis	13

Application Boundary	14

Functionality	14

Data Functionality	14

Transaction Functionality	16

Complexity	18

Complexity Weights	19

Value Adjustment Factor and Adjusted Function Points	20

Backfire Method	20

Added, Changed, and Deleted Functionality	21

Comparison of Function Points and SLOC	22

COSMOS and Function Point Analysis	23

Function Point Formulae	24

Unadjusted Function Point Count	24

Total Degree of Influence	24

Value Adjustment Factor	24

Adjusted Function Point Count	25

Source Lines of Code: Backfire Method	25

Differences in Function Point Terminology	25

Chapter 3: COCOMO Model 	26

COCOMO Model Description	26

COCOMO Equations	27

SLOC and Delivered Source Instructions	27

COCOMO Modes	28

COCOMO Cost Drivers	28

Product Attributes	29

Hardware Attributes	29

Personnel Attributes	29

Project Attributes	30

COCOMO Complexity Influence Assignments	31

COCOMO Phase Distribution	35

COCOMO Formulae	36

Unadjusted Person Months	36

Effort Adjustment Factor	36

Adjusted Person Months	36

Time to Develop	36

COCOMO II	37

Chapter 4: Rayleigh Model 	38

Rayleigh Distribution	38

Rayleigh Equations – General Description	38

Putnam’s Analysis: Software Equation	39

Manpower Buildup Index	40

Rayleigh Model	40

Development Phases	41

Application Type and Productivity	41

Rayleigh Formulae	42

Software Equation	42

Manpower Buildup Index Equation	42

Chapter 5: Project Estimation 	43

Overview	43

Model Interrelationships	44

Import and Export of Models	44

Project Report	45

Chapter 6: System Estimation 	47

System Description	47

System Development Phases	48

System-Level Effort Estimates	48

System-Level Schedule Estimates	48

System-Level Manpower Buildup Index Level	50

System-Level Project Specification and Management	50

Schedule Compression	50

System Development and COCOMO	52

System Output Report	53

References 	54

Glossary 	55

Analyst	55

COCOMO	55

COCOMO Model	55

COCOMO Model Type	55

COCOMO Phase Distribution	55

Component	55

Constructive Cost Model	55

Cost Driver	55

EAF	56

Effort Adjustment Factor	56

Embedded Mode	56

External Input	56

External Inquiry	56

External Interface File	56

External Output	56

Function Point Model	56

Function Points	57

General System Characteristics	57

GSC	57

Internal Logical File	57

Main Build Phase	57

Model	57

Organic Mode	57

Person Month	57

Project	58

Rayleigh Model	58

Reverse Engineering	58

Semi-detached Mode	58

Sensitivity Analysis	58

SLOC	58

Software Engineer	58

Software Reliability	58

Source Lines of Code	58

System	59

TDEV	59

Turnaround Time	59

Virtual Machine	59

Appendix: COSMOS INItialization File Entries	60

COSMOS.INI	60

Default Values	60

Customizing	68

Index	70

# Preface

## Revisions

### Revision 4.1  5/1/1998

This is the original version of the Technical Reference document.  The COSMOS Technical Reference was formed from material from the COSMOS User’s Guide (version 3.3), along with material created in the development of COSMOS versions 3.2 through 4.1.  The following table describes the layout of material in the COSMOS version 4.1 User’s Guide and Technical Reference, compared with the layout of material in the COSMOS version 3.3 User’s Guide.

| Chapter | User Guide V3.3 | User Guide V4.1 | Technical Reference |
| --- | --- | --- | --- |
| 1 | Introducing COSMOS | Introducing COSMOS | Introduction (new material) |
| 2 | Understanding COSMOS Basics | Understanding COSMOS Basics | Function Point Model (new material and UG V3.3 Appendices D, E, & F) |
| 3 | Managing Stand-Alone Models | Managing Stand-Alone Models | COCOMO Model (new material and UG V3.3 Appendices D, F, & G) |
| 4 | Managing Projects | Managing Projects | Rayleigh Model (new material and UG V3.3 Appendices D & H) |
| 5 | Using Advanced COSMOS Features | Managing Systems | Project (new material) |
| 6 | Printing | Using Advanced COSMOS Features | System (new material) |
| 7 | – | Printing | N/A |
| A | COSMOS System Messages | COSMOS System Messages | N/A |
| B | Troubleshooting | Troubleshooting | N/A |
| C | INI File Entries | References | N/A |
| D | Formulae | N/A | [Material now in TR Chapters 2, 3, and 4] |
| E | Differences in Function Point Terminology | N/A | [Material now in TR Chapter 2] |
| F | Complexity Assignment Guidance | N/A | [Material now in TR Chapters 2 and 3] |
| G | COCOMO Phase Distribution | N/A | [Material now in TR Chapter 3] |
| H | The Rayleigh Model | N/A | [Material now in TR Chapter 4] |
| I | References | N/A | References |
|  | Glossary | Glossary | Glossary |

## Notices

This product is provided as "freeware".  Any use or sale for profit is strictly prohibited.

## Disclaimers

### DISCLAIMER OF WARRANTY

This software and its manuals are being provided "as is" without warranties as to performance.  This program is being provided without any express or implied warranties whatsoever.  Because of the diversity of conditions and hardware under which this program may be used, no warranty of fitness for a particular purpose is offered.  The user must assume the entire risk of using the program.  Any liability of the provider is limited exclusively to product replacement.

## Acknowledgements

This document contains material that has been extracted from the International Function Point User’s Group (IFPUG).  It is reproduced in this document with permission of IFPUG.

# Chapter 1: Introduction

## Purpose of COSMOS

The Software Cost Modeling System, or COSMOS, was created to produce estimates of the effort and schedule required for software development projects.  To accomplish this goal, COSMOS combines techniques that have hitherto been described and implemented separately.  The result is a collection of models into a single package.  These models collectively describe and characterize, or quantify, the parameters that most affect the required effort and schedule for a development project.  This is true for most development projects, since the techniques employed by COSMOS are as independent of specific implementation technology and design details as possible.  Of course, there are special cases and niche projects that COSMOS will fail to forecast with the accuracy produced for mainstream software development.  “Your mileage may vary”.

## Brief COSMOS Product Description

COSMOS is an estimation tool that runs on PCs with Microsoft Windows 95  or Microsoft Windows NT .  Detailed instructions for using COSMOS are given in the COSMOS User’s Guide and the on-line help.  Further examples are given in the COSMOS User’s Guide.

COSMOS produces estimates of a software project's effort, schedule, and staffing requirements.  COSMOS combines Allan Albrecht’s (IFPUG standard) function point analysis, Barry Boehm's COCOMO model, and Lawrence Putnam’s adaptation of the Rayleigh distribution to produce these estimates.  COSMOS combines three landmark software engineering models into one system for sophisticated project forecasting.  These models are described below.  While the parameters used to tune COSMOS come from principal software engineering references, the knowledgeable user may re-tune COSMOS to align with conditions in his or her development environment.

## COSMOS Capabilities and Theory of Operation

COSMOS produces estimates of a software development project’s effort or schedule.  In a nutshell, COSMOS works as follows:

- A project is sized using standard Function Point Analysis (as described in the International Function Point User’s Group [IFPUG] Counting Practices Manual version 4.0).  Function points and how they are counted are described in chapter two of this document.  An implementation language is selected, and number of source lines of code (SLOC) is estimated from the adjusted function point count and the selected programming language using the Backfire Method.  While not a part of function point analysis per se, the Backfire Method is used with the function point count for a project, and is built into COSMOS’s implementation of the Function Point Model.  The Backfire Method is also described in chapter two.

- The SLOC estimate is fed into a selected COCOMO Model, along with cost drivers.  The COCOMO Model computes effort and schedule estimates.  COCOMO estimation is described in chapter three.

- The SLOC and schedule are fed into a Rayleigh Model that produces a “Manpower Buildup Index” (MBI).  The MBI reflects the rapidity with which a project is staffed and scheduled. The MBI predicts whether (and with what difficulty) the project can be accomplished within the time frame determined by the COCOMO model.  The COSMOS Rayleigh Model is described in chapter four.

The three COSMOS models – Function Point, COCOMO, and Rayleigh – are combined and linked into a project in order to produce estimates of effort, schedule, and staffing based on the project’s size (i.e. functionality) and the development environment’s most influential characteristics.

###### COSMOS Project Level Estimation

Since function points can be accurately counted early in the software development cycle, COSMOS’s use of function points as the project size input allows for earlier, more accurate estimates than products that require source lines of code as the primary input.  COSMOS combines the advantages of function point analysis with the robustness of the statistically calibrated COCOMO and Rayleigh models.

In addition to project-level estimation, COSMOS can produce stand-alone Function Point, COCOMO, and Rayleigh models (the three kinds used to construct a project).  These stand-alone models can be imported into other projects.  They can also be used to support the use of other parametric cost estimation tools.  For example, a COSMOS Function Point model can produce a SLOC estimate for use in products that require SLOC as the project size input.

Groups of projects can be collected into a “System”, and the effort and schedule for developing the entire system can be estimated.

COSMOS System Level Estimation

COSMOS includes sensitivity analysis and reverse engineering capabilities that help both project managers and lead technical specialists quantify uncertainties, and grapple with "What if?" questions.  Sensitivity analysis produces a range of calculated values based on the user-specified lower and upper bound values of a selected variable, generally plus-or-minus n%.   The COSMOS calculations are repeated for the lower and upper bound values, and these are shown as a range along with the other calculated outputs.  Reverse engineering allows the user to select an independent variable and its value along with the dependent variable to hold fixed (if appropriate). COSMOS recalculates the non-fixed dependent variables, running the model equations “in reverse”.  Reverse engineering is not discussed in this technical reference, but the reader can easily derive the reverse engineering equations using the formulae presented herein.

More detailed information on the models that are incorporated into COSMOS, as well as on project-level and system level estimation, are given in the following chapters of this Technical Reference.

## COSMOS Versions and Development History

COSMOS version 2.2 is a 16-bit application that runs under Microsoft Windows 3.1 , Windows 95 , or Windows NT .  It supports project estimation, and Function Point and COCOMO Models that include sensitivity analysis and reverse engineering capabilities.  Beginning with version 3.1, COSMOS is a 32-bit application that runs under Microsoft Windows 95  or Windows NT  version 4.0 or above.  Version 3.2 added support for the Rayleigh Model.  Version 3.3 added Rayleigh sensitivity analysis and reverse engineering.  Version 4.1 added support for System-level estimation.  COSMOS Version 4.1 is a superset of the capabilities of COSMOS version 2.2.

This Technical Reference describes the current 32-bit version of COSMOS.  Portions of this document are applicable to the 16-bit version of COSMOS (version 2.2).

## COSMOS Personnel

COSMOS was produced over the course of two years as a laboratory project by career software development professionals who are graduate students in East Tennessee State University’s Software Engineering program.

The personnel who worked on COSMOS are, in alphabetical order:

| OREDS Team Original Development through Version 2.2 | EDSOR Team Subsequent Development through Version 4.1 |
| --- | --- |
| David Bond | Mike Bell |
| Gaye Bond | Mike Holloway |
| Jane Gaby | Brad Mitchell |
| Chris Hilemon | Clyde Senviel |
| Jeff Jones | Selene Tolbert |
| Mary Gail Manes |  |
| Dana McLaughlin |  |
| Kris Sammons |  |
| Tony Smith |  |
| Professor: Joel Henry, PhD. | Professor: Jeff Jones, M.S. |

# Chapter 2: Function Point Model

## Introduction to Function Points

Since its introduction by Allan Albrecht in 1983, the function point metric has become the leading measure of software size for both applications and development projects.  The use of function points has several advantages over the other leading measure of software size, source lines of code (SLOC).  This chapter will describe what function points are and give some of their advantages.

Software metrics can be broadly characterized as either internal or external.  Or, one might say a particular metric describes the software implementation or the software environment, what goes on inside the software or what happens outside the software.  A few metrics (e.g., feature points) describe elements of both internals and externals, but for the most part, measures are usually internal or external.  Internal metrics tell us much about how the software is designed or constructed.  They measure the relative strength or efficiency of the design, construction, or execution.  Internal metrics tell us little about how the software is used or how it impacts the environment in which it operates, including the impact on users or the benefit to them.  On the other hand, external measures tell us little about how the software is constructed, little about the detailed design of the software modules, little about how the software actually works.  External metrics describe the software in terms of what it delivers, produces, consumes, or saves.  The factors that influence the software development can similarly be characterized either (1) external, environmental, or high-level—independent of the software design, or (2) internal, implementation, or low-level—dependent on the software design.  The key to effective software estimation is to formulate the estimate entirely in terms of external metrics and development factors.  Our goal is parametric software estimation that relies on NO internal metrics or development factors as inputs.  All of the metrics and development factors utilized by COSMOS can be determined in advance of software design.

| External Metrics and Factors | Internal Metrics |
| --- | --- |
| Function Points [IFPUG] | Source Lines of Code (SLOC) |
| General System Characteristics | Feature Point Algorithms [Capers Jones] |
| Project Constraints (COCOMO Development Mode) | Cumulative Cyclic Dependency (CCD) [John Lakos] |
| COCOMO Cost Drivers | Operators and Operands [Maurice Halstead] |
| Application Type or Productivity | Metrics for Object-Oriented Software Engineering (MOOSE) [Chidamer and Kemerer] |

The advantage of an external metric is that one does not require a detailed design or source listing to perform the measurement.  External metrics are independent of the specific design or implementation technology used.  In contrast to source lines of code, function point counting is an external metric. One would not learn much about how a software application actually works by examining its function point analysis.  Rather, one would learn about what the software does and how it impacts its environment.  Function points attempt to quantify one of the most fundamental and difficult to define concepts applicable to a software application, its functionality.  This measure of functionality is of more use in project and portfolio management than in detailed software design and construction.

The COSMOS Function Point Model consists of two parts.  The first is Function Point Analysis, which produces an adjusted function point count.  The second is the Backfire Method, which estimates SLOC from an adjusted function point count.

## Function Point Analysis

What are function points?  How are they counted, and what do they measure?  These questions are answered below.

The functionality is identified and quantified by looking at logical data groups that are used and maintained by the application, and information that enters and exits the application.

One starts to quantify an application’s functionality by defining its boundary.

## Application Boundary

The first step in the function point analysis of a software project is to establish the boundary of the application that the project establishes or enhances.  The boundary stakes out the business processes that are automated or supported by the application.  The boundary should be kept firmly in mind during the analysis.  The functionality delivered by the project is measured based on data that enter and exit the application (pass through its boundary), and data maintained within the application boundary as well as data that are used within the application but maintained outside the boundary.  Knowing where the boundary is and what is inside and outside of it, in user-identifiable terms, is crucial to distinguishing the different kinds of functionality from each other.

## Functionality

As the name implies, Function Points measure the functionality visible to the user and delivered to the user.  Functionality is divided into two kinds:

- Data functionality supplied through logical groups of data that are read or maintained.

- Transaction functionality supplied through processes provided by the software.

The functionality delivered is the sum of these two kinds of functionality:

Functionality = Data Functionality + Transaction Functionality

## Data Functionality

Data functionality is provided by files, database tables, objects, and other information storage entities.  Physical data sources are grouped into conceptually complete, or “logical” groups of data. There are two kinds of data groups in function point analysis.

- Logical data groups that are maintained within the application boundary (i.e. written by the application).  These are called Internal Logical Files (ILFs).

- Logical data groups that provide information to the application, but are maintained by another application.  These are called External Interface Files (EIFs).

## Transaction Functionality

Transaction functionality is provided by processes furnished by the application.  These processes group the individual actions of the program into self-consistent, conceptually complete operations that process or produce information and leave the software and its data in a stable, consistent state.  These are “elementary processes”, the smallest units of activity that are meaningful to the user. .  Smaller units of activity, and activity that does not leave the application in a stable state, are not counted.  The processes within the application are identified by information that enters and exits the application.  Data that crosses the application boundary signals the operation of transaction functions.  There are three kinds of transaction functions in function point analysis.

- External Input (EI) – identified by data or control information that comes into the application to perform an elementary process.  Control information is information used by the application to satisfy a business process requirement.  Data that comes into the application is used to maintain an Internal Logical File.  Typically, EI processes are used to add, change, or delete information.

- External Output (EO) – identified by calculated or derived data that exits the application.  Often, EO processes are reports.

- External Inquiry (EQ) – identified by an input/output combination that supplies a body of data in response to a request from outside the application.  The data contains lookup information only, no calculated or derived data are supplied (otherwise the process is an External Output).  The data supplied to application to perform the lookup does not maintain an Internal Logical File (otherwise the process is an External Input).  Typically, EQ processes are requests to view information.

Each function produced or enhanced by the development project is identified and weighted according to its complexity.  The sum of the weighted scores for all functions becomes the unadjusted function point count for the project.

## Complexity

Each function identified in the function point analysis – EI, EO, EQ, ILF, or EIF – is weighted according to its complexity.

For data functions (IFLs and EIFs), the complexity is determined and rated by the numbers of Record Element Types (RETs – distinct record formats) and the number of Data Element Types (DETs – distinct fields) contained within the logical group of data.

For Internal Logical Files:

|  | 1 to 19 DET | 20 to 50 DET | 51 or more DET |
| --- | --- | --- | --- |
| 1 RET | Low | Low | Average |
| 2-5 RET | Low | Average | High |
| 6 or more RET | Average | High | High |

| Where | DET = | Number of data element types (fields) |
| --- | --- | --- |
|  | RET = | Number of Record Element Types (Subgroups of Internal Logical Files based on logical/user view of the data) |

For External Interface Files

|  | 1 to 19 DET | 20 to 50 DET | 51 or more DET |
| --- | --- | --- | --- |
| 1 RET | Low | Low | Average |
| 2-5 RET | Low | Average | High |
| 6 or more RET | Average | High | High |

| Where | DET = | Number of data element types (fields) |
| --- | --- | --- |
|  | RET = | Number of Record Element Types (Subgroups of External Logical Files based on logical/user view of the data) |

For transaction functions (EIs, EOs, and EQs), the complexity is determined and rated by the numbers of File Types Referenced (FTRs – number of ILFs and EIFs used by the process) and the number of Data Element Types (DETs – distinct fields) added, changed, deleted, or produced in outputs.

For External Inputs

|  | 1 to 4 DET | 5 to 15 DET | 16 or more DET |
| --- | --- | --- | --- |
| 0-1 FTR | Low | Low | Average |
| 2 FTR | Low | Average | High |
| 3 or more FTR | Average | High | High |

| Where | DET = | Number of data element types (fields) |
| --- | --- | --- |
|  | FTR = | Number of Internal Logical Files maintained or referenced plus number of External Interface files referenced during processing of the External Input |

For External Outputs

|  | 1 to 5 DET | 6 to 19 DET | 20 or more DET |
| --- | --- | --- | --- |
| 0-1 FTR | Low | Low | Average |
| 2-3 FTR | Low | Average | High |
| 4 or more FTR | Average | High | High |

| Where | DET = | Number of data element types (fields) |
| --- | --- | --- |
|  | FTR = | Number of Internal Logical Files referenced plus number of External Interface files referenced during processing of the External Output |

For External Inquiries

	Compute the input side of the External Inquiry (just like an External Input)

	Compute the output side of the External Inquiry (just like an External Output)

	Use the higher of the two results

### Complexity Weights

The complexity weights for the different functions are given as follows:

|  |  | LOW | AVERAGE | HIGH |
| --- | --- | --- | --- | --- |
| Internal Logical File | ILF | 7 | 10 | 15 |
| External Interface File | EIF | 5 | 7 | 10 |
| External Input | EI | 3 | 4 | 6 |
| External Output | EO | 4 | 5 | 7 |
| External Inquiry | EQ | 3 | 4 | 6 |

## Value Adjustment Factor and Adjusted Function Points

The unadjusted function point count is adjusted by multiplying it by the Value Adjustment Factor (VAF) to produce the final adjusted function point count.  The Value Adjustment Factor is determined from the ratings of 14 “General System Characteristics” (GSC) that are intended to take into account special requirements placed on the application.

The 14 General System Characteristics are as follows:

| Trait | Description |
| --- | --- |
| Data Communications | The degree to which communication facilities are required for the application |
| Distributed Functions | The existence of distributed functions in the application |
| Performance | The degree to which performance is a critical issue |
| Heavily Used Configuration | The installation of the application on current equipment that is heavily used |
| Transaction Rate | The measurement of the transaction rate |
| On-line Data Entry | The complexity of on-line data transactions with consideration to the number of screens and functions |
| End User Efficiency | The degree to which on-line functions promote end user efficiency |
| On-line Update | The use of on-line updates to master files |
| Complex Processing | The amount of complex processing. Complex processing may have many control interactions and decision points, a significant number of logical and mathematical equations, or extensive exception processing |
| Reusability | The evaluation of code in terms of reusability |
| Installation Ease | The degree to which the application is easily installed |
| Operational Ease | The proficiency of the application's general operations such as startup, backup, recovery, and shutdown |
| Multiple Sites | The number of installations of the application across diverse organizations or sites |
| Facilitate Change | The appraisal of the application in terms of how easily it accommodates user modifications such as providing a flexible query facility or functions for setting and maintaining user-defined parameters |

Each of these are rated numerically from 0 (not present or no influence) to 5 (strong influence throughout).  The scores of all 14 GSCs are summed to produce a “Total Degree of Influence” (TDI).  The Value Adjustment Factor is obtained by dividing the Total Degree of Influence by 100 and adding the result to 0.65.  Thus the VAF will have a value from 0.65 to 1.35.

The adjusted function point count is the product of the unadjusted count and the value adjustment factor.  The adjusted function point count can be used to produce an estimate of source lines of code by using the Backfire Method.

## Backfire Method

The Backfire Method is a means of estimating the count of SLOC that is equivalent to the adjusted function point count.  Software Productivity Research, a firm lead by software metrics expert Capers Jones, has established “language multiplier” values for the major programming languages.  The language multiplier gives the average number of SLOC per function point for that language.  If the implementation language is chosen, one can estimate SLOC by multiplying the adjusted function point count by the language multiplier.

The Backfire Method is not part of the formal Function Point Analysis as defined by IFPUG. In COSMOS, however, the Backfire Method is used along with the Function Point Analysis, and is implemented in the Function Point Model.

## Added, Changed, and Deleted Functionality

A software development project can basically do three things, separately or in combination:

- Functionality can be added – new functionality. (If the application does not already exist, this is all that can be done)

- Functionality can be changed – different functionality.

- Functionality can be deleted – removed functionality.

All three of these possibilities are reflected in IFPUG’s formula for the function points of a development project with software enhancement:

EFP = [ ( ADD + CHGA + CFP ) * VAFA ] + ( DEL * VAFB )

where:

EFP = Enhancement project function point count

ADD = Unadjusted function point count of added functionality

CHGA = Unadjusted function point count of changed functionality, after the project

CFP = Unadjusted function point count of conversion functionality

DEL = Unadjusted function point count of deleted functionality

VAFA = Value adjustment factor, after the project

VAFB = Value adjustment factor, before the project

If the project only includes new development – added functionality – the formula for the project function point count reduces to:

DFP = ( UFP + CFP ) * VAF

where:

DFP = Development project function point count

UFP = Unadjusted function point count of new functionality

CFP = Unadjusted function point count of conversion functionality

VAF = Value adjustment factor

In a COSMOS function point model (and project), only one VAF is computed.  Because of this, COSMOS projects have one restriction: Deleted functionality cannot be included in the same project as added functionality and changed functionality.  If application functionality must be deleted, that must be estimated as a separate project with its own general system characteristic settings (and VAF value).  This is because in IFPUG’s formula for computing the function point of a development project, deleted function points are adjusted by the VAF of the application before the project, not after.

It is perfectly fine to include added functionality and changed functionality in the same COSMOS project.

## Comparison of Function Points and SLOC

Studies suggest that for most software development efforts, the “size” of the delivered software is the primary determining factor for the required effort and schedule.  Size is by no means the only factor, but it seems to a greater influence than all others.  Therefore, the measurement of the size of a software development project is the key to accurate estimation of effort and schedule.  There are two major sizing metrics: Source Lines of Code (SLOC) and Function Points.

As an external metric, function point analysis does not rely on implementation technology or detailed system design.  In contrast, SLOC is an internal metric.  By its very nature, one must have access to specific software internals to measure SLOC.  Furthermore, it is difficult to estimate SLOC precisely from system requirements, not without a good deal of assumptions about the implementation technology and system design, and even then with very limited accuracy.  This makes SLOC a difficult metric to use for planning and budgeting purposes, where estimates are desired (or required) before enough is known about the software to produce an accurate SLOC estimate.  Quoting from NASA's Parametric Cost Estimating Handbook:

"One significant problem with the COCOMO, PUTNAM and similar models is that they are based on knowing, or being able to estimate accurately, the size (in lines of code) of the software to be developed. There is often great uncertainty in the software size."

Function points, on the other hand, are directly tied to user-specified requirements and are expressed entirely in terms of logical data groups and automated business processes.  This means that function points can be counted, accurately, very early in the software development cycle.  Function points can be counted from requirements produced during the analysis phase, and can be estimated from ‘sketchy’ proposal statements.  This makes function point analysis very useful for project planning and budgeting purposes — activities that occur before a detailed design could have emerged.

Unlike SLOC, there is a standard and uniform methodology with detailed guidance for counting function points, the IFPUG Counting Practices Manual.  The Manual is supplemented by a number of detailed case studies that demonstrate the application of function point analysis to a number of actual software specifications of various types.   (There are case studies for database applications, systems based on structured analysis and design, systems based on object-oriented analysis and design, systems with GUIs, real time systems, etc.)  These standard counting practices foster a high degree of consistency between different counts taken at different times or on different projects or applications.  There is nothing like this level of consistency or rigor in counting or estimating SLOC.

Numerous case studies and feedback from industry verifies that there is a high correlation between a project’s function point count and the level of effort required to complete the project.  Therefore, it is reasonable to substitute function points in place of SLOC for parametric cost models that require SLOC counts as input, such as the COCOMO and Rayleigh models.  The Backfire Method is the means of making such a substitution.

Because function points are not tied to any specific design or implementation technology, they can be used to compare different design alternatives at a high level without the need for normalization.

Historically, SLOC has been widely used for software sizing.  The COCOMO model employed by COSMOS uses SLOC as the primary input.  But as we have discussed above, there are difficulties in using SLOC for software project cost and schedule estimation.  Function points are superior for that purpose, and have other advantages as well.  One would like to use the COCOMO model with its high level of field calibration and its exploration of relevant cost driver factors, along with function point analysis which can be determined accurately in the planning phases of software development.  Using the Backfire Method, COSMOS links function point analysis to the COCOMO model, giving users the benefits of both.

## COSMOS and Function Point Analysis

The COSMOS application does not help with function counting, per se -- a knowledgeable user still has to correctly identify EIs, EOs, EQs, ILFs, and EIFs of low, average, and high complexity.  COSMOS will calculate a function point count (i.e., applies complexity weights and the value adjustment factor) from the user's "raw" function counts and 14 general system characteristic settings.

COSMOS does, however, facilitate the use of function point analysis as a project sizing technique for input into other tools.  For example, in addition to COSMOS' native estimation capabilities, one could use a function point model from COSMOS to produce a SLOC estimate for input into other models that use SLOC as an input, such as REVIC, the U.S. Air Force's implementation of COCOMO.

One can estimate effort by simply multiplying an adjusted function point count by the productivity rate (FP/month) to get an estimate — if the productivity rate is known and where function point counting measures the kind of work performed [i.e. user-defined functionality is added, removed, changed, or converted].  However, COCOMO- and Rayleigh-based models deal with relevant factors that are not directly expressed in function point analysis, and allow the exploration of the degree of effort increase associated with schedule compression.

## Function Point Formulae

### Unadjusted Function Point Count

UFPC = (3 x LEI) + (4 x AEI) + (6 x HEI) + (4 x LEO) + (5 x AEO) + (7 x HEO) + (7 x LILF) + (10 x AILF) + (15 x HILF) + (5 x LEIF) + (7 x AEIF) + (10 x HEIF) + (3 x LEQ) + (4 x AEQ) + (6 x HEQ)

where:

UFPC = Unadjusted function point count

LEI = Number of low external inputs

AEI = Number of average external inputs

HEI = Number of high external inputs

LEO = Number of low external outputs

AEO = Number of average external outputs

HEO = Number of high external outputs

LILF = Number of low internal logical files

AILF = Number of average internal logical files

HILF = Number of high internal logical files

LEIF = Number of low external interface files

AEIF = Number of average external interface files

HEIF = Number of high external interface files

LEQ = Number of low external inquiries

AEQ = Number of average external inquiries

HEQ = Number of high external inquiries

### Total Degree of Influence

The Total Degree of Influence (TDI) is the sum of selected complexity ratings for 14 project complexity traits where the ratings are as follows:

|  | None | 0 |
| --- | --- | --- |
|  | Insignificant | 1 |
|  | Moderate | 2 |
|  | Average | 3 |
|  | Significant | 4 |
|  | Strong | 5 |

### Value Adjustment Factor

The Value Adjustment Factor (VAF) is used to convert unadjusted function points into adjusted function points.  The VAF is computed from the Total Degree of Influence (TDI) as follows:

VAF=0.65+0.01⋅TDI

where:

| VAF = | Value Adjustment Factor |
| --- | --- |
| TDI = | Total Degree of Influence |

### Adjusted Function Point Count

The Adjusted Function Point Count is the function point count as adjusted to compensate for environmental conditions or circumstances that impact the software development.  The Adjusted Function Point Count is computed from the Unadjusted Function Point Count (UFPC) and the Value Adjustment Factor (VAF) as follows:

AFPC=UFPC⋅VAF

where:

| AFPC = | Number of function points |
| --- | --- |
| UFPC = | Function point count |
| VAF = | Adjusted processing complexity |

### Source Lines of Code: Backfire Method

The Backfire Method is a means of estimating the count of SLOC that is equivalent to the adjusted function point count.  SLOC is estimated from the adjusted function point count by using the selected programming language’s “language multiplier”, as follows:

SLOC=AFPC⋅LM

where:

| SLOC = | Source lines of code |
| --- | --- |
| AFPC = | Number of function points |
| LM = | Language multiplier, a function point-to-SLOC conversion constant for the selected language |

## Differences in Function Point Terminology

Earlier releases of COSMOS, through version 3.1, employed the function point terminology of the inventor of function points, Allan Albrecht, as set forth in his 1983 paper. Releases of COSMOS from version 3.2 onward use function point terminology as set forth by the International Function Point User's Group (IFPUG), except in the COSMOS Initialization File. The differences between the two terminologies may be summarized as follows:

| Albrecht 1983 | IFPUG 4.0 |
| --- | --- |
| Processing Complexity Adjustment (PCA) Unadjusted Processing Complexity (PC) Logical Internal File (LIF) Simple/Average/Complex Complexities Function Count | Value Adjustment Factor (VAF) Total Degree of Influence (TDI) Internal Logical File (ILF) Low/Average/High Complexities Function Point Count |

# Chapter 3: COCOMO Model

## COCOMO Model Description

The Constructive Cost Model, or COCOMO, was devised by Barry Boehm and associates to produce parametric estimates of software project effort and schedule. Boehm defined a hierarchy of models: basic, intermediate, and advanced. The basic COCOMO Model  is a static single-valued model which calculates development effort and cost as a function of the estimated source lines of code (SLOC  The intermediate COCOMO Model calculates development effort and cost as a function of program size in terms of estimated SLOC and a subjective assessment of 15 “cost driver” attributes. The advanced COCOMO Model includes all intermediate features plus an assessment of cost driver's impact on each phase of the system life cycle.  COCOMO is described in detail in Dr. Boehm’s landmark text, Software Engineering Economics, published in 1981. The use of COCOMO and the principles of estimating given in Software Engineering Economics are the heart of COSMOS.

As described in the previous chapter, a considerable problem with using COCOMO is the difficulty in estimating SLOC early in the software development cycle, before a detailed software design or solution has emerged.   COSMOS was invented to overcome this difficulty.  COSMOS produces a “backfired” estimate of SLOC from a project function point count.  This SLOC estimate is input into a project’s COCOMO model.  For stand-alone COCOMO models, the user is expected to supply the SLOC to be produced in the project.  Other than the use of a SLOC estimate, COSMOS implements a “pure” intermediate COCOMO model.  All three modes (organic, semidetached, and embedded) are supported.  This chapter describes the COSMOS implementation of the intermediate COCOMO model.  For more detailed information, readers are referred to Software Engineering Economics.

## COCOMO Equations

The COCOMO model has two equations, one for computing effort and the other for computing schedule.  In Intermediate COCOMO, the effort calculation is adjusted by the product of 15 cost driver rating values.  These are described below.

The equations are as follows:

| Effort: MM = A (KDSI)B  (Fi) |  | Schedule: TDEV = C (MM)D |
| --- | --- | --- |

where:

| A,B,C,D = | Intermediate COCOMO Equation Coefficients (Constants) Mode: Organic Semidetached Embedded A= 3.20 3.00 2.80 B= 1.05 1.12 1.20 C= 2.50 2.50 2.50 D= 0.38 0.35 0.32 |
| --- | --- |
| Π (Fi) = | Product of cost driver factor values, known as the Effort Adjustment Factor |
| KDSI = | Delivered source instructions, in thousands (=K SLOC |
| MM = | Effort (Man-Months |
| TDEV = | Schedule (Development Time, in Calendar Months, assuming full staffing) |

The result of the first equation, effort, is fed into the second equation to calculate schedule.

COCOMO is a statistically calibrated model.  The equation coefficients and cost driver factors are determined by regression analysis from a database of completed projects.

## SLOC and Delivered Source Instructions

The COCOMO calculations are based on estimates of a project's size in Delivered Source Instructions (DSI). DSI is defined such that:

- Only Source lines that are delivered as part of the product are included – test drivers and other support software are excluded.

- Source lines are created by the project staff -- code created by applications generators is excluded.

- One instruction is one line of code.

- Declarations are counted as instructions.

- Comments are not counted as instructions.

COSMOS uses the SLOC estimated from the backfired function point count as the value of DSI for the project’s COCOMO model.  Stand-alone COCOMO models should adhere to the above guidelines when counting or estimating SLOC.

## COCOMO Modes

COCOMO delineates software projects into three modes of development: organic, semi-detached, and embedded.

The Organic Mode is characterized by stand-alone programs with few interfaces, a stable development environment, no new algorithms, and few constraints – usually very small programs or simple projects.

The Semidetached Mode is characterized by intermediate size projects with requirements that identify some rigid constraints.  Projects that have a mixture of organic and embedded characteristics may also be said to be semidetached.

The Embedded Mode is characterized by programs with considerable interfaces, new algorithms, or extremely tight constraints – usually very large or complicated programs.  The requirements contain very strict hardware, software, and operational constraints.

## COCOMO Cost Drivers

The COCOMO intermediate model adjusts the calculation of effort by an Effort Adjustment Factor  (EAF).  The EAF is derived from 15 cost driver attributes.  The cost drivers are grouped into four major categories: product, hardware, personnel, and project attributes.  Each of the attributes is rated on influence on project complexity using a 6-point basis that ranges from very low to extra high (not all ratings are allowed for all attributes).  Based on the rating, the corresponding effort multiplier of each cost driver is used to compute the EAF.   The EAF is the product of the rating weights of the 15 cost drivers.

### Product Attributes

These are attributes of the software product you are to develop.

| Attribute | Description |
| --- | --- |
| Required Software Reliability | The degree to which software errors can be tolerated. The range for poor reliability can be from a slight inconvenience to risk to human life |
| Size of Application Database | The ratio of the data storage to the program size |
| Complexity of Product | The degree of complexity in the application's functions; Simple functions have simple expressions in the computational operations, very little nesting in the control operations, and the data management operations consist of simple arrays in main memory; Complex functions have highly nested control operations, difficult mathematical computations, dynamic data relationships in the data storage, and micro-coding for device-dependent operations |

### Hardware Attributes

These are attributes of the hardware platform you are working with.

| Attribute | Description |
| --- | --- |
| Run-Time Performance Constraints | The measurement of use of available execution time |
| Memory Constraints | The measurement of use of available storage space |
| Virtual Machine Volatility | The amount of change to the application's environment such as the operating system and hardware upgrades |
| Required Turnaround Time | The measurement of time required for feedback |

### Personnel Attributes

These are attributes of your project team members.

| Attribute | Description |
| --- | --- |
| Analyst Capability | The percentile ranking of the analyst's aptitude |
| Software Engineer Capability | The percentile ranking of the software engineer’s programming aptitude |
| Application Experience | The number of years the staff has gained background knowledge regarding the application |
| Programming Language Experience | The number of years of experience the staff has worked with the language |
| Virtual Machine Experience | The number of years of experience the staff has worked with the operating system and hardware |

### Project Attributes

These are attributes of your software development process for this project.

| Attribute | Description |
| --- | --- |
| Use of Software Tools | The richness in features of the tools being used for development; Tools can be very basic and require additional manual involvement or the tools can be quite comprehensive with automated design, documentation, and coding components |
| Application of SE Methods | The degree of commitment of the staff to using software engineering methods and modern programming practices |
| Required Development Schedule | The significance of the project delivery date; A high rating means that early delivery is very desirable or needed |

## COCOMO Complexity Influence Assignments

The following is guidance on determining the level of influence each type of cost driver has on the complexity of the project being modeled.  The first table is for the "CPLX Product complexity" cost driver, while the second table is for all other cost drivers

| COCOMO Module Complexity Ratings VS Type of Module |  |  |
| --- | --- | --- |
| Type Of Module | Description | Rating |
| Control operations | Straight-line code with a few non-nested structured programming operators: DOs, CASEs, IF-THEN-ELSEs. Simple predicates | Very low |
|  | Straightforward nesting of SP operators. Mostly simple predicates | Low |
|  | Mostly simple nesting. Some inter-module control. Decision tables | Nominal |
|  | Highly nested SP operators with many compound predicates. Queue and stack control. Considerable inter-module control | High |
|  | Reentrant and recursive coding; Fix-priority interrupt handling | Very high |
|  | Multiple resource scheduling with dynamically changing priorities; Microcode-level control | Extra high |
| Computational operations | Evaluation of simple expressions: e.g., A = B + C * (D - E) | Very low |
|  | Evaluation of moderate-level expressions: e.g., D = SQRT (B**2 - 4. * A * C) | Low |
|  | User of standard math and statistical routines; Basic matrix/vector operations | Nominal |
|  | Basic numerical analysis: multivariate interpolation, ordinary differential equations; Basic truncation, roundoff concerns | High |
|  | Difficult but structured N.A.: near-singular matrix equations, partial differential equations | Very high |
|  | Difficult and unstructured N.A.: highly accurate analysis of noisy, stochastic data | Extra high |
| Device-dependent operations | Simple read, write statements with simple formats | Very low |
|  | No cognizance of particular processor or I/O device characteristics. I/O done at GET/PUT level; No cognizance of overlap | Low |
|  | I/O processing includes device selections, status checking, and error processing | Nominal |
|  | Operations at physical I/O level (physical storage address translations, seeks, reads, etc.). Optimized I/O overlap | High |
|  | Routines for interrupt diagnosis, servicing, masking; Communication line handling | Very high |
|  | Device timing-dependent coding, micro-programmed operations | Extra high |
| Data management operations | Simple arrays in main memory | Very low |
|  | Simple file subsetting with no data structure changes, no edits, no intermediate files | Low |
|  | Multi-file input and single file output; Simple structural changes, simple edits | Nominal |
|  | Special purpose subroutines activated by data stream contents; Complex data restructuring at record level | High |
|  | A generalized, parameter-driven file structuring routine; File building, command processing, search optimization | Very high |
|  | Highly coupled dynamic relational structures; Natural data management | Extra high |

| COCOMO Software Cost Driver Ratings |  |  |
| --- | --- | --- |
| Cost Driver | Characteristics | Rating |
| RELY Required software reliability | Effect: slight inconvenience | Very low |
|  | Low, easily recoverable losses | Low |
|  | Moderate, recoverable losses | Nominal |
|  | High financial loss | High |
|  | Risk to human life | Very high |
|  | NA | Extra high |
| DATA Database size | NA | Very low |
|  | DB bytes / Program SLOC< 10 | Low |
|  | 10 <= D/P < 100 | Nominal |
|  | 100 <= D / P < 1000 | High |
|  | D/P >= 1000 | Very high |
|  | NA | Extra high |
| TIME Execution time constraint | NA | Very low |
|  | NA | Low |
|  | <= 50% use of available execution time | Nominal |
|  | 70% | High |
|  | 85% | Very high |
|  | 95% | Extra high |
| STOR Main storage constraint | NA | Very low |
|  | NA | Low |
|  | <= 50% use of available storage | Nominal |
|  | 70% | High |
|  | 85% | Very high |
|  | 95% | Extra high |
| VIRT Virtual machine volatility* | NA | Very low |
|  | Major change every 12 months Minor: 1 month | Low |
|  | Major: 6 months Minor: 2 weeks | Nominal |
|  | Major: 2 months Minor: 1 week | High |
|  | Major: 2 weeks Minor: 2 days | Very High |
|  | NA | Extra high |
| TURN Computer turnaround time | NA | Very low |
|  | Interactive | Low |
|  | Average turnaround time < 4 hours | Nominal |
|  | 4-12 hours | High |
|  | > 12 hours | Very high |
|  | NA | Extra high |
| ACAP Analyst capability** | 15th percentile | Very low |
|  | 35th percentile | Low |
|  | 55th percentile | Nominal |
|  | 75th percentile | High |
|  | 90th percentile | Very high |
|  | NA | Extra high |
| AEXP Application experience | <= 4 months experience | Very low |
|  | 1 year | Low |
|  | 3 years | Nominal |
|  | 8 years | High |
|  | 12 years | Very high |
|  | NA | Extra high |
| PCAP Programmer capability** | 15th percentile | Very low |
|  | 35th percentile | Low |
|  | 55th percentile | Nominal |
|  | 75th percentile | High |
|  | 90th percentile | Very high |
|  | NA | Extra high |
| VEXP Virtual machine experience* | <= 1 month experience | Very low |
|  | 4 months | Low |
|  | 1 year | Nominal |
|  | 3 years | High |
|  | NA | Very high |
|  | NA | Extra high |
| LEXP Programming language experience | <= 1 month experience | Very low |
|  | 4 months | Low |
|  | 1 year | Nominal |
|  | 3 years | High |
|  | NA | Very high |
|  | NA | Extra high |
| MODP Use of modern programming practices | No use | Very low |
|  | Beginning use | Low |
|  | Some use | Nominal |
|  | General use | High |
|  | Routine use | Very high |
|  | NA | Extra high |
| TOOL Use of software tools | Basic microprocessor tools | Very low |
|  | Basic mini tools | Low |
|  | Basic midi/maxi tools | Nominal |
|  | Strong maxi programming, test tools | High |
|  | Add requirements, design, management, documentation tools | Very high |
|  | NA | Extra high |
| SCED Required development schedule | 75% of nominal | Very low |
|  | 85% | Low |
|  | 100% | Nominal |
|  | 130% | High |
|  | 160% | Very high |
|  | NA | Extra high |

*  For a given software product, the underlying virtual machine is the complex of hardware and software (OS, DBMS, etc.) it calls on to accomplish its tasks

**   Team rating criteria:  analysis (programming) ability, efficiency, ability to communicate and cooperate

## COCOMO Phase Distribution

COCOMO provides a set of tables for distributing the effort and schedule to the phases of development (system engineering, preliminary design, critical design, etc.) and activities (system analysis, coding, test planning, etc.) as a percentage of the total.  The phase distribution consists of three phases: Product Design (PD) Phase, Programming Phase, and Integration and Test (I&T) Phase.

The Product Design Phase consists of hardware-software architecture determination, product specification, review, and update.  The PD phase also encompasses program design and database design.  This phase includes requirements for verification and validation (V&V), product design, models, prototypes, risk analysis, tool acquisition, contracts, personnel planning, standards, and draft high-level end-user documentation.

The Programming Phase consists of detail design, code and unit tests.  It also includes integration planning, detail test plan, test tool acquisition, complete draft user documentation, high-level code for V&V, and design change V&V.

The Integration and Test Phase consists of the integration of individual computer program components and product test.  It also includes final changes, change V&V, and acceptance test.

For more details, see Software Engineering Economics, Tables 4-1, 4.2, and 4.3, pp. 46-50.

The following phase distribution of Effort and Schedule for the Organic, Semidetached, and Embedded modes was obtained from the Software Engineering Economics,  Table 6-8, pp. 90

| Phase Distribution of Effort and Schedule (All Modes) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Effort Distribution |  | Size |  |  |  |  |
| Mode | Phase | Small 2 KDSI | Intermediate 8 KDSI | Medium 32 KDSI | Large 128 KDSI | Very Large 512 KDSI |
| Organic | Product design (%) | 16 | 16 | 16 | 16 |  |
|  | Programming (%) | 68 | 65 | 62 | 59 |  |
|  | Detailed design (%) | 26 | 25 | 24 | 23 |  |
|  | Code and unit test (%) | 42 | 40 | 38 | 36 |  |
|  | Integration and test (%) | 16 | 19 | 22 | 25 |  |
| Semidetached | Product design (%) | 17 | 17 | 17 | 17 | 17 |
|  | Programming (%) | 64 | 61 | 58 | 55 | 52 |
|  | Detailed design (%) | 27 | 26 | 25 | 24 | 23 |
|  | Code and unit test (%) | 37 | 35 | 33 | 31 | 29 |
|  | Integration and test (%) | 19 | 22 | 25 | 28 | 31 |
| Embedded | Product design (%) | 18 | 18 | 18 | 18 | 18 |
|  | Programming (%) | 60 | 57 | 54 | 51 | 48 |
|  | Detailed design (%) | 28 | 27 | 26 | 25 | 24 |
|  | Code and unit test (%) | 32 | 30 | 28 | 26 | 24 |
|  | Integration and test (%) | 22 | 25 | 28 | 31 | 34 |
| Schedule Distribution |  | 2 KDSI | 8 KDSI | 32 KDSI | 128 KDSI | 512 KDSI |
| Organic | Product design (%) | 19 | 19 | 19 | 19 |  |
|  | Programming (%) | 63 | 59 | 55 | 51 |  |
|  | Integration and test (%) | 18 | 22 | 26 | 30 |  |
| Semidetached | Product design (%) | 24 | 25 | 26 | 27 | 28 |
|  | Programming (%) | 56 | 52 | 48 | 44 | 40 |
|  | Integration and test (%) | 20 | 23 | 26 | 29 | 32 |
| Embedded | Product design (%) | 30 | 32 | 34 | 36 | 38 |
|  | Programming (%) | 48 | 44 | 40 | 36 | 32 |
|  | Integration and test (%) | 22 | 24 | 26 | 28 | 30 |

For the SLOC sizes that fall between the lower and upper bound, linear interpolation is performed to obtain the percentages.  For SLOC sizes below the lower bound, the percentages listed under the lower bound column are used.  For SLOC sizes above the upper bound, the percentages listed under the upper bound column are used.

## COCOMO Formulae

### Unadjusted Person Months

PMNOM=N1⋅SLOC1000N2

where:

| PMNOM = | Unadjusted person-months to complete project |  |  |
| --- | --- | --- | --- |
| SLOC = | Source lines of code |  |  |
|  | For Organic | For Semidetached | For Embedded |
| N1 = | 3.2 | 3.0 | 2.8 |
| N2 = | 1.05 | 1.12 | 1.20 |

### Effort Adjustment Factor

EAF = Product of all selected cost driver attribute ratings

where:

| EAF = | Effort Adjustment Factor |
| --- | --- |

### Adjusted Person Months

PMADJ=PMNOM⋅EAF

where:

| PMADJ = | Adjusted person-months to complete project |
| --- | --- |
| PMNOM = | Unadjusted person-months to complete project |
| EAF = | Effort Adjustment Factor |

### Time to Develop

TDEV=2.5⋅PMADJN3

where:

| TDEV = | Estimated calendar time to complete project |  |  |
| --- | --- | --- | --- |
| PMADJ = | Adjusted person-months to complete project |  |  |
|  | For Organic | For Semidetached | For Embedded |
| N3 = | .38 | .35 | .32 |

## COCOMO II

Boehm and his associates have formulated a COCOMO II model. The description of COCOMO II is beyond the scope of this document.  Although COSMOS is based on the original COCOMO model, it has similarities with COCOMO II Phase 3 analysis, particularly in its use of function points as a sizing measure.

# Chapter 4: Rayleigh Model

## Rayleigh Distribution

The Rayleigh distribution is a curve that shows a step increase near the origin and a gradual tapering off toward zero.

The relationship has formed the mathematical basis for a number of hypotheses in physics.  The distribution also fits the general pattern of staff buildup in development projects.  One of the earliest attempts at theoretical cost analysis is the work of Peter Norden to quantify the changes in the number of people applied to a hardware project. Using project data from as far back as 1958, Norden used a theoretical reliability model to form an analogy which applied to the number of problems remaining to be solved in a task.  The result was the determination that the Wiebull distribution provided a theoretical basis for estimating the shape over time of the number of people applied to a project. His analysis was subsequently validated empirically. Lawrence Putnam (1978) applied Norden’s adaptation of the Rayleigh model, a special case of the Weibull model, to software development.  The results have been validated over a 15 year time period with thousands of real, completed projects. The Rayleigh-Norden curve is the basis for Putnam’s estimation program, the Software Lifecycle Model (SLIM) .

## Rayleigh Equations – General Description

The Rayleigh equation takes the conceptual form:

Quantity Produced = Process Productivity * Effort * Schedule

This means that the product of the time and effort, coupled with the process productivity of the development organization, determines how much functionality can be delivered.  The calculation form of the equation is expressed:

Size = Process Productivity Parameter * (Effort/B) (1/3) * Time (4/3)

where

- The Process Productivity Parameter is the development process proficiency of the organization. It is determined from historical data.

- Size is the quantity of function created in source lines of code, function points, objects, or other measures of function.

- Effort is the development effort required. It includes all categories of labor used on the project. Effort is consistent with the time specified below.

- B is a complexity adjustment factor. It provides for specialized skills for integration testing, documentation, and management as the size of the system increases.

- Time is the elapsed calendar development time from the start of detailed design until the product is ready to enter into operational service (frequently this is a 95% reliability level).

## Putnam’s Analysis: Software Equation

Putnam offers two equations for estimating software development effort and analyzing the effects of compressing or expanding the schedule.  The first equation, which he calls the Software Equation, can be used to compute the development effort required and therefore the cost.

Effort = (B*Size3) / [(Time4)*(Productivity Measure3)]

This equation requires the size of the project in source lines of code (SLOC) and the time for development in years as inputs. The equation also has two other parameters. The first parameter, the special skills factor (B), is directly related to the size in SLOC. Putnam provides a table for looking up this value. The second parameter, the Productivity Measure (PM), is related to the type of system that is being developed. Putnam provides two tables for computing this value. The first table shows the values for the productivity measure divided into 40 levels called the Productivity Index (PI). These levels are then related to project type in the second table. This table lists several types of applications and their associated productivity index (circa 1990). The table also gives a standard deviation for each. The standard deviation can be used to compute a range for effort given values for size and time. The inputs that the user must provide are the application type (or the user must directly choose PI or PM), the size in SLOC (either entered directly or computed from function point analysis/backfiring), and the time scheduled for the project in years. The output would be the effort required in person years and a range using the standard deviation.

## Manpower Buildup Index

The second equation uses the effort in person years, the size in SLOC, and the special skills factor to compute a Manpower Buildup Index (MBI) Parameter that can be expressed in six MBI Levels.

MBI Parameter = Effort / (B*Size3)

MBI Level = log2 (MBI Parameter) - 2

The MBI Level is the binary logarithm of the MBI Parameter minus 2.  The MBI Level is a smaller number that is coarser grain than the MBI Parameter, and thus more appropriate for reports to management.  For convenience, Putnam provides a table relating the two values. The MBI is an expression of how manpower is applied to the development effort. An MBI of one represents a schedule that is stretched out and uses a slow buildup of manpower. An MBI of six represents a schedule that is to be compressed by throwing people at the project. MBI Levels of greater than six generally indicate the proposed schedule is too ambitious to succeed for the size of project and type of application, no matter what staffing level is used.

## Rayleigh Model

COSMOS implements a simplified Rayleigh Model for the sole purpose of calculating the Manpower Buildup Index (MBI) Level.

The MBI Level may be qualitatively characterized as follows:

| MBI Level | Staff Buildup | Effort Effect | Schedule Effect | Error Effect |
| --- | --- | --- | --- | --- |
| < 0 | Extremely Slow | Lower | Higher | Lower |
| 0 | Very Slow |  |  |  |
| 1 | Slow |  |  |  |
| 2 | Moderate Slow |  |  |  |
| 3 | Moderate |  |  |  |
| 4 | Moderate Aggressive |  |  |  |
| 5 | Aggressive |  |  |  |
| 6 | Most Aggressive |  |  |  |
| > 6 | Unrealistic | Higher | Lower | Higher |

## Development Phases

Putnam separates projects into three separate phases: Feasibility Studies, Functional Design, and Main Build.  The Feasibility Studies phase outlines project specifications and plans.  The Functional Design phase records functional design specifications, test plans, and management plants.  The Main Build phase begins at the start of detail logic design and ends when the system is fully operational.  Putnam’s Rayleigh analysis is only applicable to the Main Build phase, which is typically 75% of the total schedule.  COSMOS users may specify a percentage of the total schedule taken up by the main build phase.  The default is 75%.

## Application Type and Productivity

In Rayleigh-Putnam analysis, the “productivity” of the development organization is a key concept.  Putnam determined that the productivity measure is generally dependent upon the type of application being developed.  Putnam gives a table defining several common application types with their associated productivity measures. Another table is given which relates productivity measure values to productivity index values, which range from one to forty.   (The productivity index is a logarithmic function of the productivity measure.)  The productivity index is a smaller number that is more intuitable and thus better suited for reports to management.

Productivity measures are determined from historic data.  COSMOS users with their own historic completed project database can specify their own productivity measure or productivity index values by selecting the “User-specified” Application Type.

## Rayleigh Formulae

### Software Equation

The Software Equation (SE) calculates the Effort.

SE=B⋅SIZE3TIME4⋅PM3

where:

| SE = | Estimated effort to complete project |
| --- | --- |
| B = | Skills Factor Value |
|  | The Skills Factor value is directly related to SIZE and was obtained from an article by Lawrence H. Putnam in the Encyclopedia of Software Engineering, 1994, pages 994-995. |
| SIZE = | Source Lines of Code |
| TIME = | Schedule |
| PM = | Productivity Measure Value |
|  | The Productivity Measure value was obtained from Table 1 and Table 2 from an article by Lawrence H. Putnam in the Encyclopedia of Software Engineering, 1994, page 995. |

### Manpower Buildup Index Equation

MBIParameter=EffortB⋅TIME3

MBILevel=Log2MBIParameter−2

where:

| MBI = | Manpower Buildup Index |
| --- | --- |
| B = | Skills Factor Value |
|  | The Skills Factor value is directly related to SIZE and was obtained from an article by Lawrence H. Putnam in the Encyclopedia of Software Engineering, 1994, pages 994-995. |
| TIME = | Schedule |

# Chapter 5: Project Estimation

## Overview

Software development projects are estimated in COSMOS using a Function Point Model, a COCOMO Model, and a Rayleigh Model.  Each project file contains these three models. The following diagram shows how a COSMOS Project model works:

## Model Interrelationships

The user supplies function counts (by type and complexity) and settings for the 14 General System Characteristics (GSC).  The user also specifies the language to be used in the implementation.  The function point model is used to size the project and produce an estimate of SLOC using the Backfire Method.  The SLOC estimate is fed to the project’s COCOMO model.  The user supplies the development mode and cost driver ratings to the COCOMO model.  COCOMO produces an estimate of effort and schedule, and optionally, a phase distribution breakdown of effort and schedule. The SLOC estimate from the function point model, as well as the schedule from the COCOMO model, are fed into the project’s Rayleigh model.  The user also supplies the application type or productivity information, and the percentage of the time spent in the Main Build Phase of development (which is covered by the Rayleigh Model).  From these, the Rayleigh model computes a Manpower Buildup Index for the project.

## Import and Export of Models

Stand-alone models – Function Point, COCOMO, and Rayleigh – can be imported into a project.

- When a function point model is imported, its SLOC estimate is used in the project.  The COCOMO and Rayleigh analysis is re-calculated based on the imported function point model’s SLOC estimate.

- When a COCOMO model is imported, the project’s SLOC estimate replaces the imported model’s SLOC value, the effort and schedule are re-calculated.  These are reported and used in the subsequent Rayleigh recalculation.

Models within a project can also be exported to stand-alone models for use in other projects. The import/export capability allows the user to explore different scenarios for a project without extensive re-specification of parameters.

## Project Report

A Project Estimation Report (with all Display Options on) shows Function Point, COCOMO, and Rayleigh informatiion on the project.  A representative report is shown below

Phase Distribution

Product Design Phase

Adjusted Effort:	1625.5 person months		(1355.0 - 1900.9)

Schedule:		17.3 calendar months		(16.2 - 18.3)

Average Staff:	93.9 FSP			(83.4 - 104.0)

Programming Phase

Adjusted Effort

Detailed Design:	2199.2 person months		(1833.2 - 2571.9)

Code and Unit Test:	2772.9 person months		(2311.5 - 3242.8)

Schedule:		24.7 calendar months		(23.2 - 26.1)

Average Staff:	201.1 FSP			(178.6 - 222.6)

Integration and Test Phase

Adjusted Effort:	2964.1 person months		(2470.9 - 3466.4)

Schedule:		19.8 calendar months		(18.6 - 20.9)

Average Staff:	149.8 FSP			(133.1 - 165.9)

RAYLEIGH INFORMATION:

Title:				Flight Test System

Prepared By:		Dilbert Adams

Description:		Rayleigh analysis for final user interface.

Sensitivity Analysis Type:	Productivity Measure (PM)

Source Lines of Code:	714408.2			(607247.0 - 821569.4)

Time to Develop (TDEV):	61.8 calendar months		(58.0 - 65.3)

Main Build Phase Time

(75% of TDEV):		46.4 calendar months		(43.5 - 49.0)

Application Type:		Scientific systems

Manpower Buildup Index

(MBI) Level:		2			(1 - 4)

:

# Chapter 6: System Estimation

## System Description

Beginning with version 4.1, COSMOS supports the estimation of collection of projects that are developed together as a single System.  (When referring to a System-level development in this document, the word “System” will be capitalized to differentiate it as a COSMOS estimation entity.)  The projects are assumed to each form part of an incremental development of a single software design.  Typically only minor design changes or refinements are made following the emergence of the primary System product design.   The projects within the System operate as they do elsewhere within COSMOS, as described above.  However, there are extra complexities posed by System level estimation.  These are described in this chapter.

In COSMOS, a System is composed of an array or collection of projects.  The report of System-Level Information reports the size of the System in function points and SLOC, as well as the effort and schedule required to produce the System.  An MBI level for the System is obtained from a weighted average of project MBI levels.  The System’s combined effort and schedule estimates are obtained from a combination of project-level estimates and user-specified values.  The method of calculating estimates is slightly different for effort and schedule, so these will be described separately.   To understand these methods, the software phases involved in System development must be described.

## System Development Phases

Conceptually, the development of the System is assumed to have distinct phases.  The estimation of System-level development is built from the estimates associated from these phases.  This is not to say that the System development is constrained to follow the phases given below – they are merely a convenient framework for constructing realistic estimates.  One might expect, however, that the typical incremental System development endeavor to encompass these activities:

- System-level Product Design – A planned incremental approach to System development often calls for the development team to compose an overall Product Design, which is piece-wise refined, constructed, and implemented with each incremental project.  Integrated projects share design, scaffolding, infrastructure, planning, and staffing – and build upon each other

- Programming followed by Integration & Testing for each Project’s software.

- Final Test and Evaluation – The System as a whole typically undergoes a period of final testing, evaluation, closeout, and/or integration into the business environment before being fully certified for production use.  This period usually follows the incremental development projects.

## System-Level Effort Estimates

The Effort for the entire System is estimated from the following:

- The System’s overall Product Design effort.  This may be either summed from the Product Design phases of the individual projects, or specified explicitly by the user.

- The System’s combined Programming effort.  This is obtained by summing the Programming phase efforts of the individual projects.

- The System’s combined project-level Integration and Test effort.  This is obtained by summing the Integration and Test phase efforts of the individual projects.

- The effort required for the System’s Final Test and Evaluation phase.  The user explicitly defines this effort.  The default value is zero, although preliminary studies indicate that for some projects a conservative estimate might require values of 25% to 30% of the combined effort for (1) through (3) above.

Effort System = Effort ProductDesignSystem

+  (EffortProgrammingProject  + EffortI&TProject)

+ Effort FinalTest&Evaluation .

## System-Level Schedule Estimates

The Schedule for the entire System is estimated from the following:

- The System’s overall Product Design schedule.  This may be either summed from the Product Design phases of the individual projects, or specified explicitly by the user.

- The System’s combined Programming schedule.  This is obtained by summing the Programming phase schedule of the individual projects.

- The project-level Integration and Test schedule of the project that finishes last (the “finish line” project, typically the last project in the System’s project array).  This is obtained from the Integration and Test phase schedule of the last project to finish.

- The schedule required for the System’s Final Test and Evaluation phase.  The user explicitly defines this schedule.   The default value is zero, although preliminary studies indicate that for some projects a conservative estimate might require values of 25% to 30% of the combined effort for (1) through (3) above.

Schedule System = Schedule ProductDesignSystem

+  (Schedule ProgrammingProject  )

+ Schedule I&TFinishLineProject

+ Schedule FinalTest&Evaluation .

The schedule calculation path  uses the increment that extends the schedule out to its furthest point, which is essentially the increment with the longest I&T schedule, which is effectively the increment with the longest overall schedule. In rare circumstances, where there are two or three short increments of approximately the same size (SLOC), the COCOMO mode may determine the schedule path increment, due to differences in I&T percentages.  The difference in approximation should be small

## System-Level Manpower Buildup Index Level

COSMOS computes a System MBI Level.  The System MBI Level is a weighted average of the Project MBI Levels.  Each project’s MBI level is scaled to its proportion in the System.  These scaled MBI levels are summed.  The calculation reduces to the following:

MBI Level System =   [ MBI Level Project   x  (SLOC Project / SLOC System) ]

=   ( MBI Level Project   x  SLOC Project ) / SLOC System

## System-Level Project Specification and Management

In addition to the Final Test and Evaluation estimates, and optionally the Product Design estimates, the user specifies which projects are included in the System.  Projects may be added to the System or deleted from it.  The System references its component projects by full file path name.  Once added, all project information is with the System as a “System Project”.  Any changes to a component project file that are made while the System is open will not be reflected in the System.  To change a project that is within a System, either the System must be closed, or else the project must be deleted from the System, and the revised project re-added.

## Schedule Compression

In an incrementally developed System, there may be overlap between successive projects.

Typical Incremental System:

| PD | PG | IT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | PD | PG | IT |  |  |  |  |  |
|  |  |  |  | PD | PG | IT |  |  |  |
|  |  |  |  |  |  | PD | PG | IT |  |
|  |  |  |  |  |  |  |  |  | F&TE |

Boehm implies that the Project Product Design (PD) is largely combined into an up-front System-level Product Design.  This gives:

| PD |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | PG | IT |  |  |  |  |
|  |  | PG | IT |  |  |  |
|  |  |  | PG | IT |  |  |
|  |  |  |  | PG | IT |  |
|  |  |  |  |  |  | F&TE |

If the overlap can be increased, the schedule can be compressed (at a cost or more effort and more defects).  This increase in project overlap is schedule compression.

A simple form of schedule compression is “Start Time Adjustment”.   A constant adjustment to the start time is applied to each project in the System.

Incremental System without Start Time Adjustment:

| PD |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | PG | IT |  |  |  |  |
|  |  | PG | IT |  |  |  |
|  |  |  | PG | IT |  |  |
|  |  |  |  | PG | IT |  |
|  |  |  |  |  |  | F&TE |

Incremental System with Start Time Adjustment:

| PD |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | PG | IT |  |  |  |  |
|  |  | PG | IT |  |  |  |
|  |  |  | PG | IT |  |  |
|  |  |  |  | PG | IT |  |
|  |  |  |  |  |  | F&TE |

|	   	 | ………………………… Start Time Adjustment

| PG | IT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | PG | IT |  |  |  |  |
|  |  | PG | IT |  |  |  |
|  |  |  | PG | IT |  |  |
|  |  |  |  |  |  | F&TE |

|--Compression --|

“Start Time Adjustment” is an enhancement planned for a later version of COSMOS.

## System Development and COCOMO

The employment of incremental development is indicative of more Modern Programming Practice (MPP), and this would be reflected by the "Use of Software Engineering Methods" [MODP] cost driver for the projects that are developed as a System (i.e., projects that are included within a System level estimation).  This impacts the effort and schedule of the projects involved.

What about the impact of incremental development on staffing?  In Software Engineering Economics (p 42) Boehm writes

The implications of incremental development to software cost estimation are primarily in the time phasing of project effort  ...  The main result of this modification is to level out the labor distribution curve on software projects.  Instead of the classical Rayleigh curve distribution of labor over time ... one has a more flattened labor distribution curve ...

Boehm implies that in incremental development, much of the feasibility study, planning, requirements analysis, and [general] product design is done "up front", and does not need to be repeated (or only suffers small modification) for subsequent increment Projects.  The quotation above suggests that the MBI Level is of less importance for Systems than for individual projects.  However, the System development is composed of distinct projects, and in the execution of each project the staff buildup is a factor that ought to be considered.  COSMOS computes an overall, or weighted, MBI Level for the System.  If one or more projects have high MBI Levels and these projects are an appreciable part of the overall effort, this will be revealed in the overall System MBI Level.  However, if a project is a small portion of the effort but crucial to the System, COSMOS users are encouraged to consult the project’s individual MBI Level in the interest of evaluating the risk to the System development.

Software breakage is the amount of software that is broken and must be replaced during subsequent development (Software Engineering Economics, p 56).  If we assume that no software need be deleted, or that deleted functionality is isolated within separate projects, COSMOS handles incremental projects that include breakage (i.e. changed functionality) as part of the raw function count.

Boehm recommends that wherever possible one should reduce the scale of a software project (Software Engineering Economics, p 191).  Incremental development is a way to do this. Each software feature should be evaluated as "investment", "high payoff", or "diminishing returns" (pp193-194).  A feature in the diminishing returns category should be dropped.  The remaining features should be evaluated to see if they could be deferred to a later increment of the software development (without jeopardizing product viability), thus reducing the scale of the present increment.

## System Output Report

The output for a System Level Estimation Report (with intermediate totals enabled) lists the Cumulative TDEV as well as Project Summary Information section. A representative full report (all Display Options on) will appear as follows:

SYSTEM LEVEL ESTIMATION INFORMATION:

Title:			Flight Test System

Prepared By:		Dilbert Adams

Description:		Project 1 - Initial user interface

Project 2 - Low level processes

Project 3 - Interprocess communications

Project 4 - Final user interface

Total Adj. Function Points:	33649.5

Total Source Lines of Code:	1783422.4

Total Adj. Effort:		26118.5 person months

Cumulative Time to Develop (calendar months)

Product Design:		12.3

Project Number		Programming		Integration & Test

1			18.7			22.7

2			31.8			42.9

3			49.6			66.2

4			74.3			94.1

Final Test and Eval.:	103.0

Total Time to Develop:	103.0 calendar months

System Manpower Buildup

Index (MBI) Level:	3

PROJECT SUMMARY INFORMATION:

Project	Adjusted	SLOC	Prog.	I&T	Prog.	I&T	MBI

Number	FP		Effort	Effort	TDEV	TDEV	Level

1		531.3	28157.8	169.8	85.8	6.4	4.0	2

2		5424.2	287480.5	2519.5	1632.9	13.2	11.0	3

3		14214.6	753375.9	7723.4	5470.8	17.7	16.6	4

4		13479.4	714408.2	4972.1	2964.1	24.7	19.8	2

# References

1.	Albrecht, Allan J. and John E. Gaffney, Jr., "Software Function, Source Lines of Code and Development Effort Prediction: A Software Science Validation," IEEE Transactions on Software Engineering, Volume SE-9, No. 6, November, 1983.

2.	Boehm, Barry W., "Software Engineering Economics,"  IEEE Transactions on Software Engineering, Volume SE-10, Number 1, January, 1984, pp. 4-21.

3.	Boehm, Barry W., Software Engineering Economics, 1981, Prentice-Hall, Inc.  A Simon & Schuster Company.  Upper Saddle River, New Jersey 07458, ISBN 0-13-822122-7.

5.	International Function Point Users Group, "Function Point Counting Practices Manual" (Release 4.0), January 1994.

6.	Lawrence H. Putnam, "Rayleigh Model," Encyclopedia of Software Engineering,1994, pp. 992-1000.

8.	Jones, Capers, "Backfiring: Converting Lines of Code to Function Points," Computer, November, 1995, pp. 87-88.

9.	Pressman, Roger, Software Engineering: A Practitioners Approach, 3rd edition, McGraw-Hill, New York, NY, 1992.

10.	Thayer, Richard H., Tutorial: Software Engineering Project Management, IEEE Computer Society Press, Los Alamitos, CA, 1988.

# Glossary

## Analyst

A person whose role is the investigation and determination of a user's needs. The findings of the analyst form the basis of the Software Requirements Specification (SRS) of an application.

## COCOMO

The Constructive Cost Model, published in 1981 by Dr. Barry Boehm, which defines a method of estimating required software project effort and schedule, given project lines of code.

## COCOMO Model

A saved collection of descriptive information, COCOMO attributes, COCOMO cost driver  attribute ratings and the resulting effort and project time estimates.

## COCOMO Model Type

The type of COCOMO Model  used.  Model types may be Basic, Intermediate, or Advanced.  Currently, COSMOS only uses the Intermediate COCOMO model type.

## COCOMO Phase Distribution

The Phase Distribution consists of three phases: Product Design Phase, Programming Phase, and Integration and Test Phase.

## Component

A Function Point Model, a COCOMO Model, Rayleigh Model, or a Project.

## Constructive Cost Model

See COCOMO Model.

## Cost Driver

A factor which may have a positive or negative impact on the effort required to complete a software development project.

## EAF

See Effort Adjustment Factor.

## Effort Adjustment Factor

The product of all COCOMO cost driver attribute effort multipliers, used to adjust the project person months  in Intermediate and Advanced COCOMO.

## Embedded Mode

A classification in COCOMO used for ambitious projects from unfamiliar, unforgiving, and tightly constrained environments.

## External Input

A user data type or user control type that crosses the application boundary and adds, modifies, or deletes internal logical files. The input is unique if either the input format or the processing logic is unique. An external input can have a ranking of low, average or high.

## External Inquiry

Either (1) an input/output combination that crosses the application boundary and retrieves data or (2) control information for immediate response. The inquiry does not modify data. An external inquiry can have a ranking of low, average or high.

## External Interface File

A set of logically related data used outside the application. An external interface file can have a ranking of low, average or high.

## External Output

A user data type or user control type that leaves the application boundary. The output is unique if the input format or the processing logic is unique.  Output can be files, reports, or messages sent to users or to other applications. An external output can have a ranking of low, average or high.

## Function Point Model

A saved collection of descriptive information, input/output/file counts,  value adjustment factors, and the resulting function point  count and estimated lines of code.

## Function Points

A measure of the amount of function a software system is to perform, developed by Allan J. Albrecht.  The number of function points a system has is a weighted sum of the number of inputs, outputs, files, and inquiries provided to or generated by the system.

## General System Characteristics

A set of 14 characteristics that are intended to take into account special requirements placed on the application.  The Value Adjustment Factor (used to adjust a function point count) is determined from the ratings of the 14 General System Characteristics (GSCs).

## GSC

See General System Characteristics.

## Internal Logical File

A set of logically related data used inside the application. A internal logical file can have a ranking of low, average or high.

## Main Build Phase

Main Build Phase is one of the three phases of the Rayleigh approach.  This phase begins at the start of the detail logic design and ends when the system is fully operational.  These phases lead to the calculation of the Manpower Buildup Index.

## Model

Either a Function Point Model, a COCOMO Model, or a Rayleigh Model.

## Organic Mode

A classification used in COCOMO to describe projects which come from stable, familiar, forgiving, and relatively unconstrained environments.

## Person Month

A unit of measurement for effort used in estimating schedules.  This is the amount of work a single person can do in one calendar month.

## Project

A combination of one Function Point Model, one COCOMO Model, and one Rayleigh Model  plus descriptive information about the project.  The source lines of code calculated in the Function Point Model serve as an input to the COCOMO Model and to the Rayleigh Model.

## Rayleigh Model

A saved collection of descriptive information, Rayleigh attributes, and the resulting manpower buildup estimate.

## Reverse Engineering

"What-if" analysis on a model to test the impact of scheduling or other constraints on the model.

## Semi-detached Mode

A classification used in COCOMO for intermediate-sized projects which have some rigid constraints.

## Sensitivity Analysis

Adjustment of a model or project to allow an estimated range to be produced based on uncertain model inputs.

## SLOC

See source lines of code.

## Software Engineer

A person educated, trained and/or experienced in the analysis, design, coding, testing, and documentation techniques of developing software applications.

## Software Reliability

The probability that a software will perform its functions without error.

## Source Lines of Code

The number of lines of code delivered for a project, excluding comment lines.

## System

A collection of one or more projects which implement an incrementally designed and constructed software system.

## TDEV

Time of development in calendar months.

## Turnaround Time

The time between the submission of a request and the return of the results.

## Virtual Machine

A term used in the COCOMO Model  in reference to the hardware and operating system environment of an application.

# Appendix: COSMOS INItialization File Entries

## COSMOS.INI

The COSMOS software is delivered with an initialization file, COSMOS.INI, which contains default values for various parameters.  When a new Model, Project, or System Level Estimation is created, the parameter values from the COSMOS.INI file are copied into the Model , Project, or System file.  You may customize COSMOS by changing these values.

You may also use the Language Customization Dialog Box to modify the languages and multipliers used by COSMOS.

## Default Values

This section lists the default values as they are delivered with COSMOS

[COSMOS]
Version=4.1

[Extensions]
Project_Ext        =.PRJ
Function_Point_Ext =.FPM
COCOMO_Ext         =.CCM
Rayleigh_Ext       =.RLM
System_Ext         =.SLE

[FunctionCounts]
External_Input_Simple_Mult      =3
External_Input_Average_Mult     =4
External_Input_Complex_Mult     =6
External_Output_Simple_Mult     =4
External_Output_Average_Mult    =5
External_Output_Complex_Mult    =7
Logical_Internal_Simple_Mult    =7
Logical_Internal_Average_Mult   =10
Logical_Internal_Complex_Mult   =15
External_Interface_Simple_Mult  =5
External_Interface_Average_Mult =7
External_Interface_Complex_Mult =10
External_Inquiry_Simple_Mult    =3
External_Inquiry_Average_Mult   =4
External_Inquiry_Complex_Mult   =6

[Languages]
LanguageName00 =Ada 83
LanguageMult00 =71
LanguageName01 =Ada 9X
LanguageMult01 =49
LanguageName02 =Algol
LanguageMult02 =107
LanguageName03 =APL
LanguageMult03 =32
LanguageName04 =Assembly - Basic
LanguageMult04 =320
LanguageName05 =Assembly - Macro
LanguageMult05 =213
LanguageName06 =Basic - Compiled
LanguageMult06 =91
LanguageName07 =Basic - Interpreted
LanguageMult07 =128
LanguageName08 =C
LanguageMult08 =128
LanguageName09 =C++
LanguageMult09 =53
LanguageName10 =CMS2
LanguageMult10 =107
LanguageName11 =ANSI Cobol 85
LanguageMult11 =107
LanguageName12 =Database
LanguageMult12 =40
LanguageName13 =First generation
LanguageMult13 =320
LanguageName14 =Forth
LanguageMult14 =64
LanguageName15 =Fortran 77
LanguageMult15 =107
LanguageName16 =Generators
LanguageMult16 =16
LanguageName17 =Jovial
LanguageMult17 =107
LanguageName18 =Lisp
LanguageMult18 =64
LanguageName19 =Modula 2
LanguageMult19 =80
LanguageName20 =Pascal
LanguageMult20 =91
LanguageName21 =PL/1
LanguageMult21 =80
LanguageName22 =Prolog
LanguageMult22 =64
LanguageName23 =Quick Basic
LanguageMult23 =58
LanguageName24 =Screen painters
LanguageMult24 =6
LanguageName25 =Smalltalk
LanguageMult25 =21
LanguageName26 =Spreadsheets
LanguageMult26 =6
LanguageName27 =SQL
LanguageMult27 =13
LanguageName28 =Visual Basic (v3)
LanguageMult28 =40
LanguageName29 =Visual Basic (v4)
LanguageMult29 =36
LanguageName30 =Visual Basic (v5)
LanguageMult30 =29


[Development_Mode_Constants]
Organic_PM_Nom_Mult      = 3.20
Organic_PM_Nom_Exp       = 1.05
Organic_TDEV_Mult        = 2.50
Organic_TDEV_Exp         = 0.38
Semidetached_PM_Nom_Mult = 3.00
Semidetached_PM_Nom_Exp  = 1.12
Semidetached_TDEV_Mult   = 2.50
Semidetached_TDEV_Exp    = 0.35
Embedded_PM_Nom_Mult     = 2.80
Embedded_PM_Nom_Exp      = 1.20
Embedded_TDEV_Mult       = 2.50
Embedded_TDEV_Exp        = 0.32

[Product_CDA_Group]
Product_CDA_Name00    =Required Software Reliability
Product_CDA_VL_Mult00 =0.75
Product_CDA_L_Mult00  =0.88
Product_CDA_N_Mult00  =1.00
Product_CDA_H_Mult00  =1.15
Product_CDA_VH_Mult00 =1.40
Product_CDA_EH_Mult00 =NA
Product_CDA_Name01    =Size of Application Database
Product_CDA_VL_Mult01 =NA
Product_CDA_L_Mult01  =0.94
Product_CDA_N_Mult01  =1.00
Product_CDA_H_Mult01  =1.08
Product_CDA_VH_Mult01 =1.18
Product_CDA_EH_Mult01 =NA
Product_CDA_Name02    =Complexity of Product
Product_CDA_VL_Mult02 =0.70
Product_CDA_L_Mult02  =0.85
Product_CDA_N_Mult02  =1.00
Product_CDA_H_Mult02  =1.15
Product_CDA_VH_Mult02 =1.30
Product_CDA_EH_Mult02 =1.65

[Hardware_CDA_Group]
Hardware_CDA_Name00    =Run-time Performance Constraints
Hardware_CDA_VL_Mult00 =NA
Hardware_CDA_L_Mult00  =NA
Hardware_CDA_N_Mult00  =1.00
Hardware_CDA_H_Mult00  =1.11
Hardware_CDA_VH_Mult00 =1.30
Hardware_CDA_EH_Mult00 =1.66
Hardware_CDA_Name01    =Memory Constraints
Hardware_CDA_VL_Mult01 =NA
Hardware_CDA_L_Mult01  =NA
Hardware_CDA_N_Mult01  =1.00
Hardware_CDA_H_Mult01  =1.06
Hardware_CDA_VH_Mult01 =1.21
Hardware_CDA_EH_Mult01 =1.56
Hardware_CDA_Name02    =Virtual Machine Volatility
Hardware_CDA_VL_Mult02 =NA
Hardware_CDA_L_Mult02  =0.87
Hardware_CDA_N_Mult02  =1.00
Hardware_CDA_H_Mult02  =1.15
Hardware_CDA_VH_Mult02 =1.30
Hardware_CDA_EH_Mult02 =NA
Hardware_CDA_Name03    =Required Turnaround Time
Hardware_CDA_VL_Mult03 =NA
Hardware_CDA_L_Mult03  =0.87
Hardware_CDA_N_Mult03  =1.00
Hardware_CDA_H_Mult03  =1.07
Hardware_CDA_VH_Mult03 =1.15
Hardware_CDA_EH_Mult03 =NA

[Personnel_CDA_Group]
Personnel_CDA_Name00    =Analyst Capability
Personnel_CDA_VL_Mult00 =1.46
Personnel_CDA_L_Mult00  =1.19
Personnel_CDA_N_Mult00  =1.00
Personnel_CDA_H_Mult00  =0.86
Personnel_CDA_VH_Mult00 =0.71
Personnel_CDA_EH_Mult00 =NA
Personnel_CDA_Name01    =Applications Experience
Personnel_CDA_VL_Mult01 =1.29
Personnel_CDA_L_Mult01  =1.13
Personnel_CDA_N_Mult01  =1.00
Personnel_CDA_H_Mult01  =0.91
Personnel_CDA_VH_Mult01 =0.82
Personnel_CDA_EH_Mult01 =NA
Personnel_CDA_Name02    =Software Engineer Capability
Personnel_CDA_VL_Mult02 =1.42
Personnel_CDA_L_Mult02  =1.17
Personnel_CDA_N_Mult02  =1.00
Personnel_CDA_H_Mult02  =0.86
Personnel_CDA_VH_Mult02 =0.70
Personnel_CDA_EH_Mult02 =NA
Personnel_CDA_Name03    =Virtual Machine Experience
Personnel_CDA_VL_Mult03 =1.21
Personnel_CDA_L_Mult03  =1.10
Personnel_CDA_N_Mult03  =1.00
Personnel_CDA_H_Mult03  =0.90
Personnel_CDA_VH_Mult03 =NA
Personnel_CDA_EH_Mult03 =NA
Personnel_CDA_Name04    =Programming Language Experience
Personnel_CDA_VL_Mult04 =1.14
Personnel_CDA_L_Mult04  =1.07
Personnel_CDA_N_Mult04  =1.00
Personnel_CDA_H_Mult04  =0.95
Personnel_CDA_VH_Mult04 =NA
Personnel_CDA_EH_Mult04 =NA

[Project_CDA_Group]
Project_CDA_Name00    =Use of Software Engineering Methods
Project_CDA_VL_Mult00 =1.24
Project_CDA_L_Mult00  =1.10
Project_CDA_N_Mult00  =1.00
Project_CDA_H_Mult00  =0.91
Project_CDA_VH_Mult00 =0.82
Project_CDA_EH_Mult00 =NA
Project_CDA_Name01    =Use of Software Tools
Project_CDA_VL_Mult01 =1.24
Project_CDA_L_Mult01  =1.10
Project_CDA_N_Mult01  =1.00
Project_CDA_H_Mult01  =0.91
Project_CDA_VH_Mult01 =0.83
Project_CDA_EH_Mult01 =NA
Project_CDA_Name02    =Required Development Schedule
Project_CDA_VL_Mult02 =1.23
Project_CDA_L_Mult02  =1.08
Project_CDA_N_Mult02  =1.00
Project_CDA_H_Mult02  =1.04
Project_CDA_VH_Mult02 =1.10
Project_CDA_EH_Mult02 =NA

[UserDef_CDA_Group]

[Filter_Values]
Description           =ON
FpmCcmDescription     =ON
Totals                =ON
Intermediate_Totals   =ON
SensitivityAnalysis   =OFF
PhaseDistribution     =OFF

[Application_Types]
Application_Type_Name00 =Microcode systems
Application_Type_User00 =FALSE
Application_Type_Prod00 =PI
Application_Type_Val00  =2
Application_Type_SD00   =2
Application_Type_Name01 =Real-time systems
Application_Type_User01 =FALSE
Application_Type_Prod01 =PI
Application_Type_Val01  =7
Application_Type_SD01   =2
Application_Type_Name02 =Avionic systems
Application_Type_User02 =FALSE
Application_Type_Prod02 =PI
Application_Type_Val02  =6
Application_Type_SD02   =2
Application_Type_Name03 =Command and control systems
Application_Type_User03 =FALSE
Application_Type_Prod03 =PI
Application_Type_Val03  =10
Application_Type_SD03   =3
Application_Type_Name04 =Process control systems
Application_Type_User04 =FALSE
Application_Type_Prod04 =PI
Application_Type_Val04  =10
Application_Type_SD04   =4
Application_Type_Name05 =Telecom/Message switching systems
Application_Type_User05 =FALSE
Application_Type_Prod05 =PI
Application_Type_Val05  =11
Application_Type_SD05   =3
Application_Type_Name06 =System code systems
Application_Type_User06 =FALSE
Application_Type_Prod06 =PI
Application_Type_Val06  =11
Application_Type_SD06   =3
Application_Type_Name07 =Scientific systems
Application_Type_User07 =FALSE
Application_Type_Prod07 =PI
Application_Type_Val07  =12
Application_Type_SD07   =4
Application_Type_Name08 =Business systems
Application_Type_User08 =FALSE
Application_Type_Prod08 =PI
Application_Type_Val08  =16
Application_Type_SD08   =4
Application_Type_Name09 =User specified system
Application_Type_User09 =TRUE
Application_Type_Prod09 =PI
Application_Type_Val09  =16
Application_Type_SD09   =4
Selected_application=08


[Effort_PDP_Organic]
; Product Design Effort Organic
Effort_PDP_Org_S_Per00  = 0.16
Effort_PDP_Org_I_Per00  = 0.16
Effort_PDP_Org_M_Per00  = 0.16
Effort_PDP_Org_L_Per00  = 0.16
Effort_PDP_Org_VL_Per00 = NA
; Detailed Design Effort Organic
Effort_PDP_Org_S_Per01  = 0.26
Effort_PDP_Org_I_Per01  = 0.25
Effort_PDP_Org_M_Per01  = 0.24
Effort_PDP_Org_L_Per01  = 0.23
Effort_PDP_Org_VL_Per01 = NA
; Code and Unit Test Effort Organic
Effort_PDP_Org_S_Per02  = 0.42
Effort_PDP_Org_I_Per02  = 0.40
Effort_PDP_Org_M_Per02  = 0.38
Effort_PDP_Org_L_Per02  = 0.36
Effort_PDP_Org_VL_Per02 = NA
; Integration and Test Effort Organic
Effort_PDP_Org_S_Per03  = 0.16
Effort_PDP_Org_I_Per03  = 0.19
Effort_PDP_Org_M_Per03  = 0.22
Effort_PDP_Org_L_Per03  = 0.25
Effort_PDP_Org_VL_Per03 = NA

[Sched_PDP_Organic]
; Product Design Schedule Organic
Sched_PDP_Org_S_Per00   = 0.19
Sched_PDP_Org_I_Per00   = 0.19
Sched_PDP_Org_M_Per00   = 0.19
Sched_PDP_Org_L_Per00   = 0.19
Sched_PDP_Org_VL_Per00  = NA
; Programming Schedule Organic
Sched_PDP_Org_S_Per01   = 0.63
Sched_PDP_Org_I_Per01   = 0.59
Sched_PDP_Org_M_Per01   = 0.55
Sched_PDP_Org_L_Per01   = 0.51
Sched_PDP_Org_VL_Per01  = NA
; Integration and Test Schedule Organic
Sched_PDP_Org_S_Per02   = 0.18
Sched_PDP_Org_I_Per02   = 0.22
Sched_PDP_Org_M_Per02   = 0.26
Sched_PDP_Org_L_Per02   = 0.30
Sched_PDP_Org_VL_Per02  = NA

[Effort_PDP_Semidetached]
; Product Design Effort Semidetached
Effort_PDP_Sem_S_Per00     = 0.17
Effort_PDP_Sem_I_Per00     = 0.17
Effort_PDP_Sem_M_Per00     = 0.17
Effort_PDP_Sem_L_Per00     = 0.17
Effort_PDP_Sem_VL_Per00    = 0.17
; Detailed Design Effort Semidetached
Effort_PDP_Sem_S_Per01     = 0.27
Effort_PDP_Sem_I_Per01     = 0.26
Effort_PDP_Sem_M_Per01     = 0.25
Effort_PDP_Sem_L_Per01     = 0.24
Effort_PDP_Sem_VL_Per01    = 0.23
; Code and Unit Test Effort Semidetached
Effort_PDP_Sem_S_Per02     = 0.37
Effort_PDP_Sem_I_Per02     = 0.35
Effort_PDP_Sem_M_Per02     = 0.33
Effort_PDP_Sem_L_Per02     = 0.31
Effort_PDP_Sem_VL_Per02    = 0.29
; Integration Test Effort Semidetached
Effort_PDP_Sem_S_Per03     = 0.19
Effort_PDP_Sem_I_Per03     = 0.22
Effort_PDP_Sem_M_Per03     = 0.25
Effort_PDP_Sem_L_Per03     = 0.28
Effort_PDP_Sem_VL_Per03    = 0.31

[Sched_PDP_Semidetached]
; Product Design Schedule Semidetached
Sched_PDP_Sem_S_Per00      = 0.24
Sched_PDP_Sem_I_Per00      = 0.25
Sched_PDP_Sem_M_Per00      = 0.26
Sched_PDP_Sem_L_Per00      = 0.27
Sched_PDP_Sem_VL_Per00     = 0.28
; Programming Schedule Semidetached
Sched_PDP_Sem_S_Per01      = 0.56
Sched_PDP_Sem_I_Per01      = 0.52
Sched_PDP_Sem_M_Per01      = 0.48
Sched_PDP_Sem_L_Per01      = 0.44
Sched_PDP_Sem_VL_Per01     = 0.40
; Integration and Test Schedule Semidetached
Sched_PDP_Sem_S_Per02      = 0.20
Sched_PDP_Sem_I_Per02      = 0.23
Sched_PDP_Sem_M_Per02      = 0.26
Sched_PDP_Sem_L_Per02      = 0.29
Sched_PDP_Sem_VL_Per02     = 0.32

[Effort_PDP_Embedded]
; Product Design Effort Embedded
Effort_PDP_Emb_S_Per00    = 0.18
Effort_PDP_Emb_I_Per00    = 0.18
Effort_PDP_Emb_M_Per00    = 0.18
Effort_PDP_Emb_L_Per00    = 0.18
Effort_PDP_Emb_VL_Per00   = 0.18
; Detailed Design Effort Embedded
Effort_PDP_Emb_S_Per01    = 0.28
Effort_PDP_Emb_I_Per01    = 0.27
Effort_PDP_Emb_M_Per01    = 0.26
Effort_PDP_Emb_L_Per01    = 0.25
Effort_PDP_Emb_VL_Per01   = 0.24
; Code and Unit Test Effort Embedded
Effort_PDP_Emb_S_Per02    = 0.32
Effort_PDP_Emb_I_Per02    = 0.30
Effort_PDP_Emb_M_Per02    = 0.28
Effort_PDP_Emb_L_Per02    = 0.26
Effort_PDP_Emb_VL_Per02   = 0.24
; Integration Test Effort Embedded
Effort_PDP_Emb_S_Per03    = 0.22
Effort_PDP_Emb_I_Per03    = 0.25
Effort_PDP_Emb_M_Per03    = 0.28
Effort_PDP_Emb_L_Per03    = 0.31
Effort_PDP_Emb_VL_Per03   = 0.34

[Sched_PDP_Embedded]
; Product Design Schedule Embedded
Sched_PDP_Emb_S_Per00    = 0.30
Sched_PDP_Emb_I_Per00    = 0.32
Sched_PDP_Emb_M_Per00    = 0.34
Sched_PDP_Emb_L_Per00    = 0.36
Sched_PDP_Emb_VL_Per00   = 0.38
; Programming Schedule Embedded
Sched_PDP_Emb_S_Per01    = 0.48
Sched_PDP_Emb_I_Per01    = 0.44
Sched_PDP_Emb_M_Per01    = 0.40
Sched_PDP_Emb_L_Per01    = 0.36
Sched_PDP_Emb_VL_Per01   = 0.32
; Integration and Schedule Embedded
Sched_PDP_Emb_S_Per02   = 0.22
Sched_PDP_Emb_I_Per02   = 0.24
Sched_PDP_Emb_M_Per02   = 0.26
Sched_PDP_Emb_L_Per02   = 0.28
Sched_PDP_Emb_VL_Per02  = 0.30

## Customizing

This section describes what customizations can be made to new models and project through the COCOMO.INI file.

| Tip: Make a backup copy of your COSMOS.INI file before making changes. | Customization of system parameters may be done in two ways: 1. You may change the COSMOS.INI file itself (via any text editor). This will change the defaults globally for all future Models and Projects you may create. Existing Models and Projects are not affected. 2. You may change these values within an existing Model or Project file (again with any text editor). This will change the defaults for that Model or Project only. |
| --- | --- |

The following table describes the sections of the initialization file and indicates what customizations may be done to each section.

| Section Name | Description | Customization |
| --- | --- | --- |
| Extensions | Default file extensions for projects and models | Change default file extensions [not recommended] |
| FunctionCounts | Function Point Analysis complexity weights: Multipliers used to convert numbers of inputs, outputs, files, and inquiries to the unadjusted function point count | Change multiplier values (Values in the distribution INI file are IFPUG standard) [not recommended] |
| Languages | Backfire Method conversion factors: Programming languages and multiplier used to convert the adjusted function point count to SLOC | Add language/multiplier pairs (0 - 99 pairs); Change multiplier values |
| Development_Mode_ Constants | COCOMO equation coefficients: Factors used to convert unadjusted person-months to complete project estimate | Change factor values |
| Product_CDA_ Group | Product cost driver attribute names and multiplier values for computing adjusted person-months to complete project | Change cost driver names; Change multiplier values |
| Hardware_CDA_ Group | Hardware cost driver attribute names and multiplier values for computing adjusted person-months to complete project | Change cost driver names; Change multiplier values |
| Personnel_CDA_ Group | Personnel cost driver attribute names and multiplier values for computing adjusted person-months to complete project | Change cost driver names; Change multiplier values |
| Project_CDA_Group | Project cost driver attribute names and multiplier values for computing adjusted person-months to complete project | Change cost driver names; Change multiplier values |
| UserDef_CDA_ Group | User defined cost driver attribute names and multiplier values for computing adjusted person-months to complete project | Add cost drivers and multipliers; Change cost driver names; Change multiplier values |
| Filter_Values | Display Options for new models and projects | Change to ON to see item; Change to OFF to hide item |
| Application_Types | Application types and productivity information used in the Rayleigh software equation | Add/change application types and associated productivity information |
| Effort_PDP_Organic | Percentages used to compute the effort distribution for organic-mode projects | Change percentage values |
| Sched_PDP_Organic | Percentages used to compute the schedule distribution for organic-mode projects | Change percentage values |
| Effort_PDP_ Semidetached | Percentages used to compute the effort distribution for semidetached-mode projects | Change percentage values |
| Sched_PDP_ Semidetached | Percentages used to compute the schedule distribution for semidetached-mode projects | Change percentage values |
| Effort_PDP_Embedded | Percentages used to compute the effort distribution for embedded-mode projects | Change percentage values |
| Sched_PDP_Embedded | Percentages used to compute the schedule distribution for embedded-mode projects | Change percentage values |

# Index

A

Albrecht, Allen, 54

analyst, 29, 33, 55, 63

B

Backfire Method, 8, 12, 20, 22, 25, 44, 69

Boehm, Barry, 54

C

COCOMO, 6, 8, 9, 10, 11, 12, 22, 23, 26, 27, 28, 31, 32, 35, 36, 37, 43, 44, 45, 49, 52, 55, 56, 57, 58, 59, 60, 68, 69

COCOMO Equations, 27

COCOMO Formulae, 36

COCOMO Model, 6, 9, 11, 26, 43, 55, 57, 58, 59

COCOMO Model Type, 55

COCOMO Phase Distribution, 6, 35, 55

Component, 55

Constructive Cost Model, 26, 55

COSMOS.INI, 60, 68

Cost Driver, 12, 28, 32, 55

E

EAF, 28, 36, 56

Effort Adjustment Factor, 27, 28, 36, 56

Embedded Mode, 28, 56

External Input, 16, 17, 18, 19, 56

External Inquiry, 17, 19, 56

External Interface File, 15, 18, 19, 56

External Output, 16, 17, 19, 56

F

Function Point Analysis, 8, 12, 13, 20, 23, 69

Function Point Formulae, 24

Function Point Model, 6, 8, 12, 20, 43, 55, 56, 57, 58

Function Points, 12, 14, 20, 22, 54, 57

I

INI File Entries, 6

Internal Logical File, 15, 16, 17, 18, 19, 25, 57

M

Main Build Phase, 44, 57

Model, 9, 26, 38, 44, 55, 57, 58, 60, 68

O

Organic Mode, 28, 57

P

Person Month, 36, 57

Project, 6, 9, 12, 30, 43, 45, 48, 49, 50, 53, 54, 55, 58, 60, 68, 69

R

Rayleigh Equations, 38

Rayleigh Formulae, 42

Rayleigh Model, 6, 9, 11, 38, 40, 43, 44, 54, 55, 57, 58

Reverse Engineering, 58

S

Semi-detached Mode, 58

Sensitivity Analysis, 58

SLOC, 8, 9, 10, 12, 20, 22, 23, 25, 26, 27, 32, 35, 36, 39, 40, 44, 47, 49, 50, 58, 69

Software Engineer, 11, 12, 26, 29, 35, 42, 52, 54, 58, 63

Software Reliability, 29, 58, 62

source lines of code, 8, 9, 12, 20, 22, 25, 26, 39, 42, 54, 58

System, 6, 8, 10, 12, 20, 44, 47, 48, 49, 50, 51, 52, 53, 57, 59, 60

T

TDEV, 27, 53, 59, 62

Turnaround Time, 29, 59, 63

V

Virtual Machine, 29, 59, 62